## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM AMBIOK KHOLA (PARBALAKHA) TO GORUBATHAN TAR | SM/09608 | New | Material Requisition To Resource Division |  |  | RTOR000032/2021-2022 | 835/NKWSMD | 21/03/2022 |  | Resource Division | 2.46 | 0 | 0 | 0
2 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM AMBIOK KHOLA (PARBALAKHA) TO GORUBATHAN TAR | SM/09608 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED |  |  | BILL/00530/2023-2024 | BP-2023-24-321 | 25/12/2023 |  | WEST BENGAL PARIVESH CAMPA | 5.47 | 0 | 0 | 0
3 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM AMBIOK KHOLA (PARBALAKHA) TO GORUBATHAN TAR | SM/09608 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED |  |  | BILL/00530/2023-2024 | BP-2023-24-321 | 25/12/2023 |  | WEST BENGAL PARIVESH CAMPA | 5.47 | 0 | 0 | 0
4 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM AMBIOK KHOLA (PARBALAKHA) TO GORUBATHAN TAR | SM/09608 | New | P.W.S SCHEME FROM AMBOIK KHOLA (PARBALAKHA) TO GORUBATHAN TAR IN DALIM G.P. GORUBATHAN BLOCK UNDER JAL SWAPNO PROGRAMME WITHIN DISTRICT- KALIMPONG. |  |  | ORD/000105/2021-2022 | 624/NKWSMD | 21/02/2022 | 21/07/2022 | M/S. ASHOK KUMAR PERIWAL | 356.75 | 22.42 | 6.29 | 85
5 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM AMBIOK KHOLA (PARBALAKHA) TO GORUBATHAN TAR | SM/09608 | New | FOREST PAYMENT |  |  | BILL/00961/2023-2024 | BP-2023-24-645 | 28/03/2024 |  | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0 | 0
6 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM AMBIOK KHOLA (PARBALAKHA) TO GORUBATHAN TAR | SM/09608 | New | FOREST PAYMENT |  |  | BILL/00961/2023-2024 | BP-2023-24-645 | 28/03/2024 |  | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0 | 0
Total | [13 empty] | 393.33 | 22.42 | 5.7