## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM SAMTHARA KHOLA TO CENTRE GAON, PINTALAY GAON, GUDARA GAON, BICH GAON, CHETTRI GAON | SM/09612 | New | Piped Water Supply Scheme from Samthara Khola to Centre Gaon, Pintalay Gaon, Gudara Gaon, Bich Gaon and Chettri Gaon in Nimbong G.P. Block under Jal Swapno Programme within Kalimpong District | Assistant Engineer I | Junior Engineer III | ORD/000142/2021-2022 | 749/NKWSMD | 28/02/2022 | 29/05/2022 | DINESH SHERPA | 154.6 | 90.46 | 58.51 | 100
Total | [13 empty] | 154.6 | 90.46 | 58.51