## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PWSS SCHEME FROM SISNEY KHOLA TO UPPER AND LOWER KAMBAL & DINGALI GAON | SM/09613 | New | Piped Water Supply Scheme from Sisney Khola to Upper and Lower Kambal and Dingali Gaon in Yangmakum G.P. Block l, Kalimpong under Jal Swapno Programme within Kalimpong District | Assistant Engineer I | Junior Engineer IV | ORD/000143/2021-2022 | 754/NKWSMD | 28/02/2022 | 29/05/2022 | MR. DAWA LAMA | 107.34 | 81.5 | 75.93 | 80
2 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PWSS SCHEME FROM SISNEY KHOLA TO UPPER AND LOWER KAMBAL & DINGALI GAON | SM/09613 | New | Material Requisition To Resource Division |  |  | RTOR000090/2022-2023 | 1378/NKWSMD | 22/09/2022 | 22/09/2022 | Resource Division | 0.54 | 0 | 0 | 0
Total | [13 empty] | 107.88 | 81.5 | 75.55