## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM KAIJARBOTEY JHORA TO LOWER POSHYER BHASMEY | SM/09614 | New | Piped Water Supply Scheme from Kaijarbotay Jhora to Lower Poshyer Bhasmey under Tashiding G.P. Block l, Kalimpong under Jal Swapno Programme Kalimpong District |  |  | ORD/000061/2021-2022 | 452/NKWSMD | 14/01/2022 | 14/04/2022 | SUDEN TAMANG | 85.69 | 68.54 | 79.99 | 90
2 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM KAIJARBOTEY JHORA TO LOWER POSHYER BHASMEY | SM/09614 | New | Material Requisition To Resource Division |  |  | RTOR000026/2021-2022 | 660/NKWSMD | 23/02/2022 | 23/02/2022 | Resource Division | 0.33 | 0 | 0 | 0
Total | [13 empty] | 86.02 | 68.54 | 79.68