## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM CHAGEY KHOLA TO KATAREY GAON | SM/09615 | New | P.W.S Scheme From Chagey Khola To Katarey Gaon And Its Adjoining Area Under Nimbong G.P. Block-I, Kalimpong Under Jal Jeevan Mission And Jal Swapno Programme. |  |  | ORD/000060/2021-2022 | 451/NKWSMD | 14/01/2022 | 14/04/2022 | NIM TSHERING LEPCHA | 114.97 | 114.63 | 99.71 | 100
2 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM CHAGEY KHOLA TO KATAREY GAON | SM/09615 | New | Engagement of 2(Two) no. computer operator (graduate with certificate in computer application) for the works related to JJM/Jal swapna at the Office of the Executive Engineer, Neorakhola W/S & Mtc. Division, P.H.E. Dte from 01.06.2022 to 31.05.2023 | Assistant Engineer II | Junior Engineer I | ORD/000150/2022-2023 | 680/NKWSMD | 31/05/2022 | 12/06/2022 | THE ELECTRIC SPHERE | 4.98 | 2.36 | 47.41 | 95
3 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM CHAGEY KHOLA TO KATAREY GAON | SM/09615 | New | Material Requisition To Resource Division |  |  | RTOR000014/2021-2022 | 648/NKWSMD | 23/02/2022 | 23/02/2022 | Resource Division | 0.3 | 0 | 0 | 0
Total | [13 empty] | 120.25 | 116.99 | 97.29