## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PWSS FROM MALI KHOLA TO KASHMI FOREST VILLAGE | SM/09617 | New | The Supply, Installation, commissioning & Monitoring of "Non-Electrical Continuous Chlorinator" approved by Government of India & recommended by National Jal Jeevan Mission (NJJM) supplied through Piped Water Supply Schemes (PWSS) maintained by the Public Health Engineering Department (PHED) Government of West Bengal for a minimum period of 03 (Three) months in the District of Kalimpong under different Schemes (As per Schedule) Tentative number of units:6 Unit (Each Unit containing 2 no of Device) | Assistant Engineer II | Junior Engineer II | ORD/000046/2023-2024 | 259/NKWSMD | 15/05/2023 | 15/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 31.66 | 0 | 0 | 0
2 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PWSS FROM MALI KHOLA TO KASHMI FOREST VILLAGE | SM/09617 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED |  |  | BILL/00496/2023-2024 | BP-2023-24-298 | 07/11/2023 | 07/11/2023 | WEST BENGAL PARIVESH CAMPA | 6.07 | 0 | 0 | 0
3 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PWSS FROM MALI KHOLA TO KASHMI FOREST VILLAGE | SM/09617 | New | P.W.S. Scheme from Mali khola to Kasmi Forest Village under Bong G.P. Block I, Kalimpong under Jal Jeevan Mission and Jal Swapno Programme |  |  | ORD/000066/2021-2022 | 457/NKWSMD | 14/01/2022 | 14/04/2022 | ANAND MANI PRADHAN | 90.35 | 72.35 | 80.08 | 100
4 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PWSS FROM MALI KHOLA TO KASHMI FOREST VILLAGE | SM/09617 | New | FOREST PAYMENT |  |  | BILL/00961/2023-2024 | BP-2023-24-645 | 28/03/2024 | 28/03/2024 | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0 | 0
5 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PWSS FROM MALI KHOLA TO KASHMI FOREST VILLAGE | SM/09617 | New | Demand note for payment for boundary pillars of the diverted forest land against proposed 0.0194ha land to be diverted Jal Jeevan Mission. |  |  | BILL/00107/2025-2026 |  | 04/07/2025 | 04/07/2025 | DIVISIONAL FOREST OFFICER | 0.31 | 0 | 0 | 0
Total | [13 empty] | 139.98 | 72.35 | 51.69