## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM CHAGEY KHOLA TO SAURENI | SM/09664 | New | Material Requisition To Resource Division |  |  | RTOR000007/2021-2022 | 641/NKWSMD | 23/02/2022 | 23/02/2022 | Resource Division | 0.33 | 0 | 0 | 0
2 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM CHAGEY KHOLA TO SAURENI | SM/09664 | New | P.W.S SCHEME FROM CHAGAY KHOLA TO SAURENI IN AHALAY G.P GORUBATHAN BLOCK, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | Assistant Engineer II | Junior Engineer III | ORD/000040/2021-2022 | 421/NKWSMD | 07/01/2022 | 06/07/2022 | THUPDEN BHUTIA | 133.48 | 123.84 | 92.78 | 100
Total | [13 empty] | 133.81 | 123.84 | 92.55