## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FROM SISNEY JHORA TO NORTH PEDONG | SM/09665 | New | P.W.S. Scheme from Sisney Jhora to North Pedong under Pedong G.P. Block II under Kalimpong under Jal Jeevan Mission and Jal Swapno Programme |  |  | ORD/000059/2021-2022 | 450/NKWSMD | 14/01/2022 | 14/04/2022 | GETEN NAMGYAL BHUTIA | 138.27 | 45.78 | 33.11 | 95
2 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FROM SISNEY JHORA TO NORTH PEDONG | SM/09665 | New | Material Requisition To Resource Division |  |  | RTOR000027/2021-2022 | 661/NKWSMD | 23/02/2022 | 23/02/2022 | Resource Division | 1.21 | 0 | 0 | 0
Total | [13 empty] | 139.48 | 45.78 | 32.82