## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PWSS SCHEME FROM KHANI KHOLA TO WEST SAMALBONG | SM/09669 | New | Material Requisition To Resource Division |  |  | RTOR000009/2021-2022 | 643/NKWSMD | 23/02/2022 | 23/02/2022 | Resource Division | 0.31 | 0 | 0 | 0
2 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PWSS SCHEME FROM KHANI KHOLA TO WEST SAMALBONG | SM/09669 | New | P.W.S SCHEME FROM KHANI KHOLA TO WEST SAMALBONG UNDER SAMALBONG G.P. BLOCK-I, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. |  |  | ORD/000044/2021-2022 | 423/NKWSMD | 07/01/2022 | 10/07/2024 | BASANT PRADHAN | 121.56 | 110.39 | 90.81 | 100
Total | [13 empty] | 121.87 | 110.39 | 90.58