## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM NIMBONG KHOLA TO SALDARA | SM/09670 | New | Material Requisition To Resource Division |  |  | RTOR000006/2021-2022 | 640/NKWSMD | 23/02/2022 | 23/02/2022 | Resource Division | 0.36 | 0 | 0 | 0
2 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM NIMBONG KHOLA TO SALDARA | SM/09670 | New | P.W.S SCHEME FROM NIMBONG KHOLA TO SALDARA MAIDAN, DOVAN AND ITS ADJOINING AREA UNDER NIMBONG G.P. BLOCK-I, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. |  |  | ORD/000041/2021-2022 | 420/NKWSMD | 07/01/2022 | 07/04/2022 | SANTOSH TAMANG | 117.78 | 68.95 | 58.54 | 100
Total | [13 empty] | 118.14 | 68.95 | 58.37