## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 14 Nos. existing schemes to be provided with FHTC under GTA. | SM/10265 | Retrofitting | Providing Functional household Tap connectionunder JJM & JSP Prog ramme Pws sche me from Sarki dhara to Yok Primtam Acha rya Subba Gaon Seokbir GP |  |  | VCH/000007/2022-2023 | BP-2022-23-6 | 11/04/2022 |  | SUKRAJ SUBBA | 13.95 | 0 | 0 | 0
2 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 14 Nos. existing schemes to be provided with FHTC under GTA. | SM/10265 | Retrofitting | Providing Functional household Tap connection under JJM & JSP Programme for Pws scheme from Mai teraj Jhora to Upper Gairi gaon Bhalukhop GP |  |  | VCH/000011/2022-2023 | BP-2022-23-10 | 11/04/2022 |  | GABAC AND COMPANY | 11.97 | 0 | 0 | 0
3 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 14 Nos. existing schemes to be provided with FHTC under GTA. | SM/10265 | Retrofitting | providin g Functional hou sehold Tap connection under J.JM &. JSP Pro gramme for Pws scheme from Kafleykhola to Gairigaon Bong GP |  |  | VCH/000008/2022-2023 | BP-2022-23-7 | 11/04/2022 |  | TEKENDRA ADHIKARI | 10.64 | 0 | 0 | 0
4 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 14 Nos. existing schemes to be provided with FHTC under GTA. | SM/10265 | Retrofitting | Providing Fun ct ional h ou sehold Tap connection under JJM & JSP Pro gramme for Dws scheme fr om Bhalu Khola to Lower New ar Gaon Bhalukhop GP |  |  | VCH/000009/2022-2023 | BP-2022-23-8 | 11/04/2022 |  | SUPER SAJAN CONSTRUCTION | 17.16 | 0 | 0 | 0
5 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 14 Nos. existing schemes to be provided with FHTC under GTA. | SM/10265 | Retrofitting | "Providing Functional househo ld Tap co nnection under JJM & JSP Pro gramm e for Dws scheme fr om Rabling Khola to Munt hung Busty Ka ffer Kankebong GP" |  |  | VCH/000010/2022-2023 | BP-2022-23-9 | 11/04/2022 |  | SANGAM GURUNG | 10.89 | 0 | 0 | 0
6 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 14 Nos. existing schemes to be provided with FHTC under GTA. | SM/10265 | Retrofitting | Prnviding Functional house hold Tap connection under JJM & JSP Programmne Pws sc heme from Kafal dhara And aheri Jhora to SinJee Bazar } Samaibong GP |  |  | VCH/000003/2022-2023 | BP-2022-23-2 | 11/04/2022 |  | SANTOSH TAMANG | 18.15 | 0 | 0 | 0
7 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 14 Nos. existing schemes to be provided with FHTC under GTA. | SM/10265 | Retrofitting | "Providing Functional househol d Tap connection under JJM &JSP Programme for Dws scheme from Khani Khola to Baidar, Karki, Basnet, Lusuney& Sansari Dara Gaon" |  |  | VCH/000004/2022-2023 | BP-2022-23-3 | 11/04/2022 |  | SANTOSH TAMANG | 14.01 | 0 | 0 | 0
8 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 14 Nos. existing schemes to be provided with FHTC under GTA. | SM/10265 | Retrofitting | "Providing Functional househol d Tap connection under JJM &JSP Programme for Dws scheme from Khani Khola to Baidar, Karki, Basnet, Lusuney& Sansari Dara Gaon" |  |  | VCH/000004/2022-2023 | BP-2022-23-3 | 11/04/2022 |  | SANTOSH TAMANG | 14.01 | 0 | 0 | 0
9 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 14 Nos. existing schemes to be provided with FHTC under GTA. | SM/10265 | Retrofitting | Pro viding Functional househo ld Tap connection under JJM & JSP Prow amm e Dws sch eme from Reank Khola to Pembling Khare Gaon Nimbong GP |  |  | VCH/000012/2022-2023 | BP-2022-23-11 | 11/04/2022 |  | SANGAM GURUNG | 8.51 | 0 | 0 | 0
10 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 14 Nos. existing schemes to be provided with FHTC under GTA. | SM/10265 | Retrofitting | Providing Functional. household Tap connection under JJM & JSP Programme for Dws scheme from Badiya Dhara to Dara Gaon Bhalukhop GP |  |  | VCH/000059/2022-2023 | BP-2022-23-55 | 18/05/2022 |  | GABAC AND COMPANY | 12.44 | 0 | 0 | 0
11 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 14 Nos. existing schemes to be provided with FHTC under GTA. | SM/10265 | Retrofitting | Pr oviding Fu n ctional h ousehold Tap connection und er JJM & JSP Programm e Dws sch eme from Sangbir Jhora to Barbot Pab ringt ar GP |  |  | VCH/000053/2022-2023 | BP-2022-23-42 | 06/05/2022 |  | SITA SHARMA | 18 | 0 | 0 | 0
12 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 14 Nos. existing schemes to be provided with FHTC under GTA. | SM/10265 | Retrofitting | Providing Functional household Tap connection under JJM & JSP Programme for Dws scheme from Jurant , Khola to Middle& Lowe r Chuimkhim Pabringtar |  |  | VCH/000065/2022-2023 | BP-2022-23-56 | 20/05/2022 |  | DILIP CHHETRI ACHARYA | 13.44 | 0 | 0 | 0
13 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 14 Nos. existing schemes to be provided with FHTC under GTA. | SM/10265 | Retrofitting | "Pro vidin g Fun ctional household Tap connect ion under .IJM & JS P Pro gramm e for Dw s scheme by Pumping for Chaikaar, Bha nga and Mongpong Fv Pabringtar GP" |  |  | VCH/000094/2022-2023 | BP-2022-23-87 | 30/06/2022 |  | ANAND KUMAR LAKHOTIA | 14.91 | 0 | 0 | 0
14 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 14 Nos. existing schemes to be provided with FHTC under GTA. | SM/10265 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000219/2022-2023 | 2599/NKWSMD | 17/02/2023 |  | Resource Division | 9.09 | 0 | 0 | 0
15 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 14 Nos. existing schemes to be provided with FHTC under GTA. | SM/10265 | Retrofitting | Addition Estimate for the FHTC under JJM Programme 8 nos existing schemes to be provided with FHTC under Kalimpong Block-II in the district of Kalimpong, FHTC under JJM Programme 14 nos existing schemes to be provided with FHTC, FHTC under JJM Programme 10 nos existing schemes to be provided with FHTC under Block-III, Gorubathan. |  |  | ORD/000273/2022-2023 | 1875/NKWSMD | 14/12/2022 | 12/02/2023 | YAMA CONSTRUCTIONS LLP | 62.3 | 0 | 0 | 100
Total | [13 empty] | 249.47 | 0 | 0