## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 10 Nos. existing schemes to be provided with FHTC under GTA. | SM/10266 | Retrofitting | "Providing Func tional household Tap connection under JJM & JSP Pro gram me for Pws sche me from Jhandi Jhora to Upper & lower Mangzing Pokhrebong GP" |  |  | VCH/000006/2022-2023 | BP-2022-23-5 | 11/04/2022 | 11/04/2022 | ASHOK CHETTRI | 10.86 | 0 | 0 | 0
2 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 10 Nos. existing schemes to be provided with FHTC under GTA. | SM/10266 | Retrofitting | Pr oviding house connection for Dws Scheme from Ambiok Khola to dalimtarr Busty Dalim GP |  |  | VCH/000070/2022-2023 | BP-2022-23-58 | 01/06/2022 | 01/06/2022 | ASHOK SUNAM | 14.43 | 0 | 0 | 0
3 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 10 Nos. existing schemes to be provided with FHTC under GTA. | SM/10266 | Retrofitting | "Prov iding Function al household Tap connection under JJM & JSP Programme for Dws scheme from Dobaney Jhora to 2 no phase six bus stand Paten Godak Gp" |  |  | VCH/000289/2022-2023 | BP-2022-23-178 | 25/10/2022 | 25/10/2022 | JOJO CONSTUCTION | 7.66 | 0 | 0 | 0
4 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 10 Nos. existing schemes to be provided with FHTC under GTA. | SM/10266 | Retrofitting | Providin g Functional household Tap connection under JJM and JSP Programme for Dws scheme by Pumpin g fo r Malbusty Chettri Gaon Gorubathan GP |  |  | VCH/000031/2022-2023 | BP-2022-23-30 | 20/04/2022 | 20/04/2022 | NEMESH LAMA | 9.28 | 0 | 0 | 0
5 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 10 Nos. existing schemes to be provided with FHTC under GTA. | SM/10266 | Retrofitting | providing Functional household Tap connect ion under JJM & JSP Programme for Dws scheme from Jholung khola to Sangam Gaon under Rongo GP |  |  | VCH/000029/2022-2023 | BP-2022-23-28 | 20/04/2022 | 20/04/2022 | PREM KUMAR GURUNG | 16.91 | 0 | 0 | 0
6 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 10 Nos. existing schemes to be provided with FHTC under GTA. | SM/10266 | Retrofitting | Providing Functional household Tap connection under JJM & JSP Pro grammme for Dws schem e from KAii KHola to Upper Fagu Fac tory line Nim GP |  |  | VCH/000030/2022-2023 | BP-2022-23-29 | 20/04/2022 | 20/04/2022 | NEMESH LAMA | 8.59 | 0 | 0 | 0
7 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 10 Nos. existing schemes to be provided with FHTC under GTA. | SM/10266 | Retrofitting | "Prov iding Function al household Tap connection under JJM & JSP Programme for Dws scheme from Dobaney Jhora to 2 no phase six bus stand Paten Godak Gp" |  |  | VCH/000282/2022-2023 | BP-2022-23-166 | 11/10/2022 | 11/10/2022 | JOJO CONSTUCTION | 6 | 0 | 0 | 0
8 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 10 Nos. existing schemes to be provided with FHTC under GTA. | SM/10266 | Retrofitting | Addition Estimate for the FHTC under JJM Programme 8 nos existing schemes to be provided with FHTC under Kalimpong Block-II in the district of Kalimpong, FHTC under JJM Programme 14 nos existing schemes to be provided with FHTC, FHTC under JJM Programme 10 nos existing schemes to be provided with FHTC under Block-III, Gorubathan. |  |  | ORD/000273/2022-2023 | 1875/NKWSMD | 14/12/2022 | 12/02/2023 | YAMA CONSTRUCTIONS LLP | 62.3 | 34.3 | 55.05 | 100
9 | KALIMPONG |  | Darjeeling Division II (Kalimpong) | Functional household tap connection under Jal Swapno Programme, 10 Nos. existing schemes to be provided with FHTC under GTA. | SM/10266 | Retrofitting | Providing Functional household Tap connection under JJM & JSP Programme for Dws scheme from Ashale Khola to Samsing Fari Busty Samsing Gp |  |  | ORD/000001/2020-2021 | 658/DD-II | 18/02/2021 | 19/04/2021 | SUBAN RAI | 18.62 | 18.46 | 99.12 | 100
10 | KALIMPONG |  | Darjeeling Division II (Kalimpong) | Functional household tap connection under Jal Swapno Programme, 10 Nos. existing schemes to be provided with FHTC under GTA. | SM/10266 | Retrofitting | Providing Function household Tap connecti on under JJM & JSP programme for Dws scheme from asahalay Khola to Samsing Compound Busty Sam sing Gp |  |  | ORD/000002/2020-2021 | 656/DD-II | 18/02/2021 | 19/04/2021 | SUBAN RAI | 18.61 | 18.49 | 99.36 | 100
11 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 10 Nos. existing schemes to be provided with FHTC under GTA. | SM/10266 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000218/2022-2023 | 2598/NKWSMD | 17/02/2023 | 17/02/2023 | Resource Division | 10.9 | 0 | 0 | 0
12 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 10 Nos. existing schemes to be provided with FHTC under GTA. | SM/10266 | Retrofitting | Providing Functional household Tap connection under JJM & JSP Programme for Dws scheme from Simsaray Jhora t o Upper Ka mzer in Lolay GP |  |  | BILL/01006/2023-2024 | BP-2023-24-663 | 29/03/2024 | 29/03/2024 | DIPESH RAI | 7.89 | 0 | 0 | 0
Total | [13 empty] | 192.05 | 71.24 | 37.09