## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 8 Nos. existing schemes to be provided with FHTC under GTA. | SM/10267 | Retrofitting | Pro vidin g Functional household Tap connection under JJM & JSP Programme for Dws scheme from Chamlakha Bhotia to Sangseer Mangal Dhura(Na rak) Sangsey GP |  |  | VCH/000060/2022-2023 | BP-2022-23-47 | 18/05/2022 | 18/05/2022 | DINESH SHERPA | 13.62 | 0 | 0 | 0
2 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 8 Nos. existing schemes to be provided with FHTC under GTA. | SM/10267 | Retrofitting | Pr oviding Functional household Tap connection under JJM & JSP Programme for Dws scheme from Dhaula Khola to Lava lava GP |  |  | VCH/000054/2022-2023 | BP-2022-23-38 | 06/05/2022 | 06/05/2022 | NIMA TCHERING BHUTIA | 33.95 | 0 | 0 | 0
3 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 8 Nos. existing schemes to be provided with FHTC under GTA. | SM/10267 | Retrofitting | Pro vidin g Functional household tap connection under JJM & JSP Prog ramm e for Dw s. scheme from Dabaipani Jh ora to Ran gpoo FV Sangsay GP |  |  | VCH/000005/2022-2023 | BP-2022-23-4 | 11/04/2022 | 11/04/2022 | SANTOSH TAMANG | 13.5 | 0 | 0 | 0
4 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 8 Nos. existing schemes to be provided with FHTC under GTA. | SM/10267 | Retrofitting | Pro viding Functiona l household Tap connec tio n under JJM & JSP Pro gramme for Dw sche me from Tarchu Khola to Tarkhola FV 10mile Sangsey GP |  |  | VCH/000050/2022-2023 | BP-2022-23-43 | 06/05/2022 | 06/05/2022 | ANAND MANI PRADHAN | 12.85 | 0 | 0 | 0
5 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 8 Nos. existing schemes to be provided with FHTC under GTA. | SM/10267 | Retrofitting | Pr vidin g Functional household Tap connect ion und er JJ_M & J$P Programme for Pws scheme fro m Odam Khola to Sa nyasi Dara Nav gaon Pa bringtar GP |  |  | VCH/000013/2022-2023 | BP-2022-23-12 | 11/04/2022 | 11/04/2022 | CHEMJONG ENTERPRISE | 17.69 | 0 | 0 | 0
6 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 8 Nos. existing schemes to be provided with FHTC under GTA. | SM/10267 | Retrofitting | Providing Functional household Tap connection under JJM & jSP Programme for Dws sche me from Narag Jhora to Munshi Dhura Gao n Sangsay Gp |  |  | VCH/000061/2022-2023 | BP-2022-23-48 | 18/05/2022 | 18/05/2022 | DINESH SHERPA | 10.62 | 0 | 0 | 0
7 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 8 Nos. existing schemes to be provided with FHTC under GTA. | SM/10267 | Retrofitting | "Providing house connecti on for Dws scheme from salsalay Jhora to Bhutia Bust y and Lower Meerong(Bull Farm) Pedong gp" |  |  | VCH/000149/2022-2023 | BP-2022-23-103 | 04/08/2022 | 04/08/2022 | GETEN NAMGYAL BHUTIA | 5.98 | 0 | 0 | 0
8 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 8 Nos. existing schemes to be provided with FHTC under GTA. | SM/10267 | Retrofitting | Addition Estimate for the FHTC under JJM Programme 8 nos existing schemes to be provided with FHTC under Kalimpong Block-II in the district of Kalimpong, FHTC under JJM Programme 14 nos existing schemes to be provided with FHTC, FHTC under JJM Programme 10 nos existing schemes to be provided with FHTC under Block-III, Gorubathan. |  |  | ORD/000273/2022-2023 | 1875/NKWSMD | 14/12/2022 | 12/02/2023 | YAMA CONSTRUCTIONS LLP | 62.3 | 1.74 | 2.79 | 100
9 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, 8 Nos. existing schemes to be provided with FHTC under GTA. | SM/10267 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000217/2022-2023 | 2597/NKWSMD | 17/02/2023 | 17/02/2023 | Resource Division | 6.87 | 0 | 0 | 0
Total | [13 empty] | 177.4 | 1.74 | 0.98