## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Midnapore Division | Survey & collection of data through Mobile app regarding availability of drinking water, sanitation facilities & other parameters in Primary, Upper Primary Schools, Anganwadi Centers within Paschim Medinipur & Jhargram District. | SM/09000 | Support-M&E | SURVEY & COLLECTION OF DATA THROUGH MOBILE APP REGARDING AVAILABILITY OF DRINKING WATER, SANITATION FACILITIES & OTHER PARAMETERS IN PRIMARY, UPPER PRIMARY SCHOOLS, ANGANWADI CENTERS UNDER MEDINIPUR SADAR SUB DIVISION UNDER MIDNAPORE DIVISION PHE DTE. (Sl. No.1) | AE Sadar Sub-division |  | ORD/000369/2022-2023 | 298/RWS/MID | 18/08/2022 | 08/09/2022 | UTSAV AGENCY | 3.49 | 3.49 | 100 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Survey & collection of data through Mobile app regarding availability of drinking water, sanitation facilities & other parameters in Primary, Upper Primary Schools, Anganwadi Centers within Paschim Medinipur & Jhargram District. | SM/09000 | Support-M&E | SURVEY & COLLECTION OF DATA THROUGH MOBILE APP REGARDING AVAILABILITY OF DRINKING WATER, SANITATION FACILITIES & OTHER PARAMETERS IN PRIMARY, UPPER PRIMARY SCHOOLS, ANGANWADI CENTERS UNDER MEDINIPUR SADAR SUB DIVISION UNDER MIDNAPORE DIVISION PHE DTE. (Sl. No.1) | AE Sadar Sub-division |  | ORD/000369/2022-2023 | 298/RWS/MID | 18/08/2022 | 08/09/2022 | UTSAV AGENCY | 3.49 | 3.49 | 100 | 0
3 | JHARGRAM |  | Midnapore Division | Survey & collection of data through Mobile app regarding availability of drinking water, sanitation facilities & other parameters in Primary, Upper Primary Schools, Anganwadi Centers within Paschim Medinipur & Jhargram District. | SM/09000 | Support-M&E | SURVEY & COLLECTION OF DATA THROUGH MOBILE APP REGARDING AVAILABILITY OF DRINKING WATER, SANITATION FACILITIES & OTHER PARAMETERS IN PRIMARY, UPPER PRIMARY SCHOOLS, ANGANWADI CENTERS UNDER KHARAGPUR SUB DIVISION UNDER MIDNAPORE DIVISION PHE DTE. (Sl. No. 2) | AE Kharagpur Sub-division |  | ORD/000370/2022-2023 | 299/RWS/MID | 18/08/2022 | 08/09/2022 | UTSAV AGENCY | 4.74 | 4.74 | 100 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Survey & collection of data through Mobile app regarding availability of drinking water, sanitation facilities & other parameters in Primary, Upper Primary Schools, Anganwadi Centers within Paschim Medinipur & Jhargram District. | SM/09000 | Support-M&E | SURVEY & COLLECTION OF DATA THROUGH MOBILE APP REGARDING AVAILABILITY OF DRINKING WATER, SANITATION FACILITIES & OTHER PARAMETERS IN PRIMARY, UPPER PRIMARY SCHOOLS, ANGANWADI CENTERS UNDER KHARAGPUR SUB DIVISION UNDER MIDNAPORE DIVISION PHE DTE. (Sl. No. 2) | AE Kharagpur Sub-division |  | ORD/000370/2022-2023 | 299/RWS/MID | 18/08/2022 | 08/09/2022 | UTSAV AGENCY | 4.74 | 4.74 | 100 | 0
5 | JHARGRAM |  | Midnapore Division | Survey & collection of data through Mobile app regarding availability of drinking water, sanitation facilities & other parameters in Primary, Upper Primary Schools, Anganwadi Centers within Paschim Medinipur & Jhargram District. | SM/09000 | Support-M&E | SURVEY & COLLECTION OF DATA THROUGH MOBILE APP REGARDING AVAILABILITY OF DRINKING WATER, SANITATION FACILITIES & OTHER PARAMETERS IN PRIMARY, UPPER PRIMARY SCHOOLS, ANGANWADI CENTERS UNDER GHATAL SUB DIVISION UNDER MIDNAPORE DIVISION PHE DTE. (Sl. No.3) | AE Ghatal Sub-division |  | ORD/000371/2022-2023 | 300/RWS/MID | 18/08/2022 | 08/09/2022 | UTSAV AGENCY | 2.81 | 2.81 | 100 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Division | Survey & collection of data through Mobile app regarding availability of drinking water, sanitation facilities & other parameters in Primary, Upper Primary Schools, Anganwadi Centers within Paschim Medinipur & Jhargram District. | SM/09000 | Support-M&E | SURVEY & COLLECTION OF DATA THROUGH MOBILE APP REGARDING AVAILABILITY OF DRINKING WATER, SANITATION FACILITIES & OTHER PARAMETERS IN PRIMARY, UPPER PRIMARY SCHOOLS, ANGANWADI CENTERS UNDER GHATAL SUB DIVISION UNDER MIDNAPORE DIVISION PHE DTE. (Sl. No.3) | AE Ghatal Sub-division |  | ORD/000371/2022-2023 | 300/RWS/MID | 18/08/2022 | 08/09/2022 | UTSAV AGENCY | 2.81 | 2.81 | 100 | 0
7 | JHARGRAM |  | Midnapore Division | Survey & collection of data through Mobile app regarding availability of drinking water, sanitation facilities & other parameters in Primary, Upper Primary Schools, Anganwadi Centers within Paschim Medinipur & Jhargram District. | SM/09000 | Support-M&E | SURVEY & COLLECTION OF DATA THROUGH MOBILE APP REGARDING AVAILABILITY OF DRINKING WATER, SANITATION FACILITIES & OTHER PARAMETERS IN PRIMARY, UPPER PRIMARY SCHOOLS, ANGANWADI CENTERS UNDER MEDINIPUR SADAR SUB DIVISION UNDER MIDNAPORE DIVISION PHE DTE | AE/RWS Midnapore Sub Division |  | ORD/000149/2023-2024 | 212/RWS/MID | 17/05/2023 | 16/06/2023 | UTSAV AGENCY | 0.75 | 0.73 | 97.73 | 100
8 | PASCHIM MEDINIPUR |  | Midnapore Division | Survey & collection of data through Mobile app regarding availability of drinking water, sanitation facilities & other parameters in Primary, Upper Primary Schools, Anganwadi Centers within Paschim Medinipur & Jhargram District. | SM/09000 | Support-M&E | SURVEY & COLLECTION OF DATA THROUGH MOBILE APP REGARDING AVAILABILITY OF DRINKING WATER, SANITATION FACILITIES & OTHER PARAMETERS IN PRIMARY, UPPER PRIMARY SCHOOLS, ANGANWADI CENTERS UNDER MEDINIPUR SADAR SUB DIVISION UNDER MIDNAPORE DIVISION PHE DTE | AE/RWS Midnapore Sub Division |  | ORD/000149/2023-2024 | 212/RWS/MID | 17/05/2023 | 16/06/2023 | UTSAV AGENCY | 0.75 | 0.73 | 97.73 | 100
9 | JHARGRAM |  | Midnapore Division | Survey & collection of data through Mobile app regarding availability of drinking water, sanitation facilities & other parameters in Primary, Upper Primary Schools, Anganwadi Centers within Paschim Medinipur & Jhargram District. | SM/09000 | Support-M&E | Survey & Collection of Data through Mobile App regarding availability of drinking water, sanitation facility & other parameters in Primary, Upper Primary Schools, Anganwadi Centers under Midnapore Division, PHE Dte. | Assistant Engineer (HQ) |  | ORD/000686/2023-2024 | 5429/MD | 07/12/2023 | 17/12/2023 | UTSAV AGENCY | 0.62 | 0.62 | 100 | 100
10 | PASCHIM MEDINIPUR |  | Midnapore Division | Survey & collection of data through Mobile app regarding availability of drinking water, sanitation facilities & other parameters in Primary, Upper Primary Schools, Anganwadi Centers within Paschim Medinipur & Jhargram District. | SM/09000 | Support-M&E | Survey & Collection of Data through Mobile App regarding availability of drinking water, sanitation facility & other parameters in Primary, Upper Primary Schools, Anganwadi Centers under Midnapore Division, PHE Dte. | Assistant Engineer (HQ) |  | ORD/000686/2023-2024 | 5429/MD | 07/12/2023 | 17/12/2023 | UTSAV AGENCY | 0.62 | 0.62 | 100 | 100
Total | [13 empty] | 24.81 | 24.78 | 99.86