## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Midnapore Division | Relief and restoration work in the aftermath of cyclone storm YASS under Midnapore Division, PHE.Dte | SM/10001 | Disaster | Exigency basis estimate for Strengthening Distribution system of UPVC (Class - III) pipe line for Kasanda & its adjoining mouzas W/S Scheme within Ghatal Sub-Division under Midnapore Division, PHE Dte. Nodal Points-(29-30),(32-34),(34-36) &(30-32 part) |  |  | VCH/000243/2022-2023 | BP-2021-22-558 | 04/04/2022 | 04/04/2022 | JIT ENTERPRISE | 4.58 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Relief and restoration work in the aftermath of cyclone storm YASS under Midnapore Division, PHE.Dte | SM/10001 | Disaster | Exigency basis estimate for Strengthening Distribution system of UPVC (Class - III) pipe line for Kasanda & its adjoining mouzas W/S Scheme within Ghatal Sub-Division under Midnapore Division, PHE Dte. Nodal Points-(29-30),(32-34),(34-36) &(30-32 part) |  |  | VCH/000243/2022-2023 | BP-2021-22-558 | 04/04/2022 | 04/04/2022 | JIT ENTERPRISE | 4.58 | 0 | 0 | 0
3 | JHARGRAM |  | Midnapore Division | Relief and restoration work in the aftermath of cyclone storm YASS under Midnapore Division, PHE.Dte | SM/10001 | Disaster | Exigency basis estimate for strengthening Distribution system of UPVC (Class - III) pipe line for Kasanda & its adjoining mouzas W/S Scheme within Ghatal Sub-Division under Midnapore Division, PHE Dte. Nodal Points-(28-25),28-29),(28-48) &(30-32 part) |  |  | VCH/000244/2022-2023 | BP-2021-22-559 | 04/04/2022 | 04/04/2022 | SAMIT PAL | 4.84 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Relief and restoration work in the aftermath of cyclone storm YASS under Midnapore Division, PHE.Dte | SM/10001 | Disaster | Exigency basis estimate for strengthening Distribution system of UPVC (Class - III) pipe line for Kasanda & its adjoining mouzas W/S Scheme within Ghatal Sub-Division under Midnapore Division, PHE Dte. Nodal Points-(28-25),28-29),(28-48) &(30-32 part) |  |  | VCH/000244/2022-2023 | BP-2021-22-559 | 04/04/2022 | 04/04/2022 | SAMIT PAL | 4.84 | 0 | 0 | 0
5 | JHARGRAM |  | Midnapore Division | Relief and restoration work in the aftermath of cyclone storm YASS under Midnapore Division, PHE.Dte | SM/10001 | Disaster | Repairing & Renovation for the Office of the Assistant Engineer, Ghatal Sub-Division including Ghatal Sub-District Laboratory under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000730/2022-2023 | 871/MD | 28/03/2023 | 12/05/2023 | SUBHASIS DOLAI | 10.1 | 0 | 0 | 100
6 | PASCHIM MEDINIPUR |  | Midnapore Division | Relief and restoration work in the aftermath of cyclone storm YASS under Midnapore Division, PHE.Dte | SM/10001 | Disaster | Repairing & Renovation for the Office of the Assistant Engineer, Ghatal Sub-Division including Ghatal Sub-District Laboratory under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000730/2022-2023 | 871/MD | 28/03/2023 | 12/05/2023 | SUBHASIS DOLAI | 10.1 | 0 | 0 | 100
Total | [13 empty] | 39.03 | 0 | 0