## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 5 Nos. P.W.S.S. within Binpur - I & 1 No. P.W.S.S. within Binpur - II | SM/06828 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Khasjangal / Dhansola PWSS of Binpur-I Block under Jhargram Division, PHE Dte. |  |  | ORD/000182/2020-2021 | 1406/MD | 26/11/2020 | 25/05/2021 | SAIKAT DANDAPAT | 19.14 | 8.99 | 46.97 | 1
2 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 5 Nos. P.W.S.S. within Binpur - I & 1 No. P.W.S.S. within Binpur - II | SM/06828 | Retrofitting | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM AT BIRKANAR PWSS OF BINPUR-I BLOCK UNDER JHARGRAM DIVISION ,PHE DTE.. |  |  | VCH/001885/2021-2022 | 8443208 | 26/03/2022 |  | DEBABRATA DUTTA | 6.69 | 0 | 0 | 0
3 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 5 Nos. P.W.S.S. within Binpur - I & 1 No. P.W.S.S. within Binpur - II | SM/06828 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Kantapahari PWSS of Binpur-I Block under Jhargram Division, PHE Dte. |  |  | VCH/001890/2021-2022 | 8443205 | 26/03/2022 |  | S.T. ENTERPRISE | 4.71 | 0 | 0 | 0
4 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 5 Nos. P.W.S.S. within Binpur - I & 1 No. P.W.S.S. within Binpur - II | SM/06828 | Retrofitting | Extension distribution pipe line to accommodation FHTC under JJM in Lakat PWSS Block-Binpur-I in the District of Jhargram. |  |  | VCH/000662/2022-2023 | 844313 | 06/07/2022 |  | S.B. TRADERS | 0.89 | 0 | 0 | 0
5 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 5 Nos. P.W.S.S. within Binpur - I & 1 No. P.W.S.S. within Binpur - II | SM/06828 | Retrofitting | Relaying Distribution pipe line (Part) for Netai Water Supply Scheme to accommodate FHTC under Jhargram Sub-Division, PHE Dte. within Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-III | ORD/000095/2021-2022 | 2249/MD | 28/12/2021 | 18/01/2022 | S.B.TRADERS | 15.45 | 0 | 0 | 1
6 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 5 Nos. P.W.S.S. within Binpur - I & 1 No. P.W.S.S. within Binpur - II | SM/06828 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Kechanda PWSS of Binpur-II Block under Jhargram Division, PHE Dte. [PART - 2/2] (Allotted for near about 50% of the total work) |  |  | ORD/000296/2020-2021 | 1599/MD | 14/12/2020 | 12/06/2021 | J.S.S. ENTERPRISE | 7.74 | 7.23 | 93.43 | 0
7 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 5 Nos. P.W.S.S. within Binpur - I & 1 No. P.W.S.S. within Binpur - II | SM/06828 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Kechanda PWSS of Binpur-II Block under Jhargram Division, PHE Dte. [PART - 1/2] (Allotted for near about 50% of the total work) |  |  | ORD/000295/2020-2021 | 1598/MD | 14/12/2020 | 12/06/2021 | DEBABRATA DUTTA | 7.72 | 7.32 | 94.88 | 0
8 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 5 Nos. P.W.S.S. within Binpur - I & 1 No. P.W.S.S. within Binpur - II | SM/06828 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Lakat PWSS of Binpur-I Block under Jhargram Division, PHE Dte. |  |  | ORD/000285/2020-2021 | 1583/MD | 11/12/2020 | 09/06/2021 | S.B. TRADERS | 8.2 | 5.28 | 64.39 | 0
Total | [13 empty] | 70.52 | 28.83 | 40.87