## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 3 Nos. P.W.S.S. within Binpur - I & 3 No. P.W.S.S. within Binpur - II | SM/06829 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Netai PWSS of Binpur-I Block under Jhargram Division, PHE Dte. |  |  | ORD/000286/2020-2021 | 1584/MD | 11/12/2020 | 09/06/2021 | BIDYUT KUMAR SANTRA | 40.78 | 19.54 | 47.9 | 1
2 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 3 Nos. P.W.S.S. within Binpur - I & 3 No. P.W.S.S. within Binpur - II | SM/06829 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Khasjungle PWSS of Binpur-I Block under Jhargram Division, PHE Dte. |  |  | VCH/001366/2021-2022 | 8443122 | 25/02/2022 | 25/02/2022 | M/S. SOMNATH | 7.01 | 0 | 0 | 0
3 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 3 Nos. P.W.S.S. within Binpur - I & 3 No. P.W.S.S. within Binpur - II | SM/06829 | Retrofitting | Extension distribution pipe line to accomodate FHTC under JJM in Lakat PWSS Block - Binpur-I in the District of Jhargram | Assistant Engineer | Junior Engineer-III | ORD/000094/2021-2022 | 33/JSD | 01/02/2022 | 16/02/2022 | S.B.TRADERS | 2.64 | 0 | 0 | 1
4 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 3 Nos. P.W.S.S. within Binpur - I & 3 No. P.W.S.S. within Binpur - II | SM/06829 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Aulia PWSS of Binpur-II Block under Jhargram Division, PHE Dte. |  |  | ORD/000181/2020-2021 | 1410/MD | 26/11/2020 | 25/05/2021 | GOUTAM PARIA | 14.09 | 12.14 | 86.12 | 0
5 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 3 Nos. P.W.S.S. within Binpur - I & 3 No. P.W.S.S. within Binpur - II | SM/06829 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Simulpal PWSS of Binpur-II Block under Jhargram Division, PHE Dte. |  |  | ORD/000185/2020-2021 | 1408/MD | 26/11/2020 | 25/05/2021 | GOUTAM RAY | 14.62 | 12.54 | 85.83 | 0
Total | [13 empty] | 79.15 | 44.22 | 55.87