## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Gopiballavpur - I & 1 No. P.W.S.S. within Jamboni | SM/06830 | Retrofitting | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. |  |  | VCH/001156/2020-2021 | 8443106 | 12/02/2021 | 12/02/2021 | SANDIP MANNA | 0.15 | 0 | 0 | 0
2 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Gopiballavpur - I & 1 No. P.W.S.S. within Jamboni | SM/06830 | Retrofitting | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. |  |  | VCH/001157/2020-2021 | 8443106 | 12/02/2021 | 12/02/2021 | SOVANDEB MANNA | 0.03 | 0 | 0 | 0
3 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Gopiballavpur - I & 1 No. P.W.S.S. within Jamboni | SM/06830 | Retrofitting | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. |  |  | VCH/001159/2020-2021 | 8443106 | 12/02/2021 | 12/02/2021 | ANIRBAN CHAKRABORTY | 0.18 | 0 | 0 | 0
4 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Gopiballavpur - I & 1 No. P.W.S.S. within Jamboni | SM/06830 | Retrofitting | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. |  |  | VCH/001158/2020-2021 | 8443106 | 12/02/2021 | 12/02/2021 | ARUP KR ADAK | 0.07 | 0 | 0 | 0
5 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Gopiballavpur - I & 1 No. P.W.S.S. within Jamboni | SM/06830 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Chhatinasole PWSS of Gopiballavpur-I Block under Jhargram Division, PHE Dte. |  |  | VCH/001635/2021-2022 | 8443115 | 23/03/2022 | 23/03/2022 | CHAKRABORTTI ENTERPRISE | 23.06 | 0 | 0 | 0
6 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Gopiballavpur - I & 1 No. P.W.S.S. within Jamboni | SM/06830 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Chichira PWSS of Jamboni Block under Jhargram Division, PHE Dte. |  |  | ORD/000249/2020-2021 | 1581/MD | 11/12/2020 | 09/06/2021 | SUNIL DULE | 31 | 12.55 | 40.47 | 0
7 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Gopiballavpur - I & 1 No. P.W.S.S. within Jamboni | SM/06830 | Retrofitting | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Gopiballavpur - I & 1 No. P.W.S.S. within Jamboni |  |  | VCH/001410/2022-2023 | 844368 | 30/11/2022 | 30/11/2022 | SUNIL DULE | 2.35 | 0 | 0 | 0
8 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Gopiballavpur - I & 1 No. P.W.S.S. within Jamboni | SM/06830 | Retrofitting | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Gopiballavpur - I & 1 No. P.W.S.S. within Jamboni |  |  | VCH/001411/2022-2023 | 844368 | 30/11/2022 | 30/11/2022 | SUNIL DULE | 13 | 0 | 0 | 0
9 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Gopiballavpur - I & 1 No. P.W.S.S. within Jamboni | SM/06830 | Retrofitting | Alied Works (specialy Valve Chember) under Chatinasole W/S Scheme within Jhargram Sub Division unde Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000045/2022-2023 | 31/GPSD | 18/07/2022 | 08/08/2022 | DIPAK KUMAR BAKLY | 1.29 | 0 | 0 | 100
10 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Gopiballavpur - I & 1 No. P.W.S.S. within Jamboni | SM/06830 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Chichira PWSS of Jamboni Block under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000035/2020-2021 | 1581/MD | 11/12/2020 | 09/06/2021 | SUNIL DULE | 31 | 0 | 0 | 90
11 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Gopiballavpur - I & 1 No. P.W.S.S. within Jamboni | SM/06830 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Banshia PWSS of Gopiballavpur-I Block under Jhargram Division, PHE Dte. |  |  | ORD/000183/2020-2021 | 1411/MD | 26/11/2020 | 25/05/2021 | BISHNU PADA NANDI | 3.52 | 3.22 | 91.44 | 0
Total | [13 empty] | 105.67 | 15.76 | 14.92