## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 3 Nos. P.W.S.S. within Binpur - I, 2 Nos. P.W.S.S. within Binpur - II Block , 2 Nos. P.W.S.S. within Gopiballavpur - I Block, 1 No. P.W.S.S. within Gopiballavpur - II Block, 1 No. P.W.S.S. within Nayagram Blo | SM/07875 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Baratilaboni PWSS (Phase-II) Block - Binpur-I in the District of Jhargram |  |  | ORD/000396/2021-2022 | 348/JSD | 23/11/2021 | 30/11/2021 | J.S.S. ENTERPRISE | 2.59 | 0 | 0 | 1
2 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 3 Nos. P.W.S.S. within Binpur - I, 2 Nos. P.W.S.S. within Binpur - II Block , 2 Nos. P.W.S.S. within Gopiballavpur - I Block, 1 No. P.W.S.S. within Gopiballavpur - II Block, 1 No. P.W.S.S. within Nayagram Blo | SM/07875 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Pitanow PWSS of Gopiballavpur-I Block under Jhargram Division, PHE Dte. |  |  | ORD/000049/2022-2023 | 869/MD | 10/05/2022 | 25/05/2022 | AJITESH ACHARJEE | 6 | 0 | 0 | 0
3 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 3 Nos. P.W.S.S. within Binpur - I, 2 Nos. P.W.S.S. within Binpur - II Block , 2 Nos. P.W.S.S. within Gopiballavpur - I Block, 1 No. P.W.S.S. within Gopiballavpur - II Block, 1 No. P.W.S.S. within Nayagram Blo | SM/07875 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Domsole PWSS of Binpur-II Block under Jhargram Division, PHE Dte. |  |  | ORD/000509/2020-2021 | 382/MD | 25/02/2021 | 12/03/2021 | S.B. TRADERS | 5.24 | 3.95 | 75.41 | 1
4 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 3 Nos. P.W.S.S. within Binpur - I, 2 Nos. P.W.S.S. within Binpur - II Block , 2 Nos. P.W.S.S. within Gopiballavpur - I Block, 1 No. P.W.S.S. within Gopiballavpur - II Block, 1 No. P.W.S.S. within Nayagram Blo | SM/07875 | Retrofitting | Sinking of 200 mm x 150 mm dia and depth 110 mtr. Rig bore Tubewell (Replacement) for Pathardhara W/S Scheme i.c.w providing F.H.T.C. under Jhargram Sub Division within Jhargram Division, PHE Dte. |  |  | ORD/000277/2021-2022 | 238/JSD | 24/09/2021 | 08/10/2021 | DHUMKETU ENGINEERING PRIVATE LIMITED | 4.67 | 0 | 0 | 1
5 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 3 Nos. P.W.S.S. within Binpur - I, 2 Nos. P.W.S.S. within Binpur - II Block , 2 Nos. P.W.S.S. within Gopiballavpur - I Block, 1 No. P.W.S.S. within Gopiballavpur - II Block, 1 No. P.W.S.S. within Nayagram Blo | SM/07875 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Bhera PWSS of Gopiballavpur-I Block under Jhargram Division, PHE Dte. |  |  | VCH/001388/2021-2022 | BP-2021-22-393 | 22/02/2022 | 22/02/2022 | NIRMAL DUTTA | 1.43 | 0 | 0 | 0
6 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 3 Nos. P.W.S.S. within Binpur - I, 2 Nos. P.W.S.S. within Binpur - II Block , 2 Nos. P.W.S.S. within Gopiballavpur - I Block, 1 No. P.W.S.S. within Gopiballavpur - II Block, 1 No. P.W.S.S. within Nayagram Blo | SM/07875 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza Pitanaw PWSS water supply scheme. |  |  | BILL/00726/2022-2023 | BP-2022-23-518 | 01/02/2023 | 01/02/2023 | AJITESH ACHARJEE | 0.52 | 0 | 0 | 0
7 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 3 Nos. P.W.S.S. within Binpur - I, 2 Nos. P.W.S.S. within Binpur - II Block , 2 Nos. P.W.S.S. within Gopiballavpur - I Block, 1 No. P.W.S.S. within Gopiballavpur - II Block, 1 No. P.W.S.S. within Nayagram Blo | SM/07875 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Pitanow PWSS of Gopiballavpur-I Block under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000074/2022-2023 | 869/MD | 10/05/2022 | 25/05/2022 | AJITESH ACHARJEE | 6 | 0 | 0 | 100
8 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 3 Nos. P.W.S.S. within Binpur - I, 2 Nos. P.W.S.S. within Binpur - II Block , 2 Nos. P.W.S.S. within Gopiballavpur - I Block, 1 No. P.W.S.S. within Gopiballavpur - II Block, 1 No. P.W.S.S. within Nayagram Blo | SM/07875 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Pathardahara PWSS of Nayagram Block under Jhargram Division, PHE Dte. |  |  | ORD/000364/2020-2021 | 588/JSD | 01/02/2021 | 16/02/2021 | DHUMKETU ENGINEERING PRIVATE LIMITED | 2.53 | 2.38 | 94.15 | 0
9 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 3 Nos. P.W.S.S. within Binpur - I, 2 Nos. P.W.S.S. within Binpur - II Block , 2 Nos. P.W.S.S. within Gopiballavpur - I Block, 1 No. P.W.S.S. within Gopiballavpur - II Block, 1 No. P.W.S.S. within Nayagram Blo | SM/07875 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Logan PWSS of Binpur-I Block under Jhargram Division, PHE Dte. |  |  | ORD/000361/2020-2021 | 582/JSD | 01/02/2021 | 03/03/2021 | J.S.S. ENTERPRISE | 4.38 | 0 | 0 | 0
10 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 3 Nos. P.W.S.S. within Binpur - I, 2 Nos. P.W.S.S. within Binpur - II Block , 2 Nos. P.W.S.S. within Gopiballavpur - I Block, 1 No. P.W.S.S. within Gopiballavpur - II Block, 1 No. P.W.S.S. within Nayagram Blo | SM/07875 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Barabaria PWSS of Gopiballavpur-II Block under Jhargram Division, PHE Dte. |  |  | ORD/000363/2020-2021 | 587/JSD | 01/02/2021 | 16/02/2021 | BISHNU PADA NANDI | 2.27 | 2.02 | 89.26 | 0
11 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 3 Nos. P.W.S.S. within Binpur - I, 2 Nos. P.W.S.S. within Binpur - II Block , 2 Nos. P.W.S.S. within Gopiballavpur - I Block, 1 No. P.W.S.S. within Gopiballavpur - II Block, 1 No. P.W.S.S. within Nayagram Blo | SM/07875 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Bhangabandh PWSS of Binpur-II Block under Jhargram Division, PHE Dte. |  |  | ORD/000508/2020-2021 | 381/MD | 25/02/2021 | 12/03/2021 | SAIKAT DANDAPAT | 7.78 | 7.95 | 102.28 | 0
12 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 3 Nos. P.W.S.S. within Binpur - I, 2 Nos. P.W.S.S. within Binpur - II Block , 2 Nos. P.W.S.S. within Gopiballavpur - I Block, 1 No. P.W.S.S. within Gopiballavpur - II Block, 1 No. P.W.S.S. within Nayagram Blo | SM/07875 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Bartilaboni PWSS of Binpur-I Block under Jhargram Division, PHE Dte. |  |  | ORD/000359/2020-2021 | 580/JSD | 01/02/2021 | 11/02/2021 | J.S.S. ENTERPRISE | 0.71 | 0 | 0 | 0
13 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 3 Nos. P.W.S.S. within Binpur - I, 2 Nos. P.W.S.S. within Binpur - II Block , 2 Nos. P.W.S.S. within Gopiballavpur - I Block, 1 No. P.W.S.S. within Gopiballavpur - II Block, 1 No. P.W.S.S. within Nayagram Blo | SM/07875 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Sankrail PWSS of Sankrail Block under Jhargram Division, PHE Dte. |  |  | ORD/000051/2021-2022 | 878/MD | 08/06/2021 | 23/06/2021 | PULLOCK KUMAR GHOSH | 5.5 | 5.15 | 93.6 | 0
Total | [13 empty] | 49.61 | 21.45 | 43.25