## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Hatikadua Mini PWSS (Out of 45 Nos. Mini PWSS) at Jamboni Block under Jhargram Division, PHE Dte. |  |  | ORD/000128/2021-2022 | 1224/MD | 29/07/2021 | 13/08/2021 | NIRMAL DUTTA | 5.99 | 0 | 0 | 0
2 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Dakaisol SSK Mini PWSS (Out of 45 Nos. Mini PWSS) at Binpur-II Block under Jhargram Division, PHE Dte. |  |  | ORD/000514/2020-2021 | 387/MD | 25/02/2021 | 12/03/2021 | SAIKAT DANDAPAT | 5.78 | 0 | 0 | 0
3 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Ruknimara Mini PWSS (Out of 45 Nos. Mini PWSS) at Nayagram Block under Jhargram Division, PHE Dte. |  |  | ORD/000063/2021-2022 | 1055/MD | 02/07/2021 | 17/07/2021 | ASIS KUMAR SARANGI | 5.82 | 0 | 0 | 1
4 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Nuasai Mini PWSS (Out of 45 Nos. Mini PWSS) at Nayagram Block under Jhargram Division, PHE Dte. |  |  | ORD/000164/2021-2022 | 1287/MD | 09/08/2021 | 24/08/2021 | GOUTAM PARIA | 4.92 | 0 | 0 | 1
5 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Telidanga Jr. High School Mini PWSS (Out of 45 Nos. Mini PWSS) at Binpur-II Block under Jhargram Division, PHE Dte. |  |  | ORD/000203/2021-2022 | 1377/MD | 25/08/2021 | 09/09/2021 | SAIKAT DANDAPAT | 7.42 | 0 | 0 | 0
6 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Sankhara Primary School Mini PWSS (Out of 45 Nos. Mini PWSS) at Binpur-I Block under Jhargram Division, PHE Dte. |  |  | ORD/000512/2020-2021 | 385/MD | 25/02/2021 | 12/03/2021 | SUNIL DULE | 5.37 | 4.92 | 91.59 | 1
7 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Jashpur Primary School Mini PWSS (Out of 45 Nos. Mini PWSS) at Binpur-I Block under Jhargram Division, PHE Dte. |  |  | ORD/000511/2020-2021 | 384/MD | 25/02/2021 | 12/03/2021 | SUNIL DULE | 6.16 | 6.16 | 99.97 | 1
8 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Kashafulia Mini PWSS (Out of 45 Nos. Mini PWSS) at Jamboni Block under Jhargram Division, PHE Dte. |  |  | ORD/000657/2020-2021 | 452/MD | 26/02/2021 | 13/03/2021 | NIRMAL DUTTA | 5.99 | 0 | 0 | 0
9 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Kaluasarn SSK Mini PWSS (Out of 45 Nos. Mini PWSS) at Nayagram Block under Jhargram Division, PHE Dte. |  |  | ORD/000061/2021-2022 | 824/MD | 03/06/2021 | 18/06/2021 | PROVAT KUMAR DE | 7.43 | 0 | 0 | 0
10 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Junsola PWSS of Gopiballavpur-II Block under Jhargram Division, PHE Dte. (Phase-II) |  |  | ORD/000122/2021-2022 | 817/MD | 03/06/2021 | 18/06/2021 | SATYA RANJAN DAS | 4.96 | 0 | 0 | 1
11 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Nayabasan, Khunti Village Mini PWSS (Out of 45 Nos. Mini PWSS) at Gopiballavpur-I Block under Jhargram Division, PHE Dte. |  |  | ORD/000066/2021-2022 | 1058/MD | 02/07/2021 | 17/07/2021 | BISHNU PADA NANDI | 7.83 | 5.19 | 66.22 | 1
12 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Bachurkhur Mini PWSS (Out of 45 Nos. Mini PWSS) at Nayagram Block under Jhargram Division, PHE Dte. |  |  | ORD/000068/2021-2022 | 1064/MD | 02/07/2021 | 17/07/2021 | NIMAI LAL GURIA | 7.76 | 7.64 | 98.51 | 1
13 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Baharuna Mini PWSS (Out of 45 Nos. Mini PWSS) at Gopiballavpur-II Block under Jhargram Division, PHE Dte. |  |  | ORD/000123/2021-2022 | 826/MD | 03/06/2021 | 18/06/2021 | SATYA RANJAN DAS | 8.01 | 0 | 0 | 1
14 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at DEHAGANJE Mini PWSS (Out of 45 Nos. Mini PWSS) at SANKRAIL Block under Jhargram Division, PHE Dte. |  |  | ORD/000586/2020-2021 | 626/JSD | 22/02/2021 | 24/03/2021 | ASSOCIATED ENGINEERS & TRADERS | 4.55 | 0 | 0 | 1
15 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at RANDEBPUR Mini PWSS (Out of 45 Nos. Mini PWSS) at SANKRAIL Block under Jhargram Division, PHE Dte. |  |  | ORD/000588/2020-2021 | 628/JSD | 22/02/2021 | 24/03/2021 | ASSOCIATED ENGINEERS & TRADERS | 2.74 | 0 | 0 | 1
16 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Salpatra SSK Mini PWSS (Out of 45 Nos. Mini PWSS) at Binpur-II Block under Jhargram Division, PHE Dte. |  |  | ORD/000516/2020-2021 | 389/MD | 25/02/2021 | 12/03/2021 | J.S.S. ENTERPRISE | 5.24 | 0 | 0 | 1
17 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Kalmapukuria, Dakshin Sadar Para Mini PWSS (Out of 45 Nos. Mini PWSS) at Nayagram Block under Jhargram Division, PHE Dte. |  |  | ORD/000517/2020-2021 | 390/MD | 25/02/2021 | 12/03/2021 | PROVAT KUMAR DE | 5.99 | 5.99 | 100 | 1
18 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Bhalaidiha Mini PWSS (Out of 45 Nos. Mini PWSS) at Binpur-II Block under Jhargram Division, PHE Dte. |  |  | ORD/000515/2020-2021 | 388/MD | 25/02/2021 | 12/03/2021 | DEBABRATA DUTTA | 6.07 | 0 | 0 | 1
19 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Chirakuti Mini PWSS (Out of 45 Nos. Mini PWSS) at Sankrail Block under Jhargram Division, PHE Dte. |  |  | ORD/000064/2021-2022 | 1056/MD | 02/07/2021 | 17/07/2021 | ASIS KUMAR SARANGI | 8.95 | 0 | 0 | 1
20 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Balarampur Primary School Mini PWSS (Out of 45 Nos. Mini PWSS) at Binpur-I Block under Jhargram Division, PHE Dte. |  |  | ORD/000513/2020-2021 | 386/MD | 25/02/2021 | 12/03/2021 | SUNIL DULE | 4.96 | 0 | 0 | 1
21 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Gokhurpal Mini PWSS (Out of 45 Nos. Mini PWSS) at Nayagram Block under Jhargram Division, PHE Dte. |  |  | ORD/000062/2021-2022 | 825/MD | 03/06/2021 | 18/06/2021 | PROVAT KUMAR DE | 9.07 | 0 | 0 | 1
22 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Bansketia Mini PWSS (Out of 45 Nos. Mini PWSS) at Binpur-II Block under Jhargram Division, PHE Dte. |  |  | ORD/000202/2021-2022 | 1376/MD | 25/08/2021 | 09/09/2021 | SAIKAT DANDAPAT | 6.19 | 0 | 0 | 1
23 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Tapsia Mini PWSS (Out of 45 Nos. Mini PWSS) at Gopiballavpur-II Block under Jhargram Division, PHE Dte. |  |  | ORD/000250/2021-2022 | 1211/MD | 28/07/2021 | 12/08/2021 | MAMPI ENTERPRISE | 7.42 | 0 | 0 | 1
24 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Nischintapur Mini PWSS (Out of 45 Nos. Mini PWSS) at Jhargram Block under Jhargram Division, PHE Dte. (3rd Call) |  |  | ORD/000192/2021-2022 | 1375/MD | 25/08/2021 | 09/09/2021 | A R ENTERPRISE | 4.95 | 4.58 | 92.63 | 1
25 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Nepura Village Mini PWSS (Out of 45 Nos. Mini PWSS) at Binpur-I Block under Jhargram Division, PHE Dte. |  |  | ORD/000163/2021-2022 | 1286/MD | 09/08/2021 | 24/08/2021 | SUNIL DULE | 6.4 | 0 | 0 | 1
26 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Hatipada Mini PWSS (Out of 45 Nos. Mini PWSS) at Gopiballavpur-II Block under Jhargram Division, PHE Dte. |  |  | ORD/000204/2021-2022 | 1378/MD | 25/08/2021 | 09/09/2021 | S.B. TRADERS | 6.19 | 0 | 0 | 1
27 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Pasro Primary School Mini PWSS (Out of 45 Nos. Mini PWSS) at Jhargram Block under Jhargram Division, PHE Dte. (3rd Call) |  |  | ORD/000382/2021-2022 | 1939/MD | 24/11/2021 | 09/12/2021 | DHUMKETU ENGINEERING PRIVATE LIMITED | 6.24 | 0 | 0 | 1
28 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Jamunasole Mini PWSS (Out of 45 Nos. Mini PWSS) at Jamboni Block under Jhargram Division, PHE Dte. |  |  | ORD/000658/2020-2021 | 453/MD | 26/02/2021 | 13/03/2021 | NRIPENDRA NATH SINGHA | 5.99 | 0 | 0 | 1
29 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Bihankuria JR. High School Mini PWSS (Out of 45 Nos. Mini PWSS) at NAYAGRAM Block under Jhargram Division, PHE Dte. |  |  | ORD/000584/2020-2021 | 624/JSD | 22/02/2021 | 24/03/2021 | ASSOCIATED ENGINEERS & TRADERS | 3.93 | 0 | 0 | 1
30 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting with extension of distribution pipeline to accommodate FHTC under JJM in Barjharia Mini PWSS (out of 45 nos Mini pwss)(Phase-II) Block - Nayagram in the District of Jhargram |  |  | ORD/000868/2021-2022 | 34/JSD | 01/02/2022 | 16/02/2022 | PROVAT KUMAR DE | 3.07 | 0 | 0 | 1
31 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Sinking of 200 X 150 mm dia. X 165 mtr. rig bored replacement tubewell for Rukhnimara Mini W/S Scheme in connection with Retrofitting to Accommodate FHTC under JJM in 45nos. Mini PWSS at Nayagram Block under Jhargram Division, P.H.E. Dte. (As per ANNEXURE-III) |  | Junior Engineer-II,Junior Engineer-III | ORD/000123/2022-2023 | 585/JHD | 18/11/2022 | 09/12/2022 | BIDYUT KUMAR SANTRA | 6.56 | 0 | 0 | 1
32 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at AUSHPAL ADIBASHI PARA Mini PWSS (Out of 45 Nos. Mini PWSS) at JHARGRAM Block under Jhargram Division, PHE Dte. |  |  | VCH/001747/2021-2022 | BP-2021-22-490 | 16/03/2022 | 16/03/2022 | S.B. TRADERS | 0.77 | 0 | 0 | 0
33 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | FHTC of 45 Drought. |  |  | VCH/001929/2021-2022 | BP-2021-22-103 | 03/03/2022 | 03/03/2022 | BISHNU PADA NANDI | 0.03 | 0 | 0 | 0
34 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Kui (Yartri Patikashaloy) Mini PWSS ( out of 45 nos. Mini PWSS) at Binpur-I Block under Jhargram division, PHE Dte. |  |  | VCH/000050/2022-2023 |  | 26/09/2022 | 26/09/2022 | RAMENDRA NATH KAR | 3.6 | 0 | 0 | 0
35 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Bhaliaghati Mini PWSS (Out of 45 Nos. Mini PWSS) at NAYAGRAM Block under Jhargram Division, PHE Dte. |  |  | VCH/001622/2021-2022 | BP-2021-22-425 | 02/03/2022 | 02/03/2022 | BISHNU PADA NANDI | 3.38 | 0 | 0 | 0
36 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC with extension of pipeline under JJM in Kui mini PWSS ( out of 45 mini PWSS ) ( Phase-II) Block : Binpur-I in district of Jhargram |  |  | VCH/000051/2022-2023 |  | 26/09/2022 | 26/09/2022 | RAMENDRA NATH KAR | 5.56 | 0 | 0 | 0
37 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Nuasi Mini PWSS (Out of 45 Nos. Mini PWSS) at Nayagram Block under Jhargram Division, PHE Dte. |  |  | VCH/001715/2021-2022 | BP-2021-22-455 | 11/03/2022 | 11/03/2022 | GOUTAM PARIA | 4.91 | 0 | 0 | 0
38 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Naupara PWSS of Gopiballavpur-II Block under Jhargram Division, PHE Dte. |  |  | ORD/000184/2020-2021 | 1412/MD | 26/11/2020 | 25/05/2021 | ASIS KUMAR SARANGI | 36.77 | 0 | 0 | 80
39 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Jhitka PWSS of Binpur-I Block under Jhargram Division, PHE Dte. |  |  | ORD/000283/2020-2021 | 1582/MD | 11/12/2020 | 09/06/2021 | RAMENDRA NATH KAR | 15.06 | 0 | 0 | 80
40 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Continuation Work Order For "Hire charges of Bharat Stage-II / III Diesel Motor Cabs (Luxury Taxi) / Maruti Omni (Standard-Non-Air Conditioned) having Contract Carriage Permit from the Regional Transport Authority for the Office of the Executive Engineer, Jhargram Division, PHE Dte. for the period of 6 (six) Month's, from 01.09.2022 to 28.02.2023. | Assistant Engineer |  | ORD/000140/2022-2023 | 474/JSD | 29/08/2022 | 28/02/2023 | SUNIL DULE | 0.86 | 0 | 0 | 90
41 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Manikpara High School Mini PWSS (Out of 45 Nos. Mini PWSS) at Jhargram Block under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-II,Junior Engineer-III | ORD/000150/2021-2022 | 1212/MD | 28/07/2021 | 12/08/2021 | MAMPI ENTERPRISE | 7.01 | 0 | 0 | 1
42 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Hiring of 1 (one) no, Motor Cab (standard) Commercial with Catalytic Converter attachment with Bharat Stage as per prevalent applicable standard compliant new /not older than 30 (thirty) months from the date of 1st registration on daily hire rate basis for 12 (Twelve) months only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Executive Engineer, Jhargram Division PHE Dte. (Period from 01.09.2021 to 31.08.2022) | Assistant Engineer |  | ORD/000188/2021-2022 | 186/JSD | 26/08/2021 | 26/08/2022 | SUNIL DULE | 1.52 | 0 | 0 | 100
43 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Book Binding and photo copy of Tender Documents of different works and official paper for the JJM works and others establishment works under office of the Engineer, Jhargram Division, PHE Dte. (Period from 15.01.2023 to 14.07.2023) | Assistant Engineer |  | ORD/000343/2022-2023 | 33A/JRWS | 17/01/2023 | 16/07/2023 | PRINT PREVIEW | 0.96 | 0 | 0 | 80
44 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at BHURURDIHI Mini PWSS (Out of 45 Nos. Mini PWSS) at GOPIBALLAVPUR-I Block under Jhargram Division, PHE Dte. |  |  | ORD/000579/2020-2021 | 619/JSD | 22/02/2021 | 24/03/2021 | SRIMANTA KUMAR DE | 4.29 | 4.22 | 98.34 | 0
45 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Providing FHTC at Nuasai village (45 mini scheme) under JJM in the District of Jhargram under Jhargram Division. P.H.E Dte. |  | Junior Engineer-II,Junior Engineer-III | ORD/000064/2022-2023 | 507/JSD | 13/09/2022 | 04/10/2022 | MANDAL ENTERPRISE | 1.75 | 0 | 0 | 1
46 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Hatikadua Mini PWSS (Out of 45 Nos. Mini PWSS) at Jamboni Block under Jhargram Division, PHE Dte | Assistant Engineer | Junior Engineer-II,Junior Engineer-III | ORD/000004/2021-2022 | 1224/MD | 29/07/2021 | 13/08/2021 | NIRMAL DUTTA | 5.99 | 0 | 0 | 1
47 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Raipal mini PWSS (Out of 45 Nos. Mini PWSS) at Gopiballavpur-II Block under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000166/2021-2022 | 1057/MD | 02/07/2021 | 17/07/2021 | ASIS KUMAR SARANGI | 8.25 | 0 | 0 | 100
48 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Ruknimara Mini PWSS (Out of 45 Nos. Mini PWSS) at Nayagram Block under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000167/2021-2022 | 1055/MD | 02/07/2021 | 17/07/2021 | ASIS KUMAR SARANGI | 5.82 | 0 | 0 | 100
49 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Extention Distribution pipe line for smooth functioning of Ghokurpal water (Out of 45 nos Mini PWSS) at Nayagram Block and providing due FHTC with extension pipeline of Banisole scheme (Out of 45 nos Mini PWSS) at Nayagram Block Within Jhargram Division, PHE dte. | Assistant Engineer | Junior Engineer-III | ORD/000301/2023-2024 | 376/GPSD | 03/10/2023 | 23/10/2023 | ASHIS SHEE | 3.96 | 0 | 0 | 100
50 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Jhitka PWSS of Binpur-I Block under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-III | ORD/000043/2020-2021 | 1582/MD | 11/12/2020 | 26/12/2020 | RAMENDRA NATH KAR | 5.71 | 0 | 0 | 90
51 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC with extension of pipeline under JJM in Kui Mini PWSS (out of 45 Nos. Mini PWSS) (Phase-II) Block - Binpur-I in the district of Jhargram. |  |  | ORD/000916/2021-2022 | 535/MD | 22/03/2022 | 06/04/2022 | RAMENDRA NATH KAR | 5.62 | 0 | 0 | 1
52 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Kui (Yatri Patikshaloy) Mini PWSS (Out of 45 Nos. Mini PWSS) at Binpur-I Block under Jhargram Division, PHE Dte. |  |  | ORD/000127/2021-2022 | 1223/MD | 29/07/2021 | 13/08/2021 | RAMENDRA NATH KAR | 9.07 | 0 | 0 | 1
53 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Transfer money to EE/JSD PFMS bank account. |  |  | BILL/00725/2022-2023 | BP-2022-23-692 | 10/03/2023 | 10/03/2023 | EXECUTIVE ENGINEER, JHARGRAM CIVIL DIVISION, PHE DTE. | 8.33 | 0 | 0 | 0
54 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Hiring of 1 (one) no, Motor Cab (standard) Commercial with Catalytic Converter attachment with Bharat Stage as per prevalent applicable standard compliant new /not older than 30 (thirty) months from the date of 1st registration on daily hire rate basis for 12 (Twelve) months only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Assistant Engineer, Gopiballavpur Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000017/2022-2023 | 329/JSD | 30/06/2022 | 30/06/2023 | SAIKAT DANDAPAT | 1.7 | 0 | 0 | 100
55 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Kui (Yatri Patikshaloy) Mini PWSS (Out of 45 Nos. Mini PWSS) at Binpur-I Block under Jhargram Division, PHE Dte. |  | Junior Engineer-II,Junior Engineer-III | ORD/000107/2021-2022 | 1223/MD | 29/07/2021 | 13/08/2021 | RAMENDRA NATH KAR | 9.07 | 0 | 0 | 100
56 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC with extension of pipeline under JJM in Kui Mini PWSS (out of 45 Nos. Mini PWSS) (Phase-II) Block - Binpur-I in the district of Jhargram. |  | Junior Engineer-II,Junior Engineer-III | ORD/000108/2021-2022 | 535/MD | 22/03/2022 | 06/04/2022 | RAMENDRA NATH KAR | 5.62 | 0 | 0 | 100
57 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Hiring of 1 (one) no, Motor Cab (standard) Commercial with Catalytic Converter attachment with Bharat Stage as per prevalent applicable standard compliant new /not older than 30 (thirty)months from the date of 1st registration on daily hire rate basis for 12 (Twelve) months only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Assistant Engineer, Jhargram H.Q./RWS/Gopiballavpur Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000209/2022-2023 | 408/JSD | 29/07/2022 | 29/07/2023 | JAGOMOHAN SETUA | 1.7 | 0 | 0 | 80
58 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Hiring of 1 (one) no, Motor Cab (standard) Commercial with Catalytic Converter attachment with Bharat Stage as per prevalent applicable standard compliant new not older than 30 thirty) months from the date of 1st registration on daily hire rate basis for 12 (Twelve) months only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Assistant Engineer, Jhargram Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division,Junior Engineer-III | ORD/000188/2023-2024 | 775/JSD | 31/08/2023 | 01/08/2024 | BIDYUT KUMAR SANTRA | 1.88 | 0 | 0 | 100
59 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Balance Replacement of distribution pipe line (part) for Ramgarh water supply scheme (Zone-I & Zone-II). | Assistant Engineer | Junior Engineer Binpur-I block,Junior Engineer-III | ORD/000394/2023-2024 | 972/JSD | 10/11/2023 | 01/12/2023 | ASHIS SHEE | 4.77 | 0 | 0 | 80
60 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Naupara PWSS of Gopiballavpur-II Block under Jhargram Division, PHE Dte. | Assistant Engineer | The Junior Engineer-IV Jhargram Sub-Division | ORD/000044/2020-2021 | 1412/MD | 26/11/2020 | 11/12/2020 | ASIS KUMAR SARANGI | 5.24 | 0 | 0 | 100
61 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Installation of Display Bord for JJM works at different piped water supply scheme within Nayagram Block under Jhargram Division, PHE dte. (1st Phase) | Assistant Engineer Headquarter |  | ORD/000415/2023-2024 | 58/JHD | 10/01/2024 | 24/02/2024 | PRINT PREVIEW | 0.91 | 0 | 0 | 0
62 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Continuation of Work Order "Hire charges of Bharat Stage-11/III Diesel Motor Cabs (Luxury Taxi)/Maruti Omni (Standard - Non - Air Conditioned) having Contract Carriage Permit from the Regional Transport Authority for the Office of the Executive Engineer. Jhargram Division, PHE Dte. For the period of 2 (TWO) Month's from 01.07.2023 to 31.07.2023." | Assistant Engineer | Junior Engineer-II | ORD/000612/2023-2024 | 542/JSD | 30/06/2023 | 31/07/2023 | SUNIL DULE | 0.15 | 0 | 0 | 100
63 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at KADAMDIHA Mini PWSS (Out of 45 Nos. Mini PWSS) at Nayagram Block under Jhargram Division, PHE Dte. |  |  | ORD/000459/2020-2021 | 603/JSD | 09/02/2021 | 11/03/2021 | PROVAT KUMAR DE | 3.44 | 3.42 | 99.58 | 0
64 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at AUSHPAL ADIBASHI PARA Mini PWSS (Out of 45 Nos. Mini PWSS) at JHARGRAM Block under Jhargram Division, PHE Dte. |  |  | ORD/000581/2020-2021 | 621/JSD | 22/02/2021 | 24/03/2021 | S.B. TRADERS | 4.55 | 3.37 | 74.21 | 0
65 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at BARJHARIA ICDS Mini PWSS (Out of 45 Nos. Mini PWSS) at NAYAGRAM Block under Jhargram Division, PHE Dte. |  |  | ORD/000582/2020-2021 | 622/JSD | 22/02/2021 | 24/03/2021 | DHUMKETU ENGINEERING PRIVATE LIMITED | 2.66 | 2.43 | 91.45 | 0
66 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at BANKATI Mini PWSS (Out of 45 Nos. Mini PWSS) at SANKRAIL Block under Jhargram Division, PHE Dte. |  |  | ORD/000587/2020-2021 | 627/JSD | 22/02/2021 | 24/03/2021 | ASSOCIATED ENGINEERS & TRADERS | 4.38 | 0 | 0 | 0
67 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Sijua Mini PWSS (Out of 45 Nos. Mini PWSS) at Gopiballavpur-I Block under Jhargram Division, PHE Dte. |  |  | ORD/000656/2020-2021 | 451/MD | 26/02/2021 | 13/03/2021 | BISHNU PADA NANDI | 5.98 | 5.45 | 91.03 | 0
68 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at CHULBATA Mini PWSS (Out of 45 Nos. Mini PWSS) at GOPIBALLAVPUR-I Block under Jhargram Division, PHE Dte. |  |  | ORD/000577/2020-2021 | 617/JSD | 22/02/2021 | 24/03/2021 | SRIMANTA KUMAR DE | 4.29 | 3.95 | 91.99 | 0
69 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at GARHDOAR Mini PWSS (Out of 45 Nos. Mini PWSS) at GOPIBALLAVPUR-I Block under Jhargram Division, PHE Dte. |  |  | ORD/000578/2020-2021 | 618/JSD | 22/02/2021 | 24/03/2021 | SRIMANTA KUMAR DE | 4.75 | 4.29 | 90.47 | 0
70 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Chandabila Pry. School Mini PWSS (Out of 45 Nos. Mini PWSS) at Binpur-I Block under Jhargram Division, PHE Dte. |  |  | ORD/000580/2020-2021 | 620/JSD | 22/02/2021 | 24/03/2021 | SUNIL DULE | 4.75 | 0 | 0 | 0
71 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at BHURKUNDI Mini PWSS (Out of 45 Nos. Mini PWSS) at SANKRAIL Block under Jhargram Division, PHE Dte. |  |  | ORD/000585/2020-2021 | 625/JSD | 22/02/2021 | 24/03/2021 | THE TILES | 3.4 | 0 | 0 | 0
72 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at BANISOLE Mini PWSS (Out of 45 Nos. Mini PWSS) at Nayagram Block under Jhargram Division, PHE Dte. |  |  | ORD/000457/2020-2021 | 602/JSD | 09/02/2021 | 11/03/2021 | PROVAT KUMAR DE | 3.31 | 3.04 | 91.71 | 0
73 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Book binding and photocopy of Tender Documents of different works and official paper for the JJM works and others establishment works under office of the Superintending Engineer, Western Circle, P.H.E. Dte. (period from 01.01.2023 to 30.06.2023) | Assistant Engineer | Junior Engineer,Junior Engineer-III | ORD/000344/2022-2023 | 29B/JRWS | 28/12/2022 | 27/06/2023 | M/S PIJUSH PAL | 0.97 | 0 | 0 | 100
74 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Kui Mini PWSS (Out of 45 nos Mini PWSS) (Phase-III) Block - Binpur-I in the District of Jhargram. | Assistant Engineer | Junior Engineer, Jhargram Sub-Division | ORD/000335/2023-2024 | 939/JSD | 02/11/2023 | 23/11/2023 | SAURABH KAR | 1.28 | 0 | 0 | 100
75 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Sinking of 250 X 150 mm dia. X 150 mtr.rig bored tubewell for Augmentation of Ramgarh W/S Scheme in Binpur-I Block within Jhargram District under Jhargram Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000390/2023-2024 | 2099/JHD | 12/12/2023 | 27/12/2023 | SAURABH KAR | 7.03 | 0 | 0 | 100
76 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Installation of Display Bord for JJM works at different piped water supply scheme within Sankrail Block under Jhargram Division, PHE dte. (1st Phase) | Assistant Engineer Headquarter | Junior Engineer, Gopiballavpur Sub Division | ORD/000414/2023-2024 | 57/JHD | 10/01/2024 | 24/02/2024 | PRINT PREVIEW | 0.91 | 0 | 0 | 100
77 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Installation of Display Bord for JJM works at different piped water supply scheme within JhargramBlock under Jhargram Division, PHE dte. (1st Phase) | Assistant Engineer Headquarter | Junior Engineer, Gopiballavpur Sub Division | ORD/000412/2023-2024 | 55/JHD | 10/01/2024 | 24/02/2024 | GOPAL JANA | 0.91 | 0 | 0 | 100
78 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Installation of Display Bord for JJM works at different piped water supply scheme within Jamboni Block under Jhargram Division, PHE dte. (1st Phase) | Assistant Engineer Headquarter | Junior Engineer, Gopiballavpur Sub Division | ORD/000413/2023-2024 | 56/JHD | 10/01/2024 | 24/02/2024 | GOPAL JANA | 0.91 | 0 | 0 | 100
79 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Continuation work for book binding and photocopy of Tender Documents of different works and official paper for the J.J.M. works and others establishment works under office of the Superintending Engineer, Western Circle, P.H.E. Dte. (Period from 15.07.2023 to 14.01.2024) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-III | ORD/000605/2023-2024 | 151/JRWS | 12/07/2023 | 12/01/2024 | PRINT PREVIEW | 0.96 | 0 | 0 | 100
80 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Raipal Mini PWSS (Out of 45 Nos. Mini PWSS) at Gopiballavpur-II Block under Jhargram Division, PHE Dte. |  |  | ORD/000065/2021-2022 | 1057/MD | 02/07/2021 | 17/07/2021 | ASIS KUMAR SARANGI | 8.25 | 0 | 0 | 1
81 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Continuation work for Hiring charges of Bharat Stage-III Diesel Indigo ECS Car / Motor Cabs (Luxury Taxi) having contract Carriage permit from the Regional Transport Authority valid for the State of West Bengal not older than 30 month from the date of 1st Registration on monthly hire rate basis for the period from 01.07.2023 to 30.06.2024 (12 months)) for the office of the Assistant Engineer, Gopiballavpur Sub-Division, P.H.E. Dte. The cost inclusive of all charges due to the wages of Driver, Taxes, Insurance, fees etc. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000093/2023-2024 | 275/GPSD | 01/07/2023 | 01/07/2024 | SAIKAT DANDAPAT | 1.79 | 0 | 0 | 100
82 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Hiring of 1 (one) no, Motor Cab (standard) Commercial with Catalytic Converter attachment with Bharat Stage as per prevalent applicable standard compliant new /not older than 30 (thirty)months from the date of 1st registration on daily hire rate basis for 12 (Twelve) months only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Executive Engineer, Jhargram Division PHE Dte. ( For 12 months) | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000290/2023-2024 | 1228/JHD | 28/07/2023 | 28/07/2024 | SUNIL DULE | 2.05 | 0 | 0 | 100
83 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Hatipada Mini PWSS (Out of 45 nos Mini PWSS) (Phase-II) Block - Gopiballavpur-II in the District of Jhargram. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division | Junior Engineer-III | ORD/000334/2023-2024 | 938/JSD | 02/11/2023 | 23/11/2023 | MAA LAXMI ENTERPRISE | 1.51 | 0 | 0 | 100
84 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Hiring of 1 (one) no Motor Cab (standard) commercial with Catalatyic Converter attachement with Bharat Stage as per prevalent applicable standard compliant new not older than 30 (Thirty) months from the date of 1st registration on daily hire rate basis for 12 (Twelve) months only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Assistant Engineer, Gopiballavpur Sub-Division, PHE Dte. from 01.07.2024 to 30.06.2025). | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000223/2024-2025 | 461/GPSD | 28/06/2024 | 28/06/2025 | SAIKAT DANDAPAT | 2.05 | 0 | 0 | 0
85 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | SM/08029 | Retrofitting | Continuation Order for Hiring of 1 (one) no, Motor Cab (standard) Commercial with Catalytic Converter attachment with Bharat Stage as per prevalent applicable standard compliant new /not older than 30 (thirty)months from the date of 1st registration on daily hire rate basis for 5 (Five) months only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Executive Engineer, Jhargram Division PHE Dte. ( For 5 months) | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000328/2024-2025 | 1108/JHD | 01/08/2024 | 29/12/2024 | SUNIL DULE | 0.71 | 0 | 0 | 100
Total | [13 empty] | 429.03 | 64.66 | 15.07