## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Binpur-I | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. | SM/08081 | New | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Belpahari PWSS (Zone -I) in Binpur-II Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000122/2021-2022 | : 148/JSD | 12/08/2021 | 26/08/2021 | LEMNISCATE | 4.36 | 4.36 | 100 | 0
2 | JHARGRAM | Binpur-I | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. | SM/08081 | New | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Belpahari PWSS (Zone-II) in Binpur-II Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000121/2021-2022 | 149/JSD | 12/08/2021 | 26/08/2021 | LEMNISCATE | 4.59 | 4.59 | 100 | 0
3 | JHARGRAM | Binpur-I | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. | SM/08081 | New | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Silda Pond Based PWSS in Binpur-II Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000124/2021-2022 | 155/JSD | 12/08/2021 | 26/08/2021 | LEMNISCATE | 2.35 | 2.35 | 100 | 0
4 | JHARGRAM | Binpur-I | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. | SM/08081 | New | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Belpahari PWSS (Zone-III) in Binpur-II Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000130/2021-2022 | 150/ JSD | 12/08/2021 | 26/08/2021 | LEMNISCATE | 4.31 | 4.31 | 100 | 0
5 | JHARGRAM | Binpur-I | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. | SM/08081 | New | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Netai PWSS in Binpur-1Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000089/2021-2022 | : 75/JSD | 25/06/2021 | 09/07/2021 | RADIANT | 1.91 | 1.8 | 94.16 | 0
6 | JHARGRAM | Binpur-I | Midnapore Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. | SM/08081 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR / CWR locations of different proposed piped water supply scheme at Jhargram district under Drinking Water Mitigation Master Plan. [Name of proposed Scheme - Sankrail, Bakra, Ragra (Zone-I & Zone-II) & Nakrasuli of Sankrail Block, Pithapura, Chorchita, Mahapal, Dhadangiri, Kendana, Tentulia, Gohal Mara & Kuliana of Gopiballavpur-II Block, Sijua, Shaluka & Bandarboni of Binpur-I Block, Naharia of Jamboni Block in Jhargram district.] |  |  | ORD/000543/2021-2022 | 53/MD | 13/01/2022 | 14/03/2022 | DR. GOKUL MONDAL (PHD, PROFESSOR), | 81.24 | 66.91 | 82.35 | 0
7 | JHARGRAM | Binpur-I | Midnapore Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. | SM/08081 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR / CWR locations of different proposed piped water supply scheme at Jhargram district under Drinking Water Mitigation Master Plan. [Name of proposed Scheme - Sankrail, Bakra, Ragra (Zone-I & Zone-II) & Nakrasuli of Sankrail Block, Pithapura, Chorchita, Mahapal, Dhadangiri, Kendana, Tentulia, Gohal Mara & Kuliana of Gopiballavpur-II Block, Sijua, Shaluka & Bandarboni of Binpur-I Block, Naharia of Jamboni Block in Jhargram district.] |  |  | VCH/000288/2022-2023 | BP-2021-22-553 | 04/04/2022 | 04/04/2022 | JADAVPUR UNIVERSITY | 14.34 | 0 | 0 | 0
8 | JHARGRAM | Binpur-I | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. | SM/08081 | New | Consultancy Service for Geotechnical Investigation and Report preparation for OHR location of different PWSS in Jhargram District through Jadavpur University | Assistant Engineer,Assistant Engineer Headquarter | Junior Engineer-II | ORD/000417/2023-2024 | 82/JHD | 16/01/2024 | 15/02/2024 | JADAVPUR UNIVERSITY | 43.29 | 0 | 0 | 0
9 | JHARGRAM | Binpur-I | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. | SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Jamboni Block and Others Block under Jhargram Division, PHE dte. (4th Phase) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000734/2023-2024 | 240/GPSD | 12/03/2024 | 22/03/2024 | KARNAJORA AGNIBINA SEVA SAMITY | 0.97 | 0 | 0 | 100
10 | JHARGRAM | Binpur-I | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. | SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Binpur-II Block and Others Block under Jhargram Division,PHE dte. (2nd Phase) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000606/2023-2024 | 206/GPSD | 12/03/2024 | 22/03/2024 | ASHIS SHEE | 0.97 | 0.96 | 98.58 | 100
11 | JHARGRAM | Binpur-I | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. | SM/08081 | New | Preparation of documents for uploading in Parivesh Portal for clearance of forest land proposed for PWSS under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000592/2023-2024 | 447/JHD | 14/03/2024 | 13/04/2024 | CARTO | 4.83 | 4.83 | 100 | 100
12 | JHARGRAM | Binpur-I | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. | SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Sankrail Block and Others Block under Jhargram Division ,PHE dte.(2nd Phase) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000618/2023-2024 | 211/GPSD | 12/03/2024 | 22/03/2024 | MANDAL ENTERPRISE | 0.97 | 0.96 | 98.58 | 100
13 | JHARGRAM | Binpur-I | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. | SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Binpur-I Block and Others Block under Jhargram Division ,PHE dte.(3rd Phase) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000620/2023-2024 | 213/GPSD | 12/03/2024 | 22/03/2024 | ASHIS SHEE | 0.97 | 0.96 | 98.58 | 100
14 | JHARGRAM | Binpur-I | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. | SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Sankrail Block and Others Block under Jhargram Division ,PHE dte.(5th Phase) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000640/2023-2024 | 235/GPSD | 12/03/2024 | 22/03/2024 | MANDAL ENTERPRISE | 0.97 | 0.96 | 98.58 | 100
15 | JHARGRAM | Binpur-I | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. | SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Jhargram Block and Others Block under Jhargram Division ,PHE dte.(2nd Phase) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000617/2023-2024 | 209/GPSD | 12/03/2024 | 22/03/2024 | MANDAL ENTERPRISE | 0.97 | 0.96 | 98.58 | 100
16 | JHARGRAM | Binpur-I | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. | SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Jhargram Block and Others Block under Jhargram Division ,PHE dte.(3rd Phase) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000624/2023-2024 | 217/GPSD | 12/03/2024 | 22/03/2024 | MANDAL ENTERPRISE | 0.97 | 0.96 | 98.58 | 100
17 | JHARGRAM | Binpur-I | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. | SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Sankrail Block and Others Block under Jhargram Division ,PHE dte.(3rd Phase) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000625/2023-2024 | 219/GPSD | 12/03/2024 | 22/03/2024 | MANDAL ENTERPRISE | 0.97 | 0.96 | 98.58 | 100
18 | JHARGRAM | Binpur-I | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. | SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Gopiballavpur-II Block and Others Block under Jhargram Division ,PHE dte.(4th Phase) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000630/2023-2024 | 224/GPSD | 12/03/2024 | 22/03/2024 | MAHAVIR SAMPARK PVT. LTD. | 0.97 | 0.96 | 98.58 | 100
19 | JHARGRAM | Binpur-I | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. | SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Binpur-II Block and Others Block under Jhargram Division ,PHE dte.(5th Phase) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000635/2023-2024 | 230/GPSD | 12/03/2024 | 22/03/2024 | ASHIS SHEE | 0.97 | 0.96 | 98.58 | 100
20 | JHARGRAM | Binpur-I | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. | SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Gopiballavpur-II Block and Others Block under Jhargram Division ,PHE dte.(5th Phase) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000637/2023-2024 | 232/GPSD | 12/03/2024 | 22/03/2024 | MAHAVIR SAMPARK PVT. LTD. | 0.97 | 0.96 | 98.58 | 100
21 | JHARGRAM | Binpur-I | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. | SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Binpur-I Block and Others Block under Jhargram Division ,PHE dte.(2nd Phase) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000614/2023-2024 | 205/GPSD | 12/03/2024 | 22/03/2024 | ASHIS SHEE | 0.97 | 0.96 | 98.58 | 100
22 | JHARGRAM | Binpur-I | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. | SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Gopiballavpur-I Block and Others Block under Jhargram Division ,PHE dte.(2nd Phase) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000615/2023-2024 | 207/GPSD | 12/03/2024 | 22/03/2024 | MAHAVIR SAMPARK PVT. LTD. | 0.97 | 0.96 | 98.58 | 100
23 | JHARGRAM | Binpur-I | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. | SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Binpur-II Block and Others Block under Jhargram Division ,PHE dte.(3rd Phase) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000621/2023-2024 | 214/GPSD | 12/03/2024 | 22/03/2024 | ASHIS SHEE | 0.97 | 0.96 | 98.58 | 100
24 | JHARGRAM | Binpur-I | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. | SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Gopiballavpur-I Block and Others Block under Jhargram Division ,PHE dte.(3rd Phase) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000622/2023-2024 | 215/GPSD | 12/03/2024 | 22/03/2024 | MAHAVIR SAMPARK PVT. LTD. | 0.97 | 0.96 | 98.58 | 100
25 | JHARGRAM | Binpur-I | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. | SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Gopiballavpur-I Block and Others Block under Jhargram Division ,PHE dte.(5th Phase) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000636/2023-2024 | 231/GPSD | 12/03/2024 | 22/03/2024 | MAHAVIR SAMPARK PVT. LTD. | 0.97 | 0.96 | 98.58 | 100
26 | JHARGRAM | Binpur-I | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. | SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Nayagram Block and Others Block under Jhargram Division ,PHE dte.(5th Phase) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000641/2023-2024 | 236/GPSD | 12/03/2024 | 22/03/2024 | ASHIS SHEE | 0.97 | 0.95 | 98.58 | 100
27 | JHARGRAM | Binpur-I | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. | SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Binpur-I Block and Others Block under Jhargram Division ,PHE dte.(4th Phase) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000627/2023-2024 | 221/GPSD | 12/03/2024 | 22/03/2024 | ASHIS SHEE | 0.97 | 0.96 | 98.58 | 100
28 | JHARGRAM | Binpur-I | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. | SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Gopiballavpur-I Block and Others Block under Jhargram Division ,PHE dte.(4th Phase) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000629/2023-2024 | 223/GPSD | 12/03/2024 | 22/03/2024 | MAHAVIR SAMPARK PVT. LTD. | 0.97 | 0.96 | 98.58 | 100
29 | JHARGRAM | Binpur-I | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. | SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Jhargram Block and Others Block under Jhargram Division ,PHE dte.(4th Phase) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000631/2023-2024 | 225/GPSD | 12/03/2024 | 22/03/2024 | MANDAL ENTERPRISE | 0.97 | 0.96 | 98.58 | 100
30 | JHARGRAM | Binpur-I | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. | SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Sankrail Block and Others Block under Jhargram Division ,PHE dte.(4th Phase) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000632/2023-2024 | 227/GPSD | 12/03/2024 | 22/03/2024 | MANDAL ENTERPRISE | 0.97 | 0.96 | 98.58 | 100
31 | JHARGRAM | Binpur-I | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. | SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Nayagram Block and Others Block under Jhargram Division ,PHE dte.(4th Phase) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000633/2023-2024 | 228/GPSD | 12/03/2024 | 22/03/2024 | ASHIS SHEE | 0.97 | 0.96 | 98.58 | 100
32 | JHARGRAM | Binpur-I | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. | SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Binpur-I Block and Others Block under Jhargram Division ,PHE dte.(5th Phase) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000634/2023-2024 | 229/GPSD | 12/03/2024 | 22/03/2024 | ASHIS SHEE | 0.97 | 0.95 | 98.58 | 100
33 | JHARGRAM | Binpur-I | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. | SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Nayagram Block and Others Block under Jhargram Division ,PHE dte.(3rd Phase) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000626/2023-2024 | 220/GPSD | 12/03/2024 | 22/03/2024 | ASHIS SHEE | 0.97 | 0.96 | 98.58 | 100
34 | JHARGRAM | Binpur-I | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. | SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Binpur-II Block and Others Block under Jhargram Division ,PHE dte.(4th Phase) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000628/2023-2024 | 222/GPSD | 12/03/2024 | 22/03/2024 | ASHIS SHEE | 0.97 | 0.96 | 98.58 | 100
35 | JHARGRAM | Binpur-I | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. | SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Jhargram Block and Others Block under Jhargram Division ,PHE dte.(5th Phase) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000638/2023-2024 | 233/GPSD | 12/03/2024 | 22/03/2024 | MANDAL ENTERPRISE | 0.97 | 0.96 | 98.58 | 100
36 | JHARGRAM | Binpur-I | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. | SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Jamboni Block and Others Block under Jhargram Division ,PHE dte.(5th Phase) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000639/2023-2024 | 234/GPSD | 12/03/2024 | 22/03/2024 | MANDAL ENTERPRISE | 0.97 | 0.96 | 98.58 | 100
37 | JHARGRAM | Binpur-I | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. | SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Gopiballavpur-II Block and Others Block under Jhargram Division ,PHE dte.(2nd Phase) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000616/2023-2024 | 208/GPSD | 12/03/2024 | 22/03/2024 | MAHAVIR SAMPARK PVT. LTD. | 0.97 | 0.96 | 98.58 | 100
38 | JHARGRAM | Binpur-I | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. | SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Nayagram Block and Others Block under Jhargram Division ,PHE dte.(2nd Phase) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000619/2023-2024 | 212/GPSD | 12/03/2024 | 22/03/2024 | ASHIS SHEE | 0.97 | 0.95 | 98.58 | 100
39 | JHARGRAM | Binpur-I | Jhargram Division | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. | SM/08081 | New | Installation of display board for JJM works at different piped water supply scheme within Gopiballavpur-II Block and Others Block under Jhargram Division ,PHE dte.(3rd Phase) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000623/2023-2024 | 216/GPSD | 12/03/2024 | 22/03/2024 | MAHAVIR SAMPARK PVT. LTD. | 0.97 | 0.96 | 98.58 | 100
Total | [13 empty] | 190.33 | 116.89 | 61.41