## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Midnapore Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Dhamro P.W.S.S. Within Binpur I Block Under Jhargram Division, P.H.E. Dte | SM/08733 | Retrofitting | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Dhamro PWSS in Binpur-I Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. |  |  | ORD/000275/2021-2022 | 102/JSD | 13/07/2021 | 27/07/2021 | M/S R. DUTTA & CO | 1.59 | 0 | 0 | 1
2 | JHARGRAM |  | Jhargram Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Dhamro P.W.S.S. Within Binpur I Block Under Jhargram Division, P.H.E. Dte | SM/08733 | Retrofitting | Extension distribution pipeline in connection with retrofitting to accommodate FHTC in Dhamro PWSS Block - Binpur-I under Jhargram Sub-Division,PHE Dte. | Assistant Engineer | Junior Engineer-III | ORD/000033/2022-2023 | 429/JSD | 05/08/2022 | 26/08/2022 | PRANOY KUMAR UKIL | 4.67 | 0 | 0 | 1
3 | JHARGRAM |  | Jhargram Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Dhamro P.W.S.S. Within Binpur I Block Under Jhargram Division, P.H.E. Dte | SM/08733 | Retrofitting | Replacement of pipeline by higher diameter pipe at Kanipal Mouza in connection with retrofitting to accommodate FHTC in Dhamro PWSS Block - Binpur-I under Jhargram Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000030/2022-2023 | 428/JSD | 05/08/2022 | 26/08/2022 | SAMIR PATRA | 2.91 | 0 | 0 | 1
4 | JHARGRAM |  | Jhargram Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Dhamro P.W.S.S. Within Binpur I Block Under Jhargram Division, P.H.E. Dte | SM/08733 | Retrofitting | Retrofitting and allied works to accommodate FHTC under JJM in Dhamro PWSS within Binpur-I Block under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-III | ORD/000141/2021-2022 | 1690/MD | 30/09/2021 | 15/10/2021 | SAIKAT DANDAPAT | 33.29 | 0 | 0 | 0
5 | JHARGRAM |  | Midnapore Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Dhamro P.W.S.S. Within Binpur I Block Under Jhargram Division, P.H.E. Dte | SM/08733 | Retrofitting | Transfer to EXECUTIVE ENGINEER, JHARGRAM CIVIL DIVISION, PHE DTE. PFMS bank account. |  |  | BILL/00727/2022-2023 | BP-2022-23-690 | 10/03/2023 | 10/03/2023 | EXECUTIVE ENGINEER, JHARGRAM CIVIL DIVISION, PHE DTE. | 9.21 | 0 | 0 | 0
6 | JHARGRAM |  | Midnapore Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Dhamro P.W.S.S. Within Binpur I Block Under Jhargram Division, P.H.E. Dte | SM/08733 | Retrofitting | Retrofitting and allied works to accommodate FHTC under JJM in Dhamro PWSS within Binpur-I Block under Jhargram Division, PHE Dte. |  |  | ORD/000283/2021-2022 | 1690/MD | 30/09/2021 | 15/10/2021 | SAIKAT DANDAPAT | 33.29 | 0 | 0 | 1
Total | [13 empty] | 84.94 | 0 | 0