## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Midnapore Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Laudaha P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. | SM/08734 | Retrofitting | Retrofitting and allied works to accommodate FHTC under JJM in Laudaha PWSS within Sankrail Block under Jhargram Division, PHE Dte. |  |  | ORD/000227/2021-2022 | 1535/MD | 13/09/2021 | 28/09/2021 | S.T. ENTERPRISE | 29.73 | 47.07 | 158.33 | 1
2 | JHARGRAM |  | Midnapore Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Laudaha P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. | SM/08734 | Retrofitting | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Sasarah PWSS in Gopiballavpur-I Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. |  |  | VCH/001596/2021-2022 | BP-2021-22-403 | 23/02/2022 | 23/02/2022 | ROY CHOWDHURY ASSOCIATES | 1.67 | 0 | 0 | 0
3 | JHARGRAM |  | Jhargram Mechanical Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Laudaha P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. | SM/08734 | Retrofitting | Payment for new service connection of WBSEDCL. |  |  | VCH/000725/2022-2023 | 24/JMD/PFMS/SEP | 14/09/2022 | 14/09/2022 | WBSEDCL | 0.35 | 0 | 0 | 0
4 | JHARGRAM |  | Jhargram Mechanical Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Laudaha P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. | SM/08734 | Retrofitting | Repairing & rejuvenation of various installed electro mechanical accessories for augmentation of ground water based water supply scheme for Laudaha Pump house no. II to accommodate FHTC at Sankrail block in Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer |  | ORD/000068/2022-2023 | 1126/JMD | 10/06/2022 | 10/07/2022 | MENAKA ENTERPRISE | 8.33 | 8.26 | 99.16 | 0
5 | JHARGRAM |  | Jhargram Mechanical Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Laudaha P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. | SM/08734 | Retrofitting | Supply & delivery of stand by submersible pumping machinery at pump house no. II of Laudaha ground water based water supply scheme of Sankrail block of Jhargram Dist. under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer |  | ORD/000750/2022-2023 | 163/JMD | 27/01/2023 | 03/02/2023 | MENAKA ENTERPRISE | 0.5 | 0.49 | 99.01 | 0
6 | JHARGRAM |  | Jhargram Mechanical Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Laudaha P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. | SM/08734 | Retrofitting | Supply, delivery, installation of various electro-mechanical accessories for Laudaha W/S scheme, T/W no. I to accommodate FHTC at Sankrail block in the dist. of Jhargram under Jhargram Mechanical Division, PHE Dte. | Assistant Engineer | JE (M) | ORD/000173/2023-2024 | 2099/JMD | 03/08/2023 | 02/09/2023 | P.K. ENGINEERING | 2.37 | 2.29 | 96.75 | 100
Total | [13 empty] | 42.93 | 58.11 | 135.35