## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Midnapore Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Rohini P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. | SM/08735 | Retrofitting | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Rohini PWSS in Sankrail Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. |  |  | ORD/000272/2021-2022 | 61/JSD | 18/06/2021 | 02/07/2021 | ROY CHOWDHURY ASSOCIATES | 4.38 | 4.38 | 100 | 1
2 | JHARGRAM |  | Jhargram Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Rohini P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. | SM/08735 | Retrofitting | Retrofitting of Ground Water Based Water Supply Scheme for Rohini PWSS to Accommodate FHTC in Block - Sankrail under Jhargram Division, PHE Dte. |  |  | VCH/000009/2022-2023 | null | 02/08/2022 |  | ASIS KUMAR SARANGI | 14.92 | 0 | 0 | 0
3 | JHARGRAM |  | Jhargram Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Rohini P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. | SM/08735 | Retrofitting | Construction of Boundary wall for 2nd Tube well site of Rohini W/S Scheme under Jhargram Sub-Division within Jhargram Division, PHE Dte. (B/W Length = 71.00 Mtr.) |  |  | VCH/000008/2022-2023 | null | 02/08/2022 |  | ASSOCIATED ENGINEERS & TRADERS | 5.59 | 0 | 0 | 0
4 | JHARGRAM |  | Jhargram Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Rohini P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. | SM/08735 | Retrofitting | Repairing & Renovation of RCC Over Head Reservoir (Intze type with Coloum ) of capacity 250 cum at Rohini Water Supply Scheme under Jhargram Division within Jhargram Division P.H.E. Dte |  |  | VCH/000030/2022-2023 | null | 30/08/2022 |  | ASSOCIATED ENGINEERS & TRADERS | 4.61 | 0 | 0 | 0
5 | JHARGRAM |  | Jhargram Mechanical Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Rohini P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. | SM/08735 | Retrofitting | Dismantling the existing damaged voltage stabilizer and supply, delivery & installation of newly supplied three phase 15 KVA oil cooled type voltage stabilizer with other allied works at tube well no.II of Rohini water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000603/2021-2022 | 525/JMD | 22/03/2022 | 29/03/2022 | BEE GEE CONSTRUCTION | 2.28 | 2.24 | 97.98 | 0
6 | JHARGRAM |  | Jhargram Mechanical Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Rohini P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. | SM/08735 | Retrofitting | Supply, delivery & installation of submersible pumping machinery and other electro mechanical accessories at tubewell no.II of Rohini water supply scheme in Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer |  | ORD/000769/2021-2022 | 523/JMD | 22/03/2022 | 29/03/2022 | ORIENTAL ENGINEERING CO. | 4.55 | 4.55 | 99.82 | 0
7 | JHARGRAM |  | Jhargram Mechanical Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Rohini P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. | SM/08735 | Retrofitting | Dismantling the existing damaged voltage stabilizer and supply, delivery & installation of newly supplied single phase 20 KVA oil cooled type voltage stabilizer with other allied works at tube well no.-II of Rohini water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer |  | ORD/000245/2022-2023 | 924/JMD | 12/05/2022 | 19/05/2022 | PRANAB KUMAR DAS | 2.62 | 2.57 | 98.21 | 0
8 | JHARGRAM |  | Jhargram Mechanical Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Rohini P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. | SM/08735 | Retrofitting | Making compound lighting arrangement and allied works at tube well no.I (Head work site) of Rohini water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000802/2021-2022 | 526/JMD | 22/03/2022 | 29/03/2022 | SUBHRA ENTERPRISE | 2.96 | 2.84 | 96.21 | 0
9 | JHARGRAM |  | Jhargram Mechanical Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Rohini P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. | SM/08735 | Retrofitting | Supply, delivery & installation of submersible pumping machinery and other electro mechanical accessories at tube well no.I of Rohini water supply scheme in Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer |  | ORD/000814/2021-2022 | 522/JMD | 22/03/2022 | 29/03/2022 | SWAPAN ENTERPRISE | 4.42 | 4.4 | 99.7 | 0
10 | JHARGRAM |  | Jhargram Mechanical Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Rohini P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. | SM/08735 | Retrofitting | Supply , Delivery of multicore copper control cable for actuator connection at tube well no.II of Rohini water supply scheme in Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer |  | ORD/000508/2022-2023 | 2825/JMD | 16/09/2022 | 23/09/2022 | ORIENTAL ENGINEERING CO. | 0.16 | 0.12 | 80 | 0
11 | JHARGRAM |  | Jhargram Mechanical Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Rohini P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. | SM/08735 | Retrofitting | Supply, Delivery of multicore copper control cable for actuator connection at tube well no.I of Rohini water supply scheme in Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer |  | ORD/000507/2022-2023 | 2824/JMD | 16/09/2022 | 23/09/2022 | SWAPAN ENTERPRISE | 0.08 | 0.06 | 79.99 | 0
12 | JHARGRAM |  | Jhargram Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Rohini P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. | SM/08735 | Retrofitting | Repairing & Renovation of RCC Over Head Reservoir (Intze type with Coloum ) of capacity 250 cum at Rohini Water Supply Scheme under Jhargram Division within Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer Sankrail block | ORD/000086/2021-2022 | 172/JSD | 22/03/2022 | 21/04/2022 | ASSOCIATED ENGINEERS & TRADERS | 4.81 | 4.61 | 95.81 | 1
13 | JHARGRAM |  | Midnapore Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Rohini P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. | SM/08735 | Retrofitting | Retrofitting of Ground Water Based Water Supply Scheme for Rohini PWSS to Accommodate FHTC in Block - Sankrail under Jhargram Division, PHE Dte. |  |  | ORD/000254/2021-2022 | 1526/MD | 10/09/2021 | 09/11/2021 | ASIS KUMAR SARANGI | 136.63 | 68.67 | 50.26 | 0
14 | JHARGRAM |  | Jhargram Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Rohini P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. | SM/08735 | Retrofitting | Retrofitting of Ground Water Based Water Supply Scheme for Rohini PWSS to Accommodate FHTC in Block - Sankrail under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000001/2021-2022 | 1526/MD | 10/09/2021 | 09/11/2021 | ASIS KUMAR SARANGI | 136.63 | 14.92 | 10.92 | 95
15 | JHARGRAM |  | Jhargram Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Rohini P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. | SM/08735 | Retrofitting | Construction of Boundary wall for 2nd Tube well site of Rohini W/S Scheme under Jhargram Sub-Division within Jhargram Division, PHE Dte. (B/W Length = 71.00 Mtr.) | Assistant Engineer |  | ORD/000046/2022-2023 | 870/MD | 10/05/2022 | 09/06/2022 | ASSOCIATED ENGINEERS & TRADERS | 5.98 | 5.59 | 93.44 | 100
Total | [13 empty] | 330.6 | 114.95 | 34.77