## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Midnapore Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Sasarah P.W.S.S. Within Gopiballavpur I Block Under Jhargram Division, P.H.E. | SM/08736 | Retrofitting | Retrofitting and allied works to accommodate FHTC under JJM in Sasarah PWSS within Gopiballavpur-I Block under Jhargram Division, PHE Dte. |  |  | ORD/000265/2021-2022 | 1606/MD | 17/09/2021 | 08/10/2021 | SUNIL DULE | 44.65 | 77.13 | 172.76 | 1
2 | JHARGRAM |  | Midnapore Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Sasarah P.W.S.S. Within Gopiballavpur I Block Under Jhargram Division, P.H.E. | SM/08736 | Retrofitting | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Sasarah PWSS in Gopiballavpur-I Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. |  |  | VCH/001378/2021-2022 | BP-2021-22-370 | 23/02/2022 | 23/02/2022 | ROY CHOWDHURY ASSOCIATES | 1.8 | 0 | 0 | 0
3 | JHARGRAM |  | Jhargram Mechanical Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Sasarah P.W.S.S. Within Gopiballavpur I Block Under Jhargram Division, P.H.E. | SM/08736 | Retrofitting | Supply, delivery & installation of submersible pumping machinery and other electro mechanical accessories at tubewell no. I of Sasrah water supply scheme in Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000616/2022-2023 | 3634/JMD | 07/12/2022 | 06/01/2023 | SUJOY RANJAN BHOWMICK | 6.62 | 6.49 | 98.03 | 0
4 | JHARGRAM |  | Jhargram Mechanical Division | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Sasarah P.W.S.S. Within Gopiballavpur I Block Under Jhargram Division, P.H.E. | SM/08736 | Retrofitting | Supply, delivery & installation of submersible pumping machinery and other electro mechanical accessories at tubewell no. II of Sasrah water supply scheme in Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000617/2022-2023 | 3635/JMD | 07/12/2022 | 06/01/2023 | SUJOY RANJAN BHOWMICK | 5.78 | 5.63 | 97.43 | 0
Total | [13 empty] | 58.85 | 89.26 | 151.68