## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Midnapore Division | Augmentation of Ground Water Based Water supply scheme Chandal Bandh PWSS to Accommodate FHTC in Nayagram Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09372 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Chandalbandh PWSS in Nayagram Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. |  |  | VCH/001386/2021-2022 | BP-2021-22-395 | 22/02/2022 | 22/02/2022 | RADIANT | 3.78 | 0 | 0 | 0
2 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Chandal Bandh PWSS to Accommodate FHTC in Nayagram Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09372 | Augmentation | Rendering Consultancy Service for Geotechnical Investigation and Report preparation for OHR under Chandalbund Water Supply Scheme, Nayagram block of Jhargram District. | Assistant Engineer | Junior Engineer-II | ORD/000154/2023-2024 | 1385/JHD | 17/08/2023 | 16/09/2023 | JADAVPUR UNIVERSITY | 2.34 | 0 | 0 | 0
3 | JHARGRAM |  | Midnapore Division | Augmentation of Ground Water Based Water supply scheme Chandal Bandh PWSS to Accommodate FHTC in Nayagram Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09372 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000021/2021-2022 | 2165/MD | 17/12/2021 | 17/12/2021 | Resource Division | 0.05 | 0 | 0 | 0
4 | JHARGRAM |  | Midnapore Division | Augmentation of Ground Water Based Water supply scheme Chandal Bandh PWSS to Accommodate FHTC in Nayagram Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09372 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000043/2021-2022 | 498/MD | 15/03/2022 | 15/03/2022 | Resource Division | 15.18 | 0 | 0 | 0
5 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Chandal Bandh PWSS to Accommodate FHTC in Nayagram Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09372 | Augmentation | Proforma bill of Soil Testing for Constriction of 150 cum capaicty OHR at CHANDALBANDH for Augmentation of CHANDALBANDH PWSS in Nayagram Block under Jhargram Division, PHE Dte. |  |  | BILL/00309/2023-2024 | BP-2023-24-300 | 24/11/2023 | 24/11/2023 | JADAVPUR UNIVERSITY | 1.17 | 0 | 0 | 0
6 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Chandal Bandh PWSS to Accommodate FHTC in Nayagram Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09372 | Augmentation | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 150 cum and staging height 20 mtr as per approved drawing (No:- PC-1/OHR/15/2012) including supply of all labour & materials for Augmentation of Chandal Bandh W/S Scheme within Jhargram Sub-Division under Jhargram Division P.H.E Dte. | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division,Junior Engineer-II | ORD/000163/2022-2023 | 769/JHD | 30/12/2022 | 28/06/2023 | CHAKRABORTTI ENTERPRISE | 55.3 | 40.34 | 72.95 | 95
7 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of Ground Water Based Water supply scheme Chandal Bandh PWSS to Accommodate FHTC in Nayagram Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09372 | Augmentation | Quotation payment for Chandalbandh-III. |  |  | BILL/00024/2024-2025 | 23/JMD | 24/04/2024 | 24/04/2024 | WBSEDCL | 3.17 | 0 | 0 | 0
8 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Chandal Bandh PWSS to Accommodate FHTC in Nayagram Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09372 | Augmentation | Rendering Consultancy Service for Geological Investigation & Report Preparation for OHR under Chandalbund Water Supply Scheme, Nayagram block of Jhargram District. |  |  | BILL/00388/2024-2025 | BP-2024-25-204 | 20/09/2024 | 20/09/2024 | JADAVPUR UNIVERSITY | 1.17 | 0 | 0 | 0
9 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of Ground Water Based Water supply scheme Chandal Bandh PWSS to Accommodate FHTC in Nayagram Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09372 | Augmentation | Supply, delivery, installation & commissioning of submersible pumping machinery and other electro-mechanical accessories at proposed additional T/Well as a part of augmentation of Chandalbandh W/S scheme under Jhargram Mechanical Division, PHE Dte. in the dist. of Jhargram. | Assistant Engineer,Driller-In-Charge | JE (M),Junior Engineer | ORD/000168/2023-2024 | 2092/JMD | 03/08/2023 | 17/11/2025 | BUSR ENGINEERING | 12.08 | 0 | 0 | 100
10 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Chandal Bandh PWSS to Accommodate FHTC in Nayagram Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09372 | Augmentation | Laying Rising Main including Interconnection of Proposed Augmentation Chandalbundh & Its adjoining mouzas PWSS, Block: - Nayagram, District: - Jhargram. | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000219/2024-2025 | 712/GPSD | 17/12/2024 | 07/01/2025 | DHUMKETU ENGINEERING PRIVATE LIMITED | 1.3 | 0 | 0 | 50
11 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Chandal Bandh PWSS to Accommodate FHTC in Nayagram Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09372 | Augmentation | Supply & Delivery of CI&DI Specials Sluice valves etc. for laying of Rising Main , distribution main, including interconnection between Tube Well and Raising Main and OHR with by-pass arrangement for augmentation Chandalbundh and its adjoining mouzas Water Supply Scheme within Nayagram Block under Gopiballavpur Sub Division of Jhargram Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000130/2025-2026 | 362/GPSD | 22/07/2025 | 12/08/2025 | DHUMKETU ENGINEERING PRIVATE LIMITED | 1.82 | 0 | 0 | 0
Total | [13 empty] | 97.37 | 40.34 | 41.44