## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Midnapore Division | Augmentation of Ground Water Based Water supply scheme Lalgarh PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09373 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Lalgarh PWSS in Binpur-I Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. |  |  | ORD/000237/2021-2022 | 143/JSD | 12/08/2021 | 26/08/2021 | INDRANIL DUTTA & ASSOCIATES | 4.84 | 0 | 0 | 1
2 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Lalgarh PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09373 | Augmentation | Restoration work due to laying of PHE pipe line along Lalgarh Ramgarh Road (MDR ) and KPDL road (MDR) due to augmentation of Lalgarh pipe water supply scheme under Jhargram Division, PHE Dte. |  |  | VCH/000062/2022-2023 | BP-2022-23-38 | 20/10/2022 | 20/10/2022 | EXECUTIVE ENGINEER, PWD (ROADS) JHARGRAM | 18.7 | 0 | 0 | 0
3 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Lalgarh PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09373 | Augmentation | Functional Household Tap Connection data uploading charges of different pwss under Jhargram District in JJM_IMIS portal under Jal Jeevan Mission for January-2023 and February-2023 under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000253/2022-2023 | 29A/JRWS | 28/12/2022 | 26/02/2023 | PROVAT KUMAR DE | 0.93 | 0 | 0 | 100
4 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of Ground Water Based Water supply scheme Lalgarh PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09373 | Augmentation | Supply, delivery, installation & commissioning of electro-mechanical components at T/W no. III of Lalgarh water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer | JE (M) | ORD/000155/2023-2024 | 1942/JMD | 28/07/2023 | 12/08/2023 | M/S. CHANDRANATH MUKHERJEE | 9.27 | 0 | 0 | 100
5 | JHARGRAM |  | Midnapore Division | Augmentation of Ground Water Based Water supply scheme Lalgarh PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09373 | Augmentation | Laying of Clear Water Rising Main / Distribution pipe line and FHTC work including Construction and Commissioning of RCC Over Head Reservoir (Intze type with solid raft) of capacity 300 cum and staging height 20 mtr. with including supply of all labour & materials for Augmentation of Ground based Lalgarh PWSS in Binpur- I Block within Jhargram District under Jhargram Division, PHE Dte. |  |  | ORD/000055/2022-2023 | 875/MD | 10/05/2022 | 06/11/2022 | DULAL CHANDRA DAS | 329.37 | 0 | 0 | 0
6 | JHARGRAM |  | Midnapore Division | Augmentation of Ground Water Based Water supply scheme Lalgarh PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09373 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000042/2021-2022 | 498/MD | 15/03/2022 | 15/03/2022 | Resource Division | 18.23 | 0 | 0 | 0
7 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Lalgarh PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09373 | Augmentation | Lalgarh-Ramgarh road from 0.00 kmp to 1.50 kmp and KPDL Road from 34.00 kmp to 35.00 kmp with link road 1.05 km,restoration work for laying of pipeline due to augmentation of Lalgarh pipe water supply scheme by PHE Dte. under Jhargram Highway Division in the District of Jhargram. |  |  | BILL/00032/2023-2024 | BP-2023-24-36 | 15/05/2023 | 15/05/2023 | EXECUTIVE ENGINEER, PWD (ROADS) JHARGRAM | 31.65 | 0 | 0 | 0
8 | JHARGRAM |  | Midnapore Division | Augmentation of Ground Water Based Water supply scheme Lalgarh PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09373 | Augmentation | Transfer to EE/JSD, PHE Dte. ( Aug. of Lalgarh PWSS) |  |  | BILL/00611/2022-2023 | BP-2022-23-464 | 20/12/2022 | 20/12/2022 | EXECUTIVE ENGINEER, JHARGRAM CIVIL DIVISION, PHE DTE. | 98 | 0 | 0 | 0
9 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of Ground Water Based Water supply scheme Lalgarh PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09373 | Augmentation | Supply, delivery, installation & commissioning of electro-mechanical components at T/W no. I, II and renovation of existing compound lighting arrangement with other allied works at Lalgarh water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer | JE (M),Junior Engineer | ORD/000154/2023-2024 | 1941/JMD | 28/07/2023 | 27/08/2023 | M/S. EMMESS | 21.22 | 0 | 0 | 100
10 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of Ground Water Based Water supply scheme Lalgarh PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09373 | Augmentation | Meter shifting bill for Lalgarh pwss, P/H/ no.-II |  |  | BILL/01143/2023-2024 | 25/JMD | 15/01/2024 | 15/01/2024 | WBSEDCL | 0.11 | 0 | 0 | 0
11 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Lalgarh PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09373 | Augmentation | Supply delivery of Different dia CIDF S/V for the work of ¿ Augmentation of Ground Water Based Water Supply Scheme for Lalgarh to Accommodate FHTC in Block Binpur-I under Jhargram Sub Division within Jhargram Division, PHE Dte. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division | Junior Engineer-II | ORD/000038/2022-2023 | 434/JSD | 10/08/2022 | 17/08/2022 | DULAL CHANDRA DAS | 4.42 | 0 | 0 | 100
12 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Lalgarh PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09373 | Augmentation | Laying of Clear Water Rising Main / Distribution pipe line and FHTC work including Construction and Commissioning of RCC Over Head Reservoir (Intze type with solid raft) of capacity 300 cum and staging height 20 mtr. with including supply of all labour & materials for Augmentation of Ground based Lalgarh PWSS in Binpur- I Block within Jhargram District under Jhargram Division, PHE Dte. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer-III | ORD/000055/2022-2023 | 875/MD | 10/05/2022 | 22/04/2025 | DULAL CHANDRA DAS | 329.37 | 0 | 0 | 90
13 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Lalgarh PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09373 | Augmentation | Laying of Additional Distribution Pipe Line for Augmentation of Ground Water Based Lalgarh PWSS To Accommodate FHTC In Binpur-I Block within Jhargram district under Jhargram Division P.H.E Dte. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division | Junior Engineer, Gopiballavpur Sub Division,Junior Engineer, Jhargram Sub-Division | ORD/000176/2023-2024 | 1416/JHD | 22/08/2023 | 06/10/2023 | MAMPI ENTERPRISE | 10.1 | 0 | 0 | 90
14 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Lalgarh PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09373 | Augmentation | MS STRUCTURAL GANG WAY CUM BRIDGE FOR CROSSING 200 MM HDPE PIPE OF DISTRIBUTION MAIN OF LAGARH P.W.S.S. OVER SAHAR KHAL (LOCAL NAME) IN BETWEEN LALGARH AND CHUNPARA UNDER BINPUR -I DEV. BLOCK WITHIN JHARGRAM SUB-DIVISION UNDER JHARGRAM DIVISION P.H.E.DTE. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer-III | ORD/000399/2023-2024 | 973/JSD | 10/11/2023 | 01/12/2023 | MAMPI ENTERPRISE | 4.28 | 0 | 0 | 100
Total | [13 empty] | 880.49 | 0 | 0