## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Midnapore Division | Augmentation of Ground Water Based Water Supply Scheme for Gidhni PWSS to Accommodate FHTC in Jamboni Block, Jhargram District. | SM/09374 | Augmentation | Purchasing of Materials. |  |  | VCH/001683/2021-2022 | BP-2021-22-445 | 08/03/2022 | 08/03/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 5.58 | 0 | 0 | 0
2 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Gidhni PWSS to Accommodate FHTC in Jamboni Block, Jhargram District. | SM/09374 | Augmentation | Augmentation of Ground Water Based Water Supply Scheme for Gidhni PWSS to Accommodate FHTC in Jamboni Block, Jhargram District. |  |  | VCH/000017/2022-2023 |  | 11/08/2022 | 11/08/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 5.58 | 0 | 0 | 0
3 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Gidhni PWSS to Accommodate FHTC in Jamboni Block, Jhargram District. | SM/09374 | Augmentation | Functional Household Tap Connection data uploading charges of different pwss under Jhargram District in JJM_IMIS portal under Jal Jeevan Mission for January-2023 and February-2023 under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000253/2022-2023 | 29A/JRWS | 28/12/2022 | 26/02/2023 | PROVAT KUMAR DE | 0.93 | 0 | 0 | 100
4 | JHARGRAM |  | Midnapore Division | Augmentation of Ground Water Based Water Supply Scheme for Gidhni PWSS to Accommodate FHTC in Jamboni Block, Jhargram District. | SM/09374 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000017/2021-2022 | 2162/MD | 17/12/2021 | 17/12/2021 | Resource Division | 5.58 | 0 | 0 | 0
5 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Gidhni PWSS to Accommodate FHTC in Jamboni Block, Jhargram District. | SM/09374 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000015/2022-2023 | 305/JHD | 28/02/2023 | 28/02/2023 | Resource Division | 61.6 | 0 | 0 | 0
6 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Gidhni PWSS to Accommodate FHTC in Jamboni Block, Jhargram District. | SM/09374 | Augmentation | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for newly sunk tubewell for augmentation of Gidhni (Zone-I) water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000727/2022-2023 | 308/JMD | 09/02/2023 | 09/06/2023 | SUBHASIS ROY | 7.27 | 0 | 0 | 75
7 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Gidhni PWSS to Accommodate FHTC in Jamboni Block, Jhargram District. | SM/09374 | Augmentation | Construction of boundary wall, switch room & interconnection of T/Well for augmentation of Gidhni water supply scheme with in Jamboni block under Jhargram division, P.H.E. DTE. | Assistant Engineer | Junior Engineer-II,Junior Engineer-III | ORD/000045/2024-2025 | 1138/JHD | 06/08/2024 | 05/09/2024 | NRIPENDRA NATH SINGHA | 16.16 | 0 | 0 | 95
8 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Gidhni PWSS to Accommodate FHTC in Jamboni Block, Jhargram District. | SM/09374 | Augmentation | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Charichaka ICDS water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/001399/2023-2024 | 3081/JMD | 14/03/2024 | 12/07/2024 | DAS CONSTRUCTION | 5.82 | 0 | 0 | 0
9 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Gidhni PWSS to Accommodate FHTC in Jamboni Block, Jhargram District. | SM/09374 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Gidhni PWSS Part-II) in Jamboni Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000082/2021-2022 | 273/JSD | 07/10/2021 | 22/10/2021 | M/S R. DUTTA & CO | 3.95 | 0 | 0 | 100
10 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Gidhni PWSS to Accommodate FHTC in Jamboni Block, Jhargram District. | SM/09374 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Gidhni PWSS (Part-I) in Jamboni Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000081/2021-2022 | 240/JSD | 24/09/2021 | 09/10/2021 | M/S R. DUTTA & CO | 3.92 | 0 | 0 | 100
11 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Gidhni PWSS to Accommodate FHTC in Jamboni Block, Jhargram District. | SM/09374 | Augmentation | Construction of 3.60 M X 3.0 M size Switch Room-Cum-Guard room with Sanitary Arrangement & Construction of Boundary Wall (Length 34.00 mtr. ) for Gidhni (Zone-I) Water Supply Scheme within Jhargram Sub-Division Under Jhargram Division P.H.E. Dte. (2nd Call) | Assistant Engineer | Junior Engineer-II | ORD/000134/2023-2024 | 1326/JHD | 10/08/2023 | 24/09/2023 | NRIPENDRA NATH SINGHA | 9.36 | 0 | 0 | 100
12 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Gidhni PWSS to Accommodate FHTC in Jamboni Block, Jhargram District. | SM/09374 | Augmentation | Supply delivery of CIDF S/V for the work Augmentation Gidhni Water Supply Scheme under Jhargram Sub Division within Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000406/2023-2024 | 979/JSD | 17/11/2023 | 24/11/2023 | NIRMAL DUTTA | 0.93 | 0 | 0 | 100
13 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Gidhni PWSS to Accommodate FHTC in Jamboni Block, Jhargram District. | SM/09374 | Augmentation | New service connection charges |  |  | BILL/00850/2023-2024 | 30/JMD | 19/12/2023 | 19/12/2023 | WBSEDCL | 0.21 | 0 | 0 | 0
14 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Gidhni PWSS to Accommodate FHTC in Jamboni Block, Jhargram District. | SM/09374 | Augmentation | new service connection charges at Gidhni water supply scheme |  |  | BILL/00317/2024-2025 | 136/JMD | 24/05/2024 | 24/05/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
15 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Gidhni PWSS to Accommodate FHTC in Jamboni Block, Jhargram District. | SM/09374 | Augmentation | Providing fuel and lubricant for rig unit 238/AR/HALCO for boring purpose, augmentation of Ground water based water supply scheme for Gidhni (SM/09374) of two sites in Jamboni Block under Jhargram Division PHE Dte |  |  | BILL/00709/2024-2025 | 274/JMD | 26/07/2024 | 26/07/2024 | SURAJ SERVICE STATION | 1.01 | 0 | 0 | 0
16 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Gidhni PWSS to Accommodate FHTC in Jamboni Block, Jhargram District. | SM/09374 | Augmentation | Laying of Clear Water Rising main / Distribution pipe line and FHTC work for Augmentation of Ground based Gidhni PWSS (Zone-I to IV) to Accommodate FHTC in Jamboni Block within Jhargram District under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000093/2021-2022 | 432/MD | 04/03/2022 | 01/04/2025 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 321.65 | 0 | 0 | 60
17 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Gidhni PWSS to Accommodate FHTC in Jamboni Block, Jhargram District. | SM/09374 | Augmentation | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Gidhni ICDS water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/001398/2023-2024 | 3080/JMD | 14/03/2024 | 01/01/2025 | M/S. CHANDRANATH MUKHERJEE | 5.82 | 0 | 0 | 100
Total | [13 empty] | 455.58 | 0 | 0