## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Odalchua PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. | SM/09375 | Augmentation | Supply delivery of Different dia CIDF S/V for the work of ¿ Augmentation of Ground Water Based Water Supply Scheme for Odalchua to Accommodate FHTC in Block Binpur - II under Jhargram Sub Division within Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000037/2022-2023 | 427/JSD | 05/08/2022 | 12/08/2022 | SUNIL DULE | 3.44 | 3.44 | 100 | 1
2 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Odalchua PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. | SM/09375 | Augmentation | Supply, delivery& installation of submersible pumping machinary and other Electro-Mechanical accessories for newly sunk tube well under JJM programme at Odolchua water Supply scheme T/w no-1 (Chirakuti Mouza ,JL No-91) t under Jhargram Mechanical Division P.H.E Dte. in the district of Jhargram. | DIC(D)_MMSD(D) | JE (M) | ORD/000593/2022-2023 | 3326/JMD | 14/11/2022 | 14/12/2022 | DEBJYOTI BASU | 5.42 | 5.39 | 99.42 | 0
3 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Odalchua PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. | SM/09375 | Augmentation | Payment for new service connection of WBSEDCL. |  |  | VCH/000848/2022-2023 | 20/JMD/PFMS/SEP | 29/09/2022 | 29/09/2022 | WBSEDCL | 0.21 | 0 | 0 | 0
4 | JHARGRAM |  | Midnapore Division | Augmentation of Ground Water Based Water Supply Scheme for Odalchua PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. | SM/09375 | Augmentation | Sinking of 200 mm dia. X 165 mm dia. X 200 M depth Rig Bored Tubwell (Replacement) by DTH Method for Augmentation of Source of Odalchua PWSS under Jhargram Division P.H.E. Dte. |  |  | VCH/001733/2021-2022 | BP-2021-22-473 | 16/03/2022 | 16/03/2022 | SAIKAT DANDAPAT | 1.77 | 0 | 0 | 0
5 | JHARGRAM |  | Midnapore Division | Augmentation of Ground Water Based Water Supply Scheme for Odalchua PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. | SM/09375 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Odalchua PWSS in Binpur-II Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. |  |  | VCH/001380/2021-2022 | BP-2021-22-417 | 23/02/2022 | 23/02/2022 | LEMNISCATE | 2.24 | 0 | 0 | 0
6 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Odalchua PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. | SM/09375 | Augmentation | Augmentation of Ground Water Based Water Supply Scheme for Odalchua PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. |  |  | VCH/000016/2022-2023 |  | 11/08/2022 | 11/08/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 0.96 | 0 | 0 | 0
7 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Odalchua PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. | SM/09375 | Augmentation | Construction of 3.60 M X 3.0 M size Switch Room-Cum-Guard room with Sanitary Arrangement for Odalchua Water Supply Scheme within Jhargram Sub-Division P.H.E. Dte. Under Jhargram Division P.H.E.Dte. | Assistant Engineer |  | ORD/000026/2022-2023 | 389/JSD | 27/07/2022 | 10/09/2022 | SAIKAT DANDAPAT | 4.78 | 4.58 | 95.81 | 100
8 | JHARGRAM |  | Midnapore Division | Augmentation of Ground Water Based Water Supply Scheme for Odalchua PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. | SM/09375 | Augmentation | Laying of Clear Water Rising Main / Distribution pipe line and FHTC work for Augmentation of Ground Water Based Odalchua PWSS to Accommodate FHTC in Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. |  |  | ORD/000624/2021-2022 | 177/MD | 01/02/2022 | 18/03/2022 | PROVAT KUMAR DE | 47.08 | 28.39 | 60.3 | 1
9 | JHARGRAM |  | Midnapore Division | Augmentation of Ground Water Based Water Supply Scheme for Odalchua PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. | SM/09375 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000018/2021-2022 | 2160/MD | 17/12/2021 | 17/12/2021 | Resource Division | 1.36 | 0 | 0 | 0
10 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Odalchua PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. | SM/09375 | Augmentation | New Service connection |  |  | BILL/00669/2023-2024 | 17/JMD | 10/11/2023 | 10/11/2023 | WBSEDCL | 0.26 | 0 | 0 | 0
11 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Odalchua PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. | SM/09375 | Augmentation | New Service connection |  |  | BILL/00614/2023-2024 | 5/JMD | 11/10/2023 | 11/10/2023 | WBSEDCL | 0.36 | 0 | 0 | 0
12 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Odalchua PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. | SM/09375 | Augmentation | Laying of Clear Water Rising Main / Distribution pipe line and FHTC work for Augmentation of Ground Water Based Odalchua PWSS to Accommodate FHTC in Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000049/2021-2022 | 177/MD | 01/02/2022 | 18/03/2022 | PROVAT KUMAR DE | 47.08 | 17.41 | 36.98 | 100
13 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Odalchua PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. | SM/09375 | Augmentation | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Tube well no. II of Odalchua piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000585/2023-2024 | 2986/JMD | 16/10/2023 | 13/02/2024 | DEBJYOTI BASU | 7.08 | 6.98 | 98.57 | 100
14 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Odalchua PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. | SM/09375 | Augmentation | Supply delivery & Installation of on-line booster pumping machinery at Odalchua PWSS of Binpur-II block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | Driller-In-Charge | Junior Engineer | ORD/001367/2023-2024 | 2984/JMD | 13/03/2024 | 28/03/2024 | DEBJYOTI BASU | 3.12 | 3 | 96.02 | 100
15 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Odalchua PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. | SM/09375 | Augmentation | LAFT OUT HOUSEHOLD FOR ACCOMODATE FUNCTIONAL HOUSE TAP CONNECTION (F.H.T.C.), LAYING PIPE LINE CONNECTION AT DHOBAKACHA & CHIRAKUTI MOUZA UNDER AUGMENTATION OF ODALCHUA PWSS WITH IN BINPUR-II BLOCK UNDER JHARGRAM DIVISION, P.H.E. DTE. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-II | ORD/000102/2025-2026 | 435/JSD | 08/05/2025 | 15/05/2025 | MAHAVIR SAMPARK PVT. LTD. | 0.48 | 0 | 0 | 0
16 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Odalchua PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. | SM/09375 | Augmentation | REPAIRING OF EXISTING F.H.T.C AT MOUZA ODALCHUA UNDER ODALCHUA W/S SCHEME WITH IN BINPUR-II BLOCK UNDER JHARGRAM DIVISION, P.H.E. DTE | Assistant Engineer | Junior Engineer-II | ORD/000194/2024-2025 | 1082/JSD | 27/11/2024 | 11/12/2024 | DEBABRATA DUTTA | 0.97 | 0 | 0 | 100
17 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Odalchua PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. | SM/09375 | Augmentation | Providing solarization of WBSEDCL energised pumping installation at tube well no.-I & II of Odalchua w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | Driller-In-Charge | Junior Engineer | ORD/001368/2023-2024 | 2985/JMD | 13/03/2024 | 12/04/2024 | DEBJYOTI BASU | 6.26 | 0 | 0 | 100
Total | [13 empty] | 132.87 | 69.19 | 52.07