## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Midnapore Division | Rejuvenation of Ground Water Based Naupara PWSS to Accommodate FHTC in Gopiballavpur-II Block, Jhargram District. | SM/09376 | Augmentation | Laying of clear water rising main / distribution pipe line with FHTC work, Sinking of 250mm X 150mm dia. Rig bore Tube well, Construction & Commissioning of 150 CuM RCC OHR etc. for Rejuvenation of Ground Based Naupara PWSS to accommodate FHTC in Gopiballavpur-II block within Jhargram district under Jhargram Division, PHE Dte. |  |  | ORD/000910/2021-2022 | 499/MD | 15/03/2022 | 11/09/2022 | GHOSH ENTERPRISE | 77.25 | 0 | 0 | 0
2 | JHARGRAM |  | Jhargram Division | Rejuvenation of Ground Water Based Naupara PWSS to Accommodate FHTC in Gopiballavpur-II Block, Jhargram District. | SM/09376 | Augmentation | Laying of clear water rising main / distribution pipe line with FHTC work, Sinking of 250mm X 150mm dia. Rig bore Tube well, Construction & Commissioning of 150 CuM RCC OHR etc. for Rejuvenation of Ground Based Naupara PWSS to accommodate FHTC in Gopiballavpur-II block within Jhargram district under Jhargram Division, PHE Dte |  |  | VCH/000029/2022-2023 | null | 30/08/2022 |  | GHOSH ENTERPRISE | 19.8 | 0 | 0 | 0
3 | JHARGRAM |  | Jhargram Mechanical Division | Rejuvenation of Ground Water Based Naupara PWSS to Accommodate FHTC in Gopiballavpur-II Block, Jhargram District. | SM/09376 | Augmentation | Supply, delivery and Installation of new pumping machinery and other electro mechanical accessories at Naupara T/W no -II water supply scheme at Gopiballavpur-II block of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000412/2022-2023 | 1653/JMD | 01/08/2022 | 16/08/2022 | SHOVAN KUMAR DAS | 4.59 | 4.46 | 97.16 | 0
4 | JHARGRAM |  | Jhargram Division | Rejuvenation of Ground Water Based Naupara PWSS to Accommodate FHTC in Gopiballavpur-II Block, Jhargram District. | SM/09376 | Augmentation | Non Destructive Test of OHR for Naopara W/S at Gopiballavpur-II Block under Gopiballavpur Sub Division in Jhargram Division, PHE Dte. |  | Junior Engineer-III | ORD/000076/2022-2023 | 555/JSD | 27/09/2022 | 12/10/2022 | SIRCON ENGINEERING SERVICES | 1.71 | 1.71 | 100 | 1
5 | JHARGRAM |  | Jhargram Mechanical Division | Rejuvenation of Ground Water Based Naupara PWSS to Accommodate FHTC in Gopiballavpur-II Block, Jhargram District. | SM/09376 | Augmentation | Supply, delivery & installation of voltage stabilizer and other allied works at Naupara tubewell no.1 water supply scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000619/2022-2023 | 3638/JMD | 07/12/2022 | 06/01/2023 | SOUMEN ELECTRIC | 4.41 | 4.37 | 99.07 | 0
6 | JHARGRAM |  | Jhargram Division | Rejuvenation of Ground Water Based Naupara PWSS to Accommodate FHTC in Gopiballavpur-II Block, Jhargram District. | SM/09376 | Augmentation | Laying of clear water rising main / distribution pipe line with FHTC work, Sinking of 250mm X 150mm dia. Rig bore Tube well, Construction & Commissioning of 150 CuM RCC OHR etc. for Rejuvenation of Ground Based Naupara PWSS to accommodate FHTC in Gopiballavpur-II block within Jhargram district under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-III | ORD/000087/2021-2022 | 499/MD | 15/03/2022 | 11/09/2022 | GHOSH ENTERPRISE | 77.25 | 58.16 | 75.29 | 90
7 | JHARGRAM |  | Midnapore Division | Rejuvenation of Ground Water Based Naupara PWSS to Accommodate FHTC in Gopiballavpur-II Block, Jhargram District. | SM/09376 | Augmentation | Retrofitting to accommodate FHTC under JJM in Naupara PWSS of Gopiballavpur-II Block under Jhargram Division, PHE Dte. |  |  | ORD/000184/2020-2021 | 1412/MD | 26/11/2020 | 25/05/2021 | ASIS KUMAR SARANGI | 36.77 | 0 | 0 | 80
8 | JHARGRAM |  | Midnapore Division | Rejuvenation of Ground Water Based Naupara PWSS to Accommodate FHTC in Gopiballavpur-II Block, Jhargram District. | SM/09376 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000044/2021-2022 | 498/MD | 15/03/2022 |  | Resource Division | 15.18 | 0 | 0 | 0
9 | JHARGRAM |  | Jhargram Mechanical Division | Rejuvenation of Ground Water Based Naupara PWSS to Accommodate FHTC in Gopiballavpur-II Block, Jhargram District. | SM/09376 | Augmentation | Supply, delivery, installation of pumping machinery and allied electro-mechanical accessories within newly sunk replacement tube well at P/H no. I of Naupara water supply scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | Driller-In-Charge | Junior Engineer | ORD/001044/2023-2024 | 2122/JMD | 22/02/2024 | 23/03/2024 | JAGANNATH ENTERPRISE | 5.13 | 0 | 0 | 0
Total | [13 empty] | 242.09 | 68.7 | 28.38