## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Midnapore Division | Augmentation of Ground Water Based Water Supply Scheme for Pakuria PWSS to Accommodate FHTC in Jhargram Block, Jhargram District | SM/09377 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Pukuria PWSS in Jhargram Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. |  |  | ORD/000247/2021-2022 | 147/JSD | 12/08/2021 | 26/08/2021 | INDRANIL DUTTA & ASSOCIATES | 2.94 | 2.59 | 88.06 | 1
2 | JHARGRAM |  | Midnapore Division | Augmentation of Ground Water Based Water Supply Scheme for Pakuria PWSS to Accommodate FHTC in Jhargram Block, Jhargram District | SM/09377 | Augmentation | Sinking of 250mm X 150mm dia. & depth 150 Mtr. Rig bore Tube well - II for Augmentation of Pakuria W/S Scheme within Jhargram block under Jhargram Division, PHE Dte. |  |  | ORD/000017/2022-2023 | 614/MD | 04/04/2022 | 19/04/2022 | TAPAS KUMAR GIRI | 6.58 | 5.48 | 83.27 | 1
3 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Pakuria PWSS to Accommodate FHTC in Jhargram Block, Jhargram District | SM/09377 | Augmentation | Augmentation of Ground Water Based Water Supply Scheme for Pakuria PWSS to Accommodate FHTC in Jhargram Block, Jhargram District |  |  | VCH/000015/2022-2023 |  | 11/08/2022 | 11/08/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 1.21 | 0 | 0 | 0
4 | JHARGRAM |  | Midnapore Division | Augmentation of Ground Water Based Water Supply Scheme for Pakuria PWSS to Accommodate FHTC in Jhargram Block, Jhargram District | SM/09377 | Augmentation | Purchasing of Materials. |  |  | VCH/001684/2021-2022 | BP-2021-22-445 | 08/03/2022 | 08/03/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 1.21 | 0 | 0 | 0
5 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Pakuria PWSS to Accommodate FHTC in Jhargram Block, Jhargram District | SM/09377 | Augmentation | Laying of Clear Water Rising Main / Distribution pipe line and FHTC work including Sinking of 250mm X 150mm dia. & 150 Mtr. Depth Rig bored Tube well for Augmentation of Ground Water Based Pukuria PWSS to Accommodate FHTC in Jhargram Block within Jhargram District under Jhargram Division, PHE Dte. |  | Junior Engineer-III | ORD/000103/2021-2022 | 179/MD | 01/02/2022 | 02/04/2022 | ASHIM KUMAR DEY | 96.77 | 28.93 | 29.9 | 95
6 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Pakuria PWSS to Accommodate FHTC in Jhargram Block, Jhargram District | SM/09377 | Augmentation | Construction of 3.60 M X 3.0 M size Switch Room-Cum-Guard room with Sanitary Arrangement for Pukuria Water Supply Scheme within Jhargram Sub-Division P.H.E. Dte. Under Jhargram Division P.H.E.Dte. |  | Junior Engineer-III | ORD/000027/2022-2023 | 390/JSD | 27/07/2022 | 10/09/2022 | HRITWIK DUTTA | 4.72 | 4.56 | 96.67 | 1
7 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Pakuria PWSS to Accommodate FHTC in Jhargram Block, Jhargram District | SM/09377 | Augmentation | Supply delivery of Different dia CIDF S/V for the work of ¿ Augmentation of Ground Water Based Water Supply Scheme for Pukuria to Accommodate FHTC in Block Jhargram under Jhargram Sub Division within Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000036/2022-2023 | 366/JSD | 21/07/2022 | 28/07/2022 | ASHIM KUMAR DEY | 1.79 | 1.79 | 100 | 100
8 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Pakuria PWSS to Accommodate FHTC in Jhargram Block, Jhargram District | SM/09377 | Augmentation | Construction of Boundary Wall for 2nd tubewell site for augmentation of ground water based Pukuria PWSS to accommodate FHTC in Jhargram Block within Jhargram District under Jhargram Division P.H.E.Dte. (Length-122mtr,height- 2.3 mtr above G.L. ) | Assistant Engineer Headquarter | Junior Engineer-III | ORD/000093/2022-2023 | 457/JHD | 11/11/2022 | 10/01/2023 | TAPAS KUMAR JANA | 9.03 | 8.92 | 98.76 | 1
9 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Pakuria PWSS to Accommodate FHTC in Jhargram Block, Jhargram District | SM/09377 | Augmentation | Supply, delivery, installation, commissioning & trial run of pumping machinery and other electro mechanical accessories at newly sunk replacement tubwell no.II (Near Primary School) of Pukuria W/S scheme under Jhargram Mechanical Division, PHE. Dte in the dist. of Jhargram. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000724/2022-2023 | 305/JMD | 09/02/2023 | 09/06/2023 | RSA ENTERPRISE | 9.76 | 9.16 | 93.85 | 0
10 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Pakuria PWSS to Accommodate FHTC in Jhargram Block, Jhargram District | SM/09377 | Augmentation | Laying of rising main & distribution main(part) including interconnection between tube wells of augmentation of ground water based water supply scheme for Pukuria to accommodate FHTC within Jhargram Block Under Jhargram Sub- Division within Jhargram Division, P.H.E. Dte. | Assistant Engineer Headquarter | Junior Engineer-III | ORD/000214/2022-2023 | 344/JHD | 10/03/2023 | 09/05/2023 | ASHIM KUMAR DEY | 6.78 | 6.62 | 97.76 | 100
11 | JHARGRAM |  | Midnapore Division | Augmentation of Ground Water Based Water Supply Scheme for Pakuria PWSS to Accommodate FHTC in Jhargram Block, Jhargram District | SM/09377 | Augmentation | Laying of Clear Water Rising Main / Distribution pipe line and FHTC work including Sinking of 250mm X 150mm dia. & 150 Mtr. Depth Rig bored Tube well for Augmentation of Ground Water Based Pukuria PWSS to Accommodate FHTC in Jhargram Block within Jhargram District under Jhargram Division, PHE Dte. |  |  | ORD/000626/2021-2022 | 179/MD | 01/02/2022 | 02/04/2022 | ASHIM KUMAR DEY | 96.77 | 58.23 | 60.18 | 1
12 | JHARGRAM |  | Midnapore Division | Augmentation of Ground Water Based Water Supply Scheme for Pakuria PWSS to Accommodate FHTC in Jhargram Block, Jhargram District | SM/09377 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000020/2021-2022 | 2163/MD | 17/12/2021 | 17/12/2021 | Resource Division | 1.81 | 0 | 0 | 0
13 | JHARGRAM |  | Midnapore Division | Augmentation of Ground Water Based Water Supply Scheme for Pakuria PWSS to Accommodate FHTC in Jhargram Block, Jhargram District | SM/09377 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000011/2022-2023 | 2164/MD | 21/10/2022 | 21/10/2022 | Resource Division | 5.12 | 0 | 0 | 0
14 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Pakuria PWSS to Accommodate FHTC in Jhargram Block, Jhargram District | SM/09377 | Augmentation | WBSEDCL new service connection. |  |  | BILL/00008/2022-2023 | 8/JMD/PFMS/DEC | 07/12/2022 | 07/12/2022 | WBSEDCL | 0.34 | 0 | 0 | 0
15 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Pakuria PWSS to Accommodate FHTC in Jhargram Block, Jhargram District | SM/09377 | Augmentation | Supply, delivery, installation & commisioning of pumping machinery and other electro mechanical accessories at newly sunk replacement tubwell no.I at Pukuria W/S scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000581/2022-2023 | 3195/JMD | 28/10/2022 | 27/11/2022 | DEBJYOTI BASU | 10.07 | 9.7 | 96.28 | 95
Total | [13 empty] | 254.89 | 135.98 | 53.35