## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Midnapore Division | Augmentation of Ground Water Based Water Supply Scheme for Tamajuri PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. | SM/09378 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000019/2021-2022 | 2161/MD | 17/12/2021 | 17/12/2021 | Resource Division | 1.44 | 0 | 0 | 0
2 | JHARGRAM |  | Midnapore Division | Augmentation of Ground Water Based Water Supply Scheme for Tamajuri PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. | SM/09378 | Augmentation | Extension of Distribution pipe line and FHTC work for Augmentation of Ground based Tamajuri PWSS to Accommodate FHTC in Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. |  |  | ORD/000625/2021-2022 | 178/MD | 01/02/2022 | 12/10/2025 | WATER LINK | 48.15 | 0 | 0 | 50
3 | JHARGRAM |  | Midnapore Division | Augmentation of Ground Water Based Water Supply Scheme for Tamajuri PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. | SM/09378 | Augmentation | Sinking of 200 mm dia. X 165 mm dia. X 200 M depth Rig Bored Tubwell (Replacement) by DTH Method for Augmentation of Source of Tamajuri PWSS under Jhargram Division P.H.E. Dte. |  |  | VCH/001731/2021-2022 | BP-2021-22-471 | 16/03/2022 | 16/03/2022 | BIDYUT KUMAR SANTRA | 3.62 | 0 | 0 | 0
4 | JHARGRAM |  | Midnapore Division | Augmentation of Ground Water Based Water Supply Scheme for Tamajuri PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. | SM/09378 | Augmentation | Purchasing of Materials. |  |  | VCH/001685/2021-2022 | BP-2021-22-445 | 08/03/2022 | 08/03/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 1.05 | 0 | 0 | 0
5 | JHARGRAM |  | Midnapore Division | Augmentation of Ground Water Based Water Supply Scheme for Tamajuri PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. | SM/09378 | Augmentation | Purchasing of materials for the Retrofitting to Accommodate FHTC incl. Augmentation of Source under UM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-1I Block within Jhargram District under Jhargram Division. PHE Dte. |  |  | VCH/000464/2022-2023 |  | 11/08/2022 | 11/08/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 1.05 | 0 | 0 | 0
6 | JHARGRAM |  | Midnapore Division | Augmentation of Ground Water Based Water Supply Scheme for Tamajuri PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. | SM/09378 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Tamajuri PWSS in Binpur-II Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. |  |  | VCH/001373/2021-2022 | BP-2021-22-408 | 23/02/2022 | 23/02/2022 | LEMNISCATE | 2.28 | 0 | 0 | 0
7 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Tamajuri PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. | SM/09378 | Augmentation | Augmentation of Ground Water Based Water Supply Scheme for Tamajuri PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. |  |  | VCH/000014/2022-2023 |  | 11/08/2022 | 11/08/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 1.05 | 0 | 0 | 0
8 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Tamajuri PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. | SM/09378 | Augmentation | Sinking tubewell (125 mm X 115 mm X 200 mtr) by DTH / Combination Method with supply and delivery of UPVC consumables with drilling related works at Tamajuri at Binpur-II block of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Driller-In-Charge | Junior Engineer | ORD/001396/2023-2024 | 3078/JMD | 14/03/2024 | 16/03/2024 | SUJOY RANJAN BHOWMICK | 1.27 | 0.9 | 70.35 | 100
9 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Tamajuri PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. | SM/09378 | Augmentation | Supply of Fuel and lubricants for KLR/DR/DTH-500 for the month of March 2023 during construction of RBT works under JMD,PHE dte |  |  | BILL/00320/2024-2025 | 135/JMD | 24/05/2024 | 24/05/2024 | SURAJ SERVICE STATION | 0.43 | 0 | 0 | 0
10 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Tamajuri PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. | SM/09378 | Augmentation | Construction of boundary wall, switch room & interconnection of T/Well for augmentation of Tamajur water supply scheme with in Binpur- II block under Jhargram Division, P.H.E Dte. 2nd Call (Ref. eNIT 12 of AE/JSD of 2024-25, Sl-03) | Assistant Engineer | Junior Engineer-II | ORD/000348/2024-2025 | 563/JHD | 13/03/2025 | 09/09/2025 | SAMIR PATRA | 8.2 | 0 | 0 | 100
11 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Tamajuri PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. | SM/09378 | Augmentation | New Service Connection Charges for Tamajuri PWSS |  |  | BILL/01806/2025-2026 |  | 16/12/2025 | 16/12/2025 | WBSEDCL | 0.21 | 0 | 0 | 0
12 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Tamajuri PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. | SM/09378 | Augmentation | Restoration for proposed Pipe line laying along Left side of Belpahari - Banspahari Road at Ch 10.75 KM TO Ch 11.35 under Tamajuri PWSS within Binpur-II Block under Jhargram Highway Division in the District of Jhargram. |  |  | BILL/00274/2025-2026 |  | 08/07/2025 | 08/07/2025 | EXECUTIVE ENGINEER, PWD (ROADS) JHARGRAM | 3.35 | 0 | 0 | 0
Total | [13 empty] | 72.09 | 0.9 | 1.24