## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Midnapore Division | Augmentation of Ground Water Based Water supply scheme Belaberya PWSS to Accommodate FHTC in Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09379 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000017/2022-2023 | 2395/MD | 24/11/2022 | 24/11/2022 | Resource Division | 36.34 | 0 | 0 | 0
2 | JHARGRAM |  | Midnapore Division | Augmentation of Ground Water Based Water supply scheme Belaberya PWSS to Accommodate FHTC in Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09379 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Belaberia PWSS in Gopi-IIBlock for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. |  |  | VCH/001718/2021-2022 | BP-2021-22-458 | 11/03/2022 | 11/03/2022 | LEMNISCATE | 3.01 | 0 | 0 | 0
3 | JHARGRAM |  | Midnapore Division | Augmentation of Ground Water Based Water supply scheme Belaberya PWSS to Accommodate FHTC in Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09379 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000045/2021-2022 | 498/MD | 15/03/2022 | 15/03/2022 | Resource Division | 15.18 | 0 | 0 | 0
4 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Belaberya PWSS to Accommodate FHTC in Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09379 | Augmentation | Supply delivery of Different dia CIDF S/V for the work of ¿Augmentation of Ground Water Based Water Supply Scheme for Beliabera to Accommodate FHTC in Block Gopiballavpur - II under Jhargram Sub Division within Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000070/2022-2023 | 57/GPSD | 16/09/2022 | 01/10/2022 | PROVAT KUMAR DE | 2.63 | 0 | 0 | 100
5 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Belaberya PWSS to Accommodate FHTC in Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09379 | Augmentation | Laying of Clear Water Rising Main / Distribution pipe line and FHTC work including Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft ) of capacity 150 cum and staging height 20 mtr. as per approved drawing (No:- PC-I /OHR /10/2012) including supply of all labour & materials for Augmentation of Ground Based Belaberya PWSS in Gopiballavpur -II Block within Jhargram District under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-III | ORD/000174/2022-2023 | 874/MD | 10/05/2022 | 06/11/2022 | SUBRATA DAS | 188.22 | 145.08 | 77.08 | 77
6 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of Ground Water Based Water supply scheme Belaberya PWSS to Accommodate FHTC in Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09379 | Augmentation | Supply, delivery, installation, commissioning electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Beliaberya W/S scheme under Jhargram Mechanical Division, PHE Dte. in the dist. of Jhargram. | Driller-In-Charge | Junior Engineer | ORD/000170/2023-2024 | 2094/JMD | 03/08/2023 | 02/09/2023 | S.S. GHORAI | 13.82 | 10.05 | 72.71 | 90
7 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Belaberya PWSS to Accommodate FHTC in Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09379 | Augmentation | Repairing approach road from headwork side of Beliabera PWSS to main road under Gopiballavpur-II block within Jhargram Sub-Division of Jhargram Division, PHE DTE. (Lenght-220 m) . (2nd Call) [Ref. eNIT 04 OF AE/JSD OF 2024-2025, SL No. 03] | Assistant Engineer | Junior Engineer-III | ORD/000176/2024-2025 | 1070/JSD | 26/11/2024 | 10/12/2024 | SUBRATA DAS | 3.11 | 0 | 0 | 0
8 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Belaberya PWSS to Accommodate FHTC in Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09379 | Augmentation | laying of raising main with interconnection with tube wells ,bypass connection ,road crosssing work & pending distribution main[Node 1 to Node 3,Node 5 to Node 10,Node 3 to Node 8(part)] of augmentation of ground water based water Beliabera PWSS under Gopiballavpur-II Block within Jhargram Division,P.H.E. Dte. | Assistant Engineer | Junior Engineer-III | ORD/000045/2023-2024 | 884/JHD | 08/06/2023 | 08/07/2023 | SUBRATA DAS | 16.48 | 12.25 | 74.32 | 100
9 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Belaberya PWSS to Accommodate FHTC in Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09379 | Augmentation | Sinking of 250 x 150 mm dia. x 150 mtr.rig bored tubewell at Head worksite for Augmentation of Beliabera W/S Scheme in Gopiballavpur-II Block within Jhargram District under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-III | ORD/000350/2023-2024 | 1949/JHD | 22/11/2023 | 07/12/2023 | S.R. ENTERPRISE | 7.01 | 6.5 | 92.86 | 100
10 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of Ground Water Based Water supply scheme Belaberya PWSS to Accommodate FHTC in Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09379 | Augmentation | Supply, delivery, installation of electro-mechanical components for tube well no. II of Beliabera water supply scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/001401/2023-2024 | 113/W/MMSD(D) | 12/03/2024 | 11/04/2024 | S.S. GHORAI | 1.39 | 1.37 | 98.42 | 100
11 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of Ground Water Based Water supply scheme Belaberya PWSS to Accommodate FHTC in Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09379 | Augmentation | Supply, delivery & installation of various electro-mechanical accessories at tube well no.-I of Beliabera w/s scheme in the dist. of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Driller-In-Charge | Junior Engineer | ORD/001372/2023-2024 | 2989/JMD | 13/03/2024 | 12/04/2024 | S.S. GHORAI | 1.39 | 1.36 | 97.79 | 100
Total | [13 empty] | 288.58 | 176.61 | 61.2