## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Midnapore Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Kechenda Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09380 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Kechenda PWSS in Binpur-II Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. |  |  | VCH/001374/2021-2022 | BP-2021-22-402 | 23/02/2022 | 23/02/2022 | RADIANT | 1.36 | 0 | 0 | 0
2 | JHARGRAM |  | Jhargram Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Kechenda Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09380 | Augmentation | Extension of Distribution pipe line and FHTC work for Augmentation of Ground based Kechenda PWSS to Accommodate FHTC in Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. |  | Junior Engineer-II | ORD/000101/2021-2022 | 424/JSD | 30/12/2021 | 29/01/2022 | J.S.S. ENTERPRISE | 4.68 | 0 | 0 | 1
3 | JHARGRAM |  | Jhargram Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Kechenda Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09380 | Augmentation | Balance Work of Augmentation Work of Kechanda Water Supply Scheme within Binpur-II Block under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000291/2023-2024 | 740/JSD | 16/08/2023 | 23/08/2023 | M/S MA LAXMI ENTERPRISE | 0.71 | 0 | 0 | 100
4 | JHARGRAM |  | Jhargram Mechanical Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Kechenda Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09380 | Augmentation | Sinking tubewell (200 mm X 165 mm X 135 mtr) by Rotary / Combination Method with supply and delivery of UPVC consumables with drilling related works near Kechenda PWSS at Binpur-II block of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Driller-In-Charge | Junior Engineer | ORD/001397/2023-2024 | 3079/JMD | 14/03/2024 | 19/03/2024 | SUJOY RANJAN BHOWMICK | 3.32 | 0 | 0 | 100
5 | JHARGRAM |  | Jhargram Mechanical Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Kechenda Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09380 | Augmentation | New Service Connection Charges for Kechanda T/W - III PWSS |  |  | BILL/01032/2024-2025 | 369/JMD | 24/09/2024 | 24/09/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
6 | JHARGRAM |  | Jhargram Mechanical Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Kechenda Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09380 | Augmentation | Supply of diesel and lubricants for KLR/DR/DTH-500 unit during PWSS works under JJM for scheme (SM/09380) KECHENDA PWSS |  |  | BILL/00898/2024-2025 | 329/JMD | 29/08/2024 | 29/08/2024 | SURAJ SERVICE STATION | 0.93 | 0 | 0 | 0
7 | JHARGRAM |  | Jhargram Mechanical Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Kechenda Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09380 | Augmentation | Supply, delivery, installation, commissioning of submersible pumping machinery and other Electro Mechanical accessories at newly sunk tube well at Kechenda of Binpur-II block of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Driller-In-Charge | Junior Engineer | ORD/000802/2024-2025 | 7305/JMD | 13/11/2024 | 13/12/2024 | M/S. NABIN GOPAL SENGUPTA | 2.12 | 0 | 0 | 100
8 | JHARGRAM |  | Jhargram Mechanical Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Kechenda Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09380 | Augmentation | Dismantling the existing damaged voltage stabilizer & supply, delivery & installation of newly supplied single phase 10 KVA oil cooled type voltage stabilizer with other allied works at tube well no.-I of Kechenda water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Driller-In-Charge | Junior Engineer | ORD/001403/2023-2024 | 3096/JMD | 15/03/2024 | 14/04/2024 | M/S. NABIN GOPAL SENGUPTA | 1.79 | 0 | 0 | 100
Total | [13 empty] | 15.12 | 0 | 0