## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Midnapore Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Banspahari Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09381 | Augmentation | Sinking of 200 mm dia. X 165 mm dia. X 200 M depth Rig Bored Tubwell (Replacement) by DTH Method for Augmentation of Source of Banspahari PWSS under Jhargram Division P.H.E. Dte. |  |  | VCH/001732/2021-2022 | BP-2021-22-472 | 16/03/2022 | 16/03/2022 | SUNIL DULE | 3.36 | 0 | 0 | 0
2 | JHARGRAM |  | Midnapore Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Banspahari Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09381 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Banspahari PWSS in Binpur-II Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. |  |  | VCH/001375/2021-2022 | BP-2021-22-401 | 23/02/2022 | 23/02/2022 | RADIANT | 1.8 | 0 | 0 | 0
3 | JHARGRAM |  | Jhargram Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Banspahari Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09381 | Augmentation | Extension of Distribution pipe line and FHTC work for Augmentation of Ground based Banspahari PWSS to Accommodate FHTC in Binpur -II Block within Jhargram District under Jhargram Division, PHE Dte. |  |  | VCH/000026/2022-2023 |  | 23/08/2022 | 23/08/2022 | SUNIL DULE | 14.12 | 0 | 0 | 0
4 | JHARGRAM |  | Jhargram Mechanical Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Banspahari Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09381 | Augmentation | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Replacement Tube Well no. II of Banspahari piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000152/2023-2024 | 1940/JMD | 28/07/2023 | 27/08/2023 | ECO ENTERPRISE | 8.35 | 0 | 0 | 98
5 | JHARGRAM |  | Jhargram Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Banspahari Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09381 | Augmentation | Health Assessment (Conducting Non Destructive Test) of Existing RCC O.H.R (Zone-I) of capacity 50000 gallon with staging height of 20 mtr. of Ramgarh Piped Water Supply Scheme at Binpur-I Block under Jhargram Sub Division within Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000021/2022-2023 | 426/JSD | 05/08/2022 | 20/08/2022 | SIRCON ENGINEERING SERVICES | 4.4 | 0 | 0 | 1
6 | JHARGRAM |  | Jhargram Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Banspahari Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09381 | Augmentation | Sinking of 200 mm dia. X 165 mm dia. X 200 M depth Rig Bored Tube-well (Replacement) 2 Nd T/W site by D.T.H. Method, Construction of Boundary Wall ( Length 34.00 mtr. ) 2Nd T/W & Interconnection of 2 Nos. Newly Sunk T/W at Banspahari Water Supply Scheme within Jhargram Sub-Division Under Jhargram Division P.H.E.Dte. |  | Junior Engineer-II | ORD/000004/2023-2024 | 569/JHD | 25/04/2023 | 09/06/2023 | SUNIL DULE | 8.03 | 0 | 0 | 100
7 | JHARGRAM |  | Midnapore Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Banspahari Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09381 | Augmentation | Extension of Distribution pipe line and FHTC work for Augmentation of Ground based Banspahari PWSS to Accommodate FHTC in Binpur -II Block within Jhargram District under Jhargram Division, PHE Dte. |  |  | ORD/000019/2022-2023 | 616/MD | 04/04/2022 | 25/04/2022 | SUNIL DULE | 14.28 | 0 | 0 | 1
8 | JHARGRAM |  | Jhargram Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Banspahari Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09381 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Belpahari PWSS (Zone-III) in Binpur-II Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. |  | Junior Engineer-II | ORD/000125/2021-2022 | 150/JSD | 12/08/2021 | 26/08/2021 | LEMNISCATE | 4.31 | 0 | 0 | 100
9 | JHARGRAM |  | Jhargram Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Banspahari Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09381 | Augmentation | Extension of Distribution pipe line and FHTC work for Augmentation of Ground based Banspahari PWSS to Accommodate FHTC in Binpur -II Block within Jhargram District under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000082/2022-2023 | 616/MD | 04/04/2022 | 25/04/2022 | SUNIL DULE | 14.28 | 0 | 0 | 100
Total | [13 empty] | 72.93 | 0 | 0