## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Midnapore Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09383 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Rantua PWSS in Gopiballavpur-II Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. |  |  | ORD/000222/2021-2022 | 113/JSD | 22/07/2021 | 05/08/2021 | ROY CHOWDHURY ASSOCIATES | 4.49 | 3.94 | 87.71 | 1
2 | JHARGRAM |  | Midnapore Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09383 | Augmentation | Purchasing of Materials. |  |  | VCH/001686/2021-2022 | BP-2021-22-445 | 08/03/2022 |  | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 5.68 | 0 | 0 | 0
3 | JHARGRAM |  | Jhargram Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09383 | Augmentation | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. |  |  | VCH/000013/2022-2023 | null | 11/08/2022 |  | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 5.68 | 0 | 0 | 0
4 | JHARGRAM |  | Jhargram Mechanical Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09383 | Augmentation | Supply, delivery and Installation of new pumping machinery and other electro mechanical accessories at Rantua T/W no -II water supply scheme at Gopiballavpur-II block of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000597/2022-2023 | 1661/JMD | 01/08/2022 | 16/08/2022 | BUSR ENGINEERING | 4.54 | 4.39 | 96.52 | 0
5 | JHARGRAM |  | Jhargram Mechanical Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09383 | Augmentation | Supply, delivery & installation of voltage stabilizer, chlorine machine and other allied works at Rantua tubewell no. 2 water supply scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000618/2022-2023 | 3636/JMD | 07/12/2022 | 06/01/2023 | BUSR ENGINEERING | 5.67 | 5.56 | 98.13 | 0
6 | JHARGRAM |  | Midnapore Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09383 | Augmentation | Money transfer to EE/JSD. |  |  | BILL/00708/2022-2023 | BP-2022-23-691 | 10/03/2023 |  | EXECUTIVE ENGINEER, JHARGRAM CIVIL DIVISION, PHE DTE. | 3.63 | 0 | 0 | 0
7 | JHARGRAM |  | Midnapore Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09383 | Augmentation | Money transfer to EE/JSD. |  |  | BILL/00708/2022-2023 | BP-2022-23-691 | 10/03/2023 |  | EXECUTIVE ENGINEER, JHARGRAM CIVIL DIVISION, PHE DTE. | 3.63 | 0 | 0 | 0
8 | JHARGRAM |  | Jhargram Mechanical Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09383 | Augmentation | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories at T/W no. III & IV as part of augmentation of Rantua W/S scheme under Jhargram Mechanical Division, PHE Dte. in the dist. of Jhargram. | Assistant Engineer | JE (M) | ORD/000169/2023-2024 | 2093/JMD | 03/08/2023 | 30/01/2024 | RSA ENTERPRISE | 19.73 | 0 | 0 | 0
9 | JHARGRAM |  | Midnapore Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09383 | Augmentation | Laying of Clear Water Rising Main / Distribution pipe line and FHTC work including Sinking of 250 X 150mm dia. X 120 Mtr. Depth Rig bored Tube well for Augmentation of Ground Based Rantua PWSS to Accommodate FHTC in Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. |  |  | ORD/000592/2021-2022 | 137/MD | 27/01/2022 | 28/03/2022 | SUNIL DULE | 82.58 | 82.52 | 99.93 | 1
10 | JHARGRAM |  | Jhargram Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09383 | Augmentation | Replacement of pipeline from Bajnaguri Chawk to Bajanaguri Primary School and installation of different dia sluice valves at different position of distribution pipeline network for Rantua PWSS in Gopiballavpur-II block Jhargrm Division, PHE Dte | Assistant Engineer | Junior Engineer-III | ORD/000199/2022-2023 | 215/JHD | 15/02/2023 | 01/04/2023 | SUNIL DULE | 10.64 | 4.69 | 44.05 | 80
11 | JHARGRAM |  | Midnapore Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09383 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000016/2021-2022 | 2164/MD | 17/12/2021 |  | Resource Division | 8.06 | 0 | 0 | 0
12 | JHARGRAM |  | Jhargram Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09383 | Augmentation | Laying of Clear Water Rising Main / Distribution pipe line and FHTC work including Sinking of 250 X 150mm dia. X 120 Mtr. Depth Rig bored Tube well for Augmentation of Ground Based Rantua PWSS to Accommodate FHTC in Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-III | ORD/000128/2021-2022 | 137/MD | 27/01/2022 | 28/03/2022 | SUNIL DULE | 14.43 | 13.54 | 93.84 | 100
Total | [13 empty] | 168.75 | 114.63 | 67.93