## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in Nayagram Block (Part) PWSS. | SM/09384 | Retrofitting | Retrofitting to Accommodate FHTC for Sub-Surface Water Based Piped Water Supply Scheme in Nayagram Block (Part) under JJM under Jhargram Division P.H.E. Dte. |  |  | VCH/000002/2022-2023 |  | 19/07/2022 | 19/07/2022 | GOBINDA MAITY | 73.78 | 0 | 0 | 0
2 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in Nayagram Block (Part) PWSS. | SM/09384 | Retrofitting | Retrofitting to Accommodate FHTC for Sub-Surface Water Based Piped Water Supply Scheme in Nayagram Block (Part) under JJM under Jhargram Division P.H.E. Dte. |  |  | VCH/000020/2022-2023 |  | 12/08/2022 | 12/08/2022 | GOBINDA MAITY | 60 | 0 | 0 | 0
3 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in Nayagram Block (Part) PWSS. | SM/09384 | Retrofitting | Hiring of 1 (one) no, Motor Cab (standard) Commercial with Catalytic Converter attachment with Bharat Stage as per prevalent applicable standard compliant new not older than 30 (thirty) months from the date of 1st registration on daily hire rate basis for 04 (Four) months only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Assistant Engineer, Jhargram Sub-Division PHE Dte.(from 01.01.2023 to 30.04.2023) | Assistant Engineer |  | ORD/000241/2022-2023 | 761/JSD | 30/12/2022 | 30/04/2023 | BIDYUT KUMAR SANTRA | 0.67 | 1.34 | 198.74 | 99
4 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in Nayagram Block (Part) PWSS. | SM/09384 | Retrofitting | Lay Left Out Different Dia Pipe with Balace F.H.T.C (700 Nos), Of Nayagram (part) Sub-Surface based pipe water supply scheme under Nayagram Dev. Block under Gopiballavpur Sub-Division of Jhargram Division PHE Dte. the District of Jhargram. | Assistant Engineer | Junior Engineer-II | ORD/000340/2023-2024 | 1871/JHD | 01/11/2023 | 16/12/2023 | GOBINDA MAITY | 101.65 | 25.68 | 25.26 | 36
5 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in Nayagram Block (Part) PWSS. | SM/09384 | Retrofitting | Functional Household Tap Connection data uploading charges of different pwss under Jhargram District in JJM_IMIS portal under Jal Jeevan Mission for January-2023 and February-2023 under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000253/2022-2023 | 29A/JRWS | 28/12/2022 | 26/02/2023 | PROVAT KUMAR DE | 0.93 | 0 | 0 | 100
6 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in Nayagram Block (Part) PWSS. | SM/09384 | Retrofitting | Erection of scaffolding with necessary cross bracing and fixtures and removal after condition assesment for the OHR of Zone-IX of Nayagram (Part) W/S Scheme within Nayagram Dev. Block of Jhargram Division P.H.E Dte. | Assistant Engineer | Junior Engineer-II | ORD/000085/2023-2024 | 663/JSD | 21/07/2023 | 11/08/2023 | SUNIL DULE | 2.29 | 2.29 | 99.79 | 100
7 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Nayagram Block (Part) PWSS. | SM/09384 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000009/2022-2023 | 355 | 29/09/2022 | 29/09/2022 | Resource Division | 0.22 | 0 | 0 | 0
8 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in Nayagram Block (Part) PWSS. | SM/09384 | Retrofitting | Construction of Neutralization Pit at Khanamuri, under Nayagram block (part) sub-surface base water supply scheme under Jhargram Division P.H.E.Dte. (Part-A) & Construction of Neutralization Pit at Barasukjora under Jhargram Division P.H.E.Dte. (Part-B) |  | Junior Engineer-II | ORD/000232/2022-2023 | 541/JSD | 23/09/2022 | 23/10/2022 | MAHAVIR SAMPARK PVT. LTD. | 0.29 | 0 | 0 | 100
9 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in Nayagram Block (Part) PWSS. | SM/09384 | Retrofitting | Continuation Order for the Work of "Retrofitting to Accommodate FHTC for Sub-Surface Water Based Piped Water Supply Scheme in Nayagram Block (Part) under JJM under Jhargram Division P.H.E. Dte. (For Zone VIII-B)" |  | Junior Engineer-II | ORD/000078/2022-2023 | 337/JHD | 26/09/2022 | 25/11/2022 | GOBINDA MAITY | 95.26 | 91.82 | 96.38 | 1
10 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in Nayagram Block (Part) PWSS. | SM/09384 | Retrofitting | Supply delivery of DI Specials, for the work of Nayagram Block (Part) Sub Surface Based Water Supply Scheme under Gopiballavpur Sub Division of Jhargram Division, PHE Dte. | Assistant Engineer | The Junior Engineer-IV Jhargram Sub-Division | ORD/000389/2023-2024 | 464/GPSD | 12/12/2023 | 27/12/2023 | S.B.TRADERS | 3.44 | 3.44 | 100 | 100
11 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in Nayagram Block (Part) PWSS. | SM/09384 | Retrofitting | Retrofitting to Accommodate FHTC for Sub-Surface Water Based Piped Water Supply Scheme in Nayagram Block (Part) under JJM under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000042/2022-2023 | 805/MD | 28/04/2022 | 28/01/2026 | GOBINDA MAITY | 659.49 | 350.09 | 53.08 | 100
12 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in Nayagram Block (Part) PWSS. | SM/09384 | Retrofitting | Laying Of Balance Distribution System of HDPE (Pe-100- Pn-6) And D.I. (K-7) Pipe For Zone - Viii-B & Xiii-A Of Sub- Surface Water Supply Scheme For Nayagram Block (Part) Under Jhargram Sub-Division P.H.E. Dte. Of Jhargram Division P.H.E.Dte. | Assistant Engineer | Junior Engineer-II,Junior Engineer-III | ORD/000004/2024-2025 | 801/JHD | 06/06/2024 | 06/07/2024 | SUBHRANIL DAS | 25.56 | 6.68 | 26.14 | 100
Total | [13 empty] | 1023.59 | 481.32 | 47.02