## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in Kuldiha PWSS under Nayagram Block. | SM/09386 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Kuldiha Water Supply Scheme Block -Nayagram in the District of Jhargram. | Assistant Engineer | Junior Engineer-III | ORD/000197/2022-2023 | 225/JHD | 16/02/2023 | 02/04/2023 | GOBINDA MAITY | 20.73 | 13.51 | 65.19 | 1
2 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in Kuldiha PWSS under Nayagram Block. | SM/09386 | Retrofitting | New service connection charges |  |  | BILL/00155/2022-2023 | BP-2022-23-156 | 01/03/2023 | 01/03/2023 | WBSEDCL | 1.12 | 0 | 0 | 0
3 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in Kuldiha PWSS under Nayagram Block. | SM/09386 | Retrofitting | Supply CI & DI specials for laying rising,interconnection between tube wells and risingmain with allied works of Kuldiha water supply scheme within Nayagram Block under Gopiballavpur sub Division of Jhargram Division,PHE Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division,Junior Engineer, Gopiballavpur Sub Division | ORD/000029/2024-2025 | 507/GPSD | 30/07/2024 | 09/08/2024 | ENVOTECH INFRA SOLUTION | 2.67 | 0 | 0 | 95
Total | [13 empty] | 24.51 | 13.51 | 55.13