## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Jhargram Division | Agumentation of Ground Water Based Birkarnar Water Supply scheme in Binpur-I Block within Jhargram District i.c.w. providing FHTC under Jhargram Division, PHE Dte. | SM/09434 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Birkarnar PWSS in Binpur-I Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. |  | Junior Engineer-III | ORD/000091/2021-2022 | 97/JSD | 08/07/2021 | 22/07/2021 | RADIANT | 1.8 | 1.79 | 99.3 | 1
2 | JHARGRAM |  | Jhargram Division | Agumentation of Ground Water Based Birkarnar Water Supply scheme in Binpur-I Block within Jhargram District i.c.w. providing FHTC under Jhargram Division, PHE Dte. | SM/09434 | Augmentation | Retrofitting with relaying of distribution pipeline to accommodate FHTC under JJM of Rejuvenation of Birkarnar water supply scheme at Block - Binpur-I in the District of Jhargram |  | Junior Engineer-III | ORD/000129/2022-2023 | 202/JSD | 04/04/2022 | 25/04/2022 | DEBASIS DATTA | 4.69 | 4.55 | 96.98 | 1
3 | JHARGRAM |  | Jhargram Division | Agumentation of Ground Water Based Birkarnar Water Supply scheme in Binpur-I Block within Jhargram District i.c.w. providing FHTC under Jhargram Division, PHE Dte. | SM/09434 | Augmentation | Retrofitting with relaying of distribution pipeline to accommodate FHTC under JJM of Rejuvenation of Birkarnar water supply scheme at Block - Binpur-I in the District of Jhargram |  |  | VCH/000019/2022-2023 |  | 12/08/2022 | 12/08/2022 | DEBASIS DATTA | 4.5 | 0 | 0 | 0
4 | JHARGRAM |  | Jhargram Division | Agumentation of Ground Water Based Birkarnar Water Supply scheme in Binpur-I Block within Jhargram District i.c.w. providing FHTC under Jhargram Division, PHE Dte. | SM/09434 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Birkarnar PWSS in Binpur-I Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. |  |  | VCH/000004/2022-2023 |  | 02/08/2022 | 02/08/2022 | RADIANT | 1.79 | 0 | 0 | 0
5 | JHARGRAM |  | Jhargram Division | Agumentation of Ground Water Based Birkarnar Water Supply scheme in Binpur-I Block within Jhargram District i.c.w. providing FHTC under Jhargram Division, PHE Dte. | SM/09434 | Augmentation | Retrofitting with relaying of distribution pipeline to accommodate FHTC under JJM of rejuvenation of Birkarnar Water Supply Scheme at Block Binpur-I in the district of Jhargram. (Adintariam Bill) |  |  | VCH/000031/2022-2023 |  | 01/09/2022 | 01/09/2022 | DEBASIS DATTA | 0.05 | 0 | 0 | 0
6 | JHARGRAM |  | Jhargram Division | Agumentation of Ground Water Based Birkarnar Water Supply scheme in Binpur-I Block within Jhargram District i.c.w. providing FHTC under Jhargram Division, PHE Dte. | SM/09434 | Augmentation | Restoration work for laying pipeline along the Lalgarh-Ramgarh Road (near 3rd kmp) due to Augmentation of Birkarner Piped W/S Scheme under Jhargram Divison |  |  | BILL/00224/2023-2024 | BP-2023-24-137 | 03/08/2023 | 03/08/2023 | EXECUTIVE ENGINEER, PWD (ROADS) JHARGRAM | 1.83 | 0 | 0 | 0
Total | [13 empty] | 14.67 | 6.34 | 43.23