## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Midnapore Division | Augmentation of ground water based water supply scheme for Khasjungle ICW FHTC work. | SM/09881 | Augmentation | Sinking of 250mm X 150mm dia. & depth 135 Mtr. Rig bore Tube well (Replacement) for Augmentation of Khasjungal W/S Scheme within Binpur-I block under Jhargram Division, PHE Dte. |  |  | ORD/000016/2022-2023 | 613/MD | 04/04/2022 | 19/04/2022 | TAPAS KUMAR GIRI | 6.13 | 0 | 0 | 1
2 | JHARGRAM |  | Midnapore Division | Augmentation of ground water based water supply scheme for Khasjungle ICW FHTC work. | SM/09881 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Khasjungle PWSS in Binpur-I Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. |  |  | VCH/001383/2021-2022 | BP-2021-22-409 | 23/02/2022 | 23/02/2022 | RADIANT | 1.35 | 0 | 0 | 0
3 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of ground water based water supply scheme for Khasjungle ICW FHTC work. | SM/09881 | Augmentation | Withdrawing the damaged sub-mersible pumping machinery and installation of same capacity departmentally supplied pump motor set with other allied works at Khasjangle water supply scheme, tube well no.-1 at Binpur-I block in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,DIC(D)_MMSD(D) | Junior Engineer | ORD/000915/2022-2023 | 1572/JMD | 26/07/2022 | 31/07/2022 | M/S. EMMESS | 4.18 | 0 | 0 | 100
4 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of ground water based water supply scheme for Khasjungle ICW FHTC work. | SM/09881 | Augmentation | Supply, delivery and laying of additional Cable, pipe & erection of fencing arrangement with other allied accessories at T/W no.-II of Khasjungle W/S Scheme at Binpur-I Block in the district of Jhargram under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000055/2025-2026 | 1240/JMD | 02/06/2025 | 31/08/2025 | SOUMEN ELECTRIC | 3.39 | 0 | 0 | 100
Total | [13 empty] | 15.04 | 0 | 0