## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Midnapore Division | Augmentation of ground water based water supply scheme for Khasjungle ICW FHTC work. | SM/09881 | Augmentation | Sinking of 250mm X 150mm dia. & depth 135 Mtr. Rig bore Tube well (Replacement) for Augmentation of Khasjungal W/S Scheme within Binpur-I block under Jhargram Division, PHE Dte. |  |  | ORD/000016/2022-2023 | 613/MD | 04/04/2022 | 19/04/2022 | TAPAS KUMAR GIRI | 6.13 | 5.21 | 85.02 | 1
2 | JHARGRAM |  | Midnapore Division | Augmentation of ground water based water supply scheme for Khasjungle ICW FHTC work. | SM/09881 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Khasjungle PWSS in Binpur-I Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. |  |  | VCH/001383/2021-2022 | BP-2021-22-409 | 23/02/2022 | 23/02/2022 | RADIANT | 1.35 | 0 | 0 | 0
3 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of ground water based water supply scheme for Khasjungle ICW FHTC work. | SM/09881 | Augmentation | Withdrawing the damaged sub-mersible pumping machinery and installation of same capacity departmentally supplied pump motor set with other allied works at Khasjangle water supply scheme, tube well no.-1 at Binpur-I block in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,DIC(D)_MMSD(D) | Junior Engineer | ORD/000915/2022-2023 | 1572/JMD | 26/07/2022 | 31/07/2022 | M/S. EMMESS | 4.18 | 4.18 | 99.9 | 100
4 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of ground water based water supply scheme for Khasjungle ICW FHTC work. | SM/09881 | Augmentation | Dismantling the existing damaged voltage stabilizer and supply, delivery & installation of newly supplied single phase 10 KVA oil cooled type voltage stabilizer with other allied works at tube well no.-II of Khasjungle water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000740/2024-2025 | 6942/JMD | 13/09/2024 | 01/01/2025 | PADMA ENGINEERING CO. | 2.03 | 0 | 0 | 100
Total | [13 empty] | 13.68 | 9.39 | 68.61