## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of ground water based Chichira water supply scheme ICW providing FHTC. | SM/09882 | Augmentation | Supply delivery & installation of pumping machinery and other electro mechanical accessories for the newly sunk replacement tube well no -II at Chichira w/s scheme to accommodate FHTC at Jamboni block of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000520/2022-2023 | 3068/JMD | 28/09/2022 | 28/10/2022 | SHOVAN KUMAR DAS | 9.89 | 0 | 0 | 0
2 | JHARGRAM |  | Midnapore Division | Augmentation of ground water based Chichira water supply scheme ICW providing FHTC. | SM/09882 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Chichira PWSS in Jamboni Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. |  |  | VCH/001385/2021-2022 | BP-2021-22-394 | 22/02/2022 | 22/02/2022 | RADIANT | 1.38 | 0 | 0 | 0
3 | JHARGRAM |  | Jhargram Division | Augmentation of ground water based Chichira water supply scheme ICW providing FHTC. | SM/09882 | Augmentation | Sinking of 250mm X 150mm dia. & depth 150 Mtr. Rig bore Tube well for Augmentation of Chichira W/S Scheme under Jhargram Division, PHE Dte. |  |  | VCH/000024/2022-2023 |  | 16/08/2022 | 16/08/2022 | NIRPENDRA NATH SINGHA | 4.78 | 0 | 0 | 0
4 | JHARGRAM |  | Midnapore Division | Augmentation of ground water based Chichira water supply scheme ICW providing FHTC. | SM/09882 | Augmentation | Sinking of 250mm X 150mm dia. & depth 150 Mtr. Rig bore Tube well for Augmentation of Chichira W/S Scheme under Jhargram Division, PHE Dte. |  |  | ORD/000018/2022-2023 | 615/MD | 04/04/2022 | 19/04/2022 | NRIPENDRA NATH SINGHA | 6.58 | 0 | 0 | 0
5 | JHARGRAM |  | Jhargram Division | Augmentation of ground water based Chichira water supply scheme ICW providing FHTC. | SM/09882 | Augmentation | Sinking of 250mm X 150mm dia. & depth 150 Mtr. Rig bore Tube well for Augmentation of Chichira W/S Scheme under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000146/2022-2023 | 615/MD | 04/04/2022 | 19/04/2022 | NIPENDRANATH SINGHA | 6.58 | 0 | 0 | 1
6 | JHARGRAM |  | Jhargram Division | Augmentation of ground water based Chichira water supply scheme ICW providing FHTC. | SM/09882 | Augmentation | DISMANTILING OF CONCRETE ROAD & RESTORATION AT CHICHIRA VILLAGE UNDER CHICHIRA W/S SCHEME WITHIN JAMBONI BLOCK UNDER JHARGRAM DIVISION, P.H.E. DTE. (Phase-I). | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000108/2024-2025 | 197/JRWS | 12/07/2024 | 11/08/2024 | SUNIL DULE | 0.97 | 0 | 0 | 0
7 | JHARGRAM |  | Jhargram Division | Augmentation of ground water based Chichira water supply scheme ICW providing FHTC. | SM/09882 | Augmentation | DISMANTILING OF CONCRETE ROAD & RESTORATION AT CHICHIRA VILLAGE UNDER CHICHIRA W/S SCHEME WITHIN JAMBONI BLOCK UNDER JHARGRAM DIVISION, P.H.E. DTE. (Phase-II). | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000109/2024-2025 | 198/JRWS | 12/07/2024 | 11/08/2024 | SUNIL DULE | 0.97 | 0 | 0 | 0
8 | JHARGRAM |  | Jhargram Division | Augmentation of ground water based Chichira water supply scheme ICW providing FHTC. | SM/09882 | Augmentation | LEFT OUT HABITATION ACCOMODATE FUNCTIONAL HOUSE TAP CONNECTION (F.H.T.C.) AT CHICHIRA MOUZA UNDER CHICHIRA WATER SUPPLY SCHEME WITH IN JAMBONI BLOCK UNDER JHARGRAM DIVISION, P.H.E. DTE. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000008/2024-2025 | 261/JRWS | 07/08/2024 | 06/10/2024 | SAUBHIK KUMAR NAG | 3.8 | 0 | 0 | 0
Total | [13 empty] | 34.96 | 0 | 0