## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Mahuli T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000529/2022-2023 | 3073/JMD | 28/09/2022 | 26/01/2023 | SUBHASIS ROY | 5.7 | 5.12 | 89.87 | 0
2 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply delivery of CIDF S/V for the work of Stand Alone Water Supply Scheme (269 nos.) for Jamboni Block area under Jhargram Sub Division within Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000031/2022-2023 | 365/JSD | 21/07/2022 | 05/08/2022 | SUNIL DULE | 4.8 | 4.8 | 100 | 1
3 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking and providing manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Bag Doba mouza , tube well no. 2 and others of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer |  | ORD/000096/2021-2022 | 655/JMD | 31/12/2021 | 07/01/2022 | P.K. ENGINEERING | 8.69 | 8.69 | 100 | 1
4 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking and providing manpower for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Amlasol mouza, tube well no.2 and others of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | Junior Engineer-II | ORD/000097/2021-2022 | 83/JMD | 31/01/2022 | 07/02/2022 | DEBJYOTI BASU | 3.77 | 3.77 | 100 | 1
5 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking and providing manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Chhota Jharia mouza , tube well no. 3 and others of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer |  | ORD/000099/2021-2022 | 669/JMD | 31/12/2021 | 07/01/2022 | SUBHASIS ROY | 5.53 | 5.53 | 100 | 1
6 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking and providing manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Bam Diha mouza and others of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer |  | ORD/000098/2021-2022 | 709/JMD | 31/12/2021 | 07/01/2022 | M/S. BIKASH DE | 4.21 | 4.21 | 100 | 1
7 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. (Furniture and computer tools supply) |  |  | VCH/000045/2022-2023 |  | 23/09/2022 | 23/09/2022 | IONET | 0.44 | 0 | 0 | 0
8 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Midnapore Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone units for Drought like situation Prone 08 Blocks of Jhargram District (Model standalone Grid power operated W/S System for Habitations/mouzas with 400 & more population) under mid-trem plan of master plan. |  |  | VCH/000373/2022-2023 | BP-2022-23-57 | 13/05/2022 | 13/05/2022 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 73.7 | 0 | 0 | 0
9 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | WBSEDCL Payment for New service connection. |  |  | VCH/000856/2022-2023 | 1/JMD/PFMS/OCT | 18/10/2022 | 18/10/2022 | WBSEDCL | 4.58 | 0 | 0 | 0
10 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Midnapore Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Requisition of fund for ASHA Incentive in the activity of onsite drinking water testing at the village level by trained ASHAs in Jhargram District. |  |  | VCH/000717/2022-2023 | BP-2022-23-157 | 12/07/2022 | 12/07/2022 | DISTRICT HEALTH & FAMILY WELFARE SAMITI JHARGRAM HEALTH DISTRICT | 3.65 | 0 | 0 | 0
11 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Payment for new service connection of WBSEDCL. |  |  | VCH/000726/2022-2023 | 23/JMD/PFMS/SEP | 09/09/2022 | 09/09/2022 | WBSEDCL | 6.27 | 0 | 0 | 0
12 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | WBSEDCL payment for new Service Connection. |  |  | VCH/000878/2022-2023 | 2/JMD/PFMS/OCT | 25/10/2022 | 25/10/2022 | WBSEDCL | 6.46 | 0 | 0 | 0
13 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Midnapore Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | For WBSEDCL quotations i.c.t. Construction of RBTW under standalone pipe water supply scheme. |  |  | VCH/000468/2022-2023 | BP-2022-23-230 | 22/08/2022 | 22/08/2022 | EXECUTIVE ENGINEER, JHARGRAM MECHANICAL DIVISION, PHE DTE. | 4.18 | 0 | 0 | 0
14 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Midnapore Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone units for drought line situation prone 8 blocks of Jhargram District. |  |  | VCH/000617/2022-2023 | BP-2022-23-121 | 18/06/2022 | 18/06/2022 | EXECUTIVE ENGINEER, JHARGRAM MECHANICAL DIVISION, PHE DTE. | 75.97 | 0 | 0 | 0
15 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Payment for new service connection of WBSEDCL. |  |  | VCH/000846/2022-2023 | 22/JMD/PFMS/SEP | 29/09/2022 | 29/09/2022 | WBSEDCL | 1.87 | 0 | 0 | 0
16 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Midnapore Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Nayagram_1_6 under Jhargram Division in the District of Jhargram. |  |  | ORD/000651/2021-2022 | 192/MD | 01/02/2022 | 31/07/2022 | M/S. B. N. ENTERPRISES | 107.25 | 0 | 0 | 0
17 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Jamui stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000150/2022-2023 | 1455/JMD | 19/07/2022 | 16/11/2022 | SUBHAM ENTERPRISE | 6.86 | 5.04 | 73.42 | 0
18 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Garkhelar stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000154/2022-2023 | 1459/JMD | 19/07/2022 | 16/11/2022 | M/S D.G.B. ENTERPRISE | 6.87 | 5.03 | 73.19 | 0
19 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Kank Para stand alone piped water supply scheme, tube well no.-II of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000142/2022-2023 | 1416/JMD | 14/07/2022 | 11/11/2022 | SHOVAN KUMAR DAS | 6.86 | 4.73 | 68.93 | 0
20 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Baghmari stand alone piped water supply scheme, tube well no.-II of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000172/2022-2023 | 1472/JMD | 19/07/2022 | 16/11/2022 | MAA BHABOTARINE ENTERPRISE | 6.86 | 5.03 | 73.26 | 0
21 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Garkhelar stand alone piped water supply scheme, tube well no.-III of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000161/2022-2023 | 1461/JMD | 19/07/2022 | 16/11/2022 | BALAJI CONSTRUCTION | 6.86 | 0 | 0 | 0
22 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Lakshanpur stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000140/2022-2023 | 1414/JMD | 14/07/2022 | 11/11/2022 | M/S. EMMESS | 6.83 | 4.83 | 70.61 | 100
23 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Garkhelar stand alone piped water supply scheme, tube well no.-II of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000160/2022-2023 | 1460/JMD | 19/07/2022 | 16/11/2022 | JAL PRAVAHIKA PVT. LTD. | 6.87 | 5.03 | 73.2 | 0
24 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Kank Para stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000141/2022-2023 | 1415/JMD | 14/07/2022 | 11/11/2022 | KAMAKHYA ENTERPRISE | 6.8 | 4.69 | 68.91 | 0
25 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Dubrajpur stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000145/2022-2023 | 1419/JMD | 14/07/2022 | 11/11/2022 | SUJOY RANJAN BHOWMICK | 6.86 | 6.31 | 91.97 | 100
26 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Jhaurishol stand alone piped water supply scheme, tube well no.-II of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000271/2022-2023 | 1738/JMD | 17/08/2022 | 15/12/2022 | M/S. P.P. ELECTRICALS | 6.85 | 6.27 | 91.52 | 0
27 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Dhobani Sol stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000266/2022-2023 | 1735/JMD | 17/08/2022 | 15/12/2022 | DAS CONSTRUCTION | 6.85 | 6.24 | 91.1 | 0
28 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Chhota Tal Pada stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000268/2022-2023 | 1734/JMD | 17/08/2022 | 15/12/2022 | GOENKA ENTERPRISE | 6.86 | 5.02 | 73.2 | 0
29 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dhirighutu T/W no. I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000557/2022-2023 | 3162/JMD | 19/10/2022 | 16/02/2023 | JAGANNATH ENTERPRISE | 5.72 | 5.08 | 88.81 | 0
30 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dubrajpur T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000579/2022-2023 | 3193/JMD | 28/10/2022 | 25/02/2023 | BOSE AND CHATTERJEE INDUSTRIES | 5.68 | 5.11 | 90.01 | 0
31 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Aguibil T/W no. I & II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000516/2022-2023 | 3064/JMD | 28/09/2022 | 26/01/2023 | MENAKA ENTERPRISE | 6.79 | 0 | 0 | 0
32 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Barighati T/W no. I & II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000671/2022-2023 | 4210/JMD | 28/12/2022 | 27/04/2023 | MAA BHABOTARINE ENTERPRISE | 6.84 | 0 | 0 | 0
33 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Lekraanchra T/W no. -I & II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000672/2022-2023 | 4211/JMD | 28/12/2022 | 27/04/2023 | MANAS KUMAR SAHA | 6.84 | 0 | 0 | 0
34 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bara Rajgram Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000658/2022-2023 | 4197/JMD | 28/12/2022 | 27/04/2023 | DIPALI CONSTRUCTION | 5.78 | 5.16 | 89.39 | 0
35 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Amla Kora T/W no. -II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000539/2022-2023 | 3082/JMD | 28/09/2022 | 26/01/2023 | MAA BHABOTARINE ENTERPRISE | 5.71 | 4.13 | 72.4 | 0
36 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Choto Jharia T/W no. -III Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000537/2022-2023 | 3080/JMD | 28/09/2022 | 26/01/2023 | ASHUTOSH DAS & CO. | 5.63 | 5.02 | 89.24 | 0
37 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Amla Kora T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000538/2022-2023 | 3081/JMD | 28/09/2022 | 26/01/2023 | A.M.S. ENTERPRISE | 5.7 | 0 | 0 | 0
38 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Balia Geria T/W no. I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000550/2022-2023 | 3157/JMD | 19/10/2022 | 16/02/2023 | BUSR ENGINEERING | 5.7 | 5.1 | 89.55 | 0
39 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bag Doba T/W no. II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000565/2022-2023 | 3165/JMD | 19/10/2022 | 16/02/2023 | M/S. NABIN GOPAL SENGUPTA | 5.71 | 5.14 | 90.01 | 0
40 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bhaluk Chua T/W no. I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000556/2022-2023 | 3161/JMD | 19/10/2022 | 16/02/2023 | KAMAKHYA ENTERPRISE | 5.71 | 4.82 | 84.47 | 0
41 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kendisol T/W no. -I & II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000519/2022-2023 | 3067/JMD | 28/09/2022 | 26/01/2023 | SOUMEN ELECTRIC | 6.79 | 4.86 | 71.66 | 0
42 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Lakhipara T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000530/2022-2023 | 3074/JMD | 28/09/2022 | 26/01/2023 | SWAPAN ENTERPRISE | 5.71 | 4.99 | 87.43 | 0
43 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Shutpipal, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000691/2022-2023 | 147/JMD | 19/01/2023 | 19/05/2023 | M/S. NABIN GOPAL SENGUPTA | 5.78 | 4.21 | 72.8 | 95
44 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Rukhni Mara (Pry. School) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000559/2022-2023 | 3164/JMD | 19/10/2022 | 16/02/2023 | S.S. GHORAI | 5.71 | 5.11 | 89.51 | 0
45 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bara Sol, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000711/2022-2023 | 261/JMD | 03/02/2023 | 03/06/2023 | JAL PRAVAHIKA PVT. LTD. | 5.78 | 0 | 0 | 0
46 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Purna Pani stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000719/2022-2023 | 3516/JMD | 29/11/2022 | 06/12/2022 | SUBHASIS ROY | 0.07 | 0 | 0 | 0
47 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bachhur Khoyar (Purba Para) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000704/2022-2023 | 3486/JMD | 29/11/2022 | 06/12/2022 | DEB KUMAR BASU | 0.07 | 0 | 0 | 0
48 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bachhur Khoyar (Ramchandrapur) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000701/2022-2023 | 3490/JMD | 29/11/2022 | 06/12/2022 | DEB KUMAR BASU | 0.07 | 0 | 0 | 0
49 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Sankisol stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000702/2022-2023 | 3541/JMD | 29/11/2022 | 06/12/2022 | DEB KUMAR BASU | 0.07 | 0 | 0 | 0
50 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Rajpara T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000721/2022-2023 | 3519/JMD | 29/11/2022 | 06/12/2022 | DEB KUMAR BASU | 0.07 | 0 | 0 | 0
51 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Mura Kati (G.P. - Barakhankri) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000717/2022-2023 | 268/JMD | 03/02/2023 | 03/06/2023 | DAS CONSTRUCTION | 5.76 | 5.07 | 87.91 | 95
52 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Marchi Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000687/2022-2023 | 143/JMD | 19/01/2023 | 19/05/2023 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 5.78 | 0 | 0 | 0
53 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Tukurya mouza of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000876/2021-2022 | 567/JMD | 23/12/2021 | 27/12/2021 | CHAKRABORTY MINING & ENGINEERING | 2.77 | 0 | 0 | 0
54 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Shahari mouza of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000879/2021-2022 | 576/JMD | 23/12/2021 | 27/12/2021 | CHAKRABORTY MINING & ENGINEERING | 0.33 | 0 | 0 | 0
55 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Shahari mouza of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000875/2021-2022 | 575/JMD | 23/12/2021 | 27/12/2021 | CHAKRABORTY MINING & ENGINEERING | 2.77 | 0 | 0 | 0
56 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bara Ningui, Tube Well no.-III Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000012/2023-2024 | 960/JMD | 25/04/2023 | 23/08/2023 | MENAKA ENTERPRISE | 5.78 | 5.15 | 89.19 | 95
57 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Dhengbahara mouza, tube well no.2 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000882/2021-2022 | 144/JMD | 31/01/2022 | 02/02/2022 | CHAKRABORTY MINING & ENGINEERING | 0.15 | 0 | 0 | 0
58 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Ramkrishnapur, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000018/2023-2024 | 966/JMD | 25/04/2023 | 23/08/2023 | M/S. EMMESS | 5.78 | 4.13 | 71.49 | 95
59 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Rangua mouza, tube well no.2 of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000888/2021-2022 | 485/JMD | 23/12/2021 | 27/12/2021 | SUJOY RANJAN BHOWMICK | 2.62 | 0 | 0 | 0
60 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Salika mouza of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000884/2021-2022 | 558/JMD | 23/12/2021 | 27/12/2021 | CHAKRABORTY MINING & ENGINEERING | 0.33 | 0 | 0 | 0
61 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Dhadka mouza of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000886/2021-2022 | 543/JMD | 23/12/2021 | 27/12/2021 | CHAKRABORTY MINING & ENGINEERING | 2.59 | 0 | 0 | 0
62 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Dhadka mouza of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000878/2021-2022 | 544/JMD | 23/12/2021 | 27/12/2021 | CHAKRABORTY MINING & ENGINEERING | 0.33 | 0 | 0 | 0
63 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply and delivery of Silpaulin for Drilling works at Rig Store of MMSD(D) in Jhargram Dist. under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000771/2022-2023 | 1011/JMD | 26/05/2022 | 02/06/2022 | MONORANJAN DEY | 1.84 | 0 | 0 | 0
64 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Amadubi mouza, tube well no.1 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000891/2021-2022 | 94/JMD | 31/01/2022 | 02/02/2022 | DEBJYOTI BASU | 0.15 | 0 | 0 | 0
65 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Rangua mouza, tube well no.2 of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000889/2021-2022 | 486/JMD | 23/12/2021 | 27/12/2021 | SUJOY RANJAN BHOWMICK | 0.33 | 0 | 0 | 0
66 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Dhengbahara mouza, tube well no.2 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000881/2021-2022 | 143/JMD | 31/01/2022 | 02/02/2022 | CHAKRABORTY MINING & ENGINEERING | 0.71 | 0 | 0 | 0
67 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Salika mouza of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000883/2021-2022 | 557/JMD | 23/12/2021 | 27/12/2021 | CHAKRABORTY MINING & ENGINEERING | 2.77 | 0 | 0 | 0
68 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking & Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Rangua & others mouza, of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer |  | ORD/000160/2021-2022 | 484/JMD | 23/12/2021 | 08/01/2022 | DEBJYOTI BASU | 2.39 | 2.39 | 100 | 0
69 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Amadubi mouza, tube well no.2 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000896/2021-2022 | 96/JMD | 31/01/2022 | 02/02/2022 | DEBJYOTI BASU | 0.15 | 0 | 0 | 0
70 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Bara Mara mouza of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000905/2021-2022 | 721/JMD | 31/12/2021 | 04/01/2022 | M/S. SAMRIDDHI ENTERPRISE | 0.33 | 0 | 0 | 0
71 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Bali Muri mouza of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000906/2021-2022 | 708/JMD | 31/12/2021 | 04/01/2022 | M/S. SAMRIDDHI ENTERPRISE | 0.33 | 0 | 0 | 0
72 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Paschim Gholai stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000805/2022-2023 | 3513/JMD | 29/11/2022 | 06/12/2022 | M/S. NABIN GOPAL SENGUPTA | 0.07 | 0 | 0 | 0
73 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Sal Bani mouza of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000900/2021-2022 | 722/JMD | 31/12/2021 | 04/01/2022 | M/S. SAMRIDDHI ENTERPRISE | 2.6 | 0 | 0 | 0
74 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Sal Bani mouza of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000901/2021-2022 | 723/JMD | 31/12/2021 | 04/01/2022 | M/S. SAMRIDDHI ENTERPRISE | 0.33 | 0 | 0 | 0
75 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Bihankuria mouza of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000902/2021-2022 | 645/JMD | 31/12/2021 | 04/01/2022 | M/S. SAMRIDDHI ENTERPRISE | 2.6 | 0 | 0 | 0
76 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Bihankuria mouza of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000903/2021-2022 | 646/JMD | 31/12/2021 | 04/01/2022 | M/S. SAMRIDDHI ENTERPRISE | 0.33 | 0 | 0 | 0
77 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Bara Mara mouza of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000904/2021-2022 | 720/JMD | 31/12/2021 | 04/01/2022 | M/S. SAMRIDDHI ENTERPRISE | 2.6 | 0 | 0 | 0
78 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Amadubi mouza, tube well no.1 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000894/2021-2022 | 93/JMD | 31/01/2022 | 02/02/2022 | DEBJYOTI BASU | 0.71 | 0 | 0 | 0
79 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Amadubi mouza, tube well no.2 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000895/2021-2022 | 95/JMD | 31/01/2022 | 02/02/2022 | DEBJYOTI BASU | 0.71 | 0 | 0 | 0
80 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Birbhanpur Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000054/2023-2024 | 1349/JMD | 06/06/2023 | 04/10/2023 | JAGANNATH ENTERPRISE | 5.78 | 5.17 | 89.39 | 95
81 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bhaluk Ghara Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000757/2022-2023 | 663/JMD | 24/03/2023 | 22/07/2023 | T.N. BANERJEE | 5.77 | 0 | 0 | 0
82 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Bhadai stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000812/2022-2023 | 3535/JMD | 29/11/2022 | 06/12/2022 | P.K. ENGINEERING | 0.07 | 0 | 0 | 0
83 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Tukurya mouza of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000885/2021-2022 | 568/JMD | 23/12/2021 | 27/12/2021 | CHAKRABORTY MINING & ENGINEERING | 0.33 | 0 | 0 | 0
84 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Binpur-II_1_2 under Jhargram Division in the District of Jhargram. | Assistant Engineer | Junior Engineer-II | ORD/000155/2021-2022 | 285/MD | 15/02/2022 | 14/08/2022 | J.K. BUILDERS | 75.35 | 0 | 0 | 0
85 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Baghjhapa stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000807/2022-2023 | 3517/JMD | 29/11/2022 | 06/12/2022 | M/S. SAMRIDDHI ENTERPRISE | 0.07 | 0 | 0 | 0
86 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Sonamui stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000810/2022-2023 | 3515/JMD | 29/11/2022 | 06/12/2022 | P.K. ENGINEERING | 0.07 | 0 | 0 | 0
87 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Chandabila, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000038/2023-2024 | 1293/JMD | 30/05/2023 | 27/09/2023 | S.S. GHORAI | 5.78 | 5.06 | 87.61 | 95
88 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Chilkigar mouza, tube well no.3 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000908/2021-2022 | 564/JMD | 23/12/2021 | 27/12/2021 | CHAKRABORTY MINING & ENGINEERING | 0.33 | 0 | 0 | 0
89 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Rangua T/W no. I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000097/2023-2024 | 1713/JMD | 13/07/2023 | 10/11/2023 | SUBHASIS ROY | 5.77 | 0 | 0 | 0
90 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Chilkigar mouza, tube well no.3 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000907/2021-2022 | 563/JMD | 23/12/2021 | 27/12/2021 | CHAKRABORTY MINING & ENGINEERING | 2.6 | 0 | 0 | 0
91 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bag Doba T/W no. II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000806/2022-2023 | 3497/JMD | 29/11/2022 | 06/12/2022 | M/S. NABIN GOPAL SENGUPTA | 0.07 | 0 | 0 | 0
92 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dhumsai T/W no. -II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000808/2022-2023 | 3483/JMD | 29/11/2022 | 06/12/2022 | M/S. SAMRIDDHI ENTERPRISE | 0.07 | 0 | 0 | 0
93 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Salgaria (Near Club) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000809/2022-2023 | 3481/JMD | 29/11/2022 | 06/12/2022 | SAMARPITA ENGINEERING | 0.07 | 0 | 0 | 0
94 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kundal Pahari T/W no. -I & II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000094/2023-2024 | 1710/JMD | 13/07/2023 | 09/01/2024 | DAS CONSTRUCTION | 6.89 | 0 | 0 | 0
95 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Amlasol T/W no. -I & II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000811/2022-2023 | 3445/JMD | 29/11/2022 | 06/12/2022 | P.K. ENGINEERING | 0.07 | 0 | 0 | 0
96 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Gohalberya T/W no. -III & IV Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000084/2023-2024 | 1707/JMD | 13/07/2023 | 09/01/2024 | SUJOY RANJAN BHOWMICK | 6.89 | 0 | 0 | 0
97 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Rupai T/W no. -I & II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000085/2023-2024 | 1708/JMD | 13/07/2023 | 09/01/2024 | DEBJYOTI BASU | 6.89 | 0 | 0 | 0
98 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Bali Muri mouza of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000893/2021-2022 | 707/JMD | 31/12/2021 | 04/01/2022 | M/S. BIKASH DE | 2.6 | 0 | 0 | 0
99 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Baradhansol, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000091/2023-2024 | 1731/JMD | 14/07/2023 | 11/11/2023 | M/S. SAMRIDDHI ENTERPRISE | 5.78 | 0 | 0 | 0
100 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Baradhansol, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000092/2023-2024 | 1732/JMD | 14/07/2023 | 11/11/2023 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 5.78 | 0 | 0 | 0
101 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Metyalsol Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000093/2023-2024 | 1733/JMD | 14/07/2023 | 11/11/2023 | SAMARPITA ENGINEERING | 5.78 | 0 | 0 | 0
102 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Khasjangal, Tube Well no.-VI Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000110/2023-2024 | 1769/JMD | 19/07/2023 | 16/11/2023 | ECO ENTERPRISE | 5.77 | 0 | 0 | 0
103 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking & Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Murar & other mouza of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer |  | ORD/000161/2021-2022 | 498/JMD | 23/12/2021 | 24/01/2022 | SUJOY RANJAN BHOWMICK | 4.31 | 4.31 | 100 | 0
104 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply and delivery of Silpaulin for Drilling works at Rig Store of MMSD(D) in Jhargram Dist. under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer |  | ORD/000249/2022-2023 | 1011/JMD | 26/05/2022 | 02/06/2022 | MONORANJAN DEY | 1.34 | 1.34 | 100 | 0
105 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing one no. 10 MT capacity truck along with licensed driver on daily basis for Rig unit no. 21D/LT/500 of MMSD(D) under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer |  | ORD/000250/2022-2023 | 1027/JMD | 30/05/2022 | 28/08/2022 | MONORANJAN DEY | 0.92 | 0.92 | 100 | 0
106 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bhaluk Chua T/W no. I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000817/2022-2023 | 3493/JMD | 29/11/2022 | 06/12/2022 | KAMAKHYA ENTERPRISE | 0.07 | 0 | 0 | 0
107 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply & delivery of different size hydraulic hose & filter membrane for Hydraulic unit , cross member for shaft line ,lubricants for engine and others works for KLR /DR/DTH -500 & 21D/LT-500 rig unit & brake shoe assembly for LMP-500 rig unit . | Assistant Engineer |  | ORD/000162/2021-2022 | 494/JMD | 15/03/2022 | 14/04/2022 | B. P. TRADING CORPORATION | 4.41 | 4.41 | 100 | 0
108 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Khasjangal, Tube Well no.-IV Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000108/2023-2024 | 1767/JMD | 19/07/2023 | 16/11/2023 | PRANAB KUMAR DAS | 5.78 | 0 | 0 | 0
109 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Khasjangal, Tube Well no.-V Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000109/2023-2024 | 1768/JMD | 19/07/2023 | 16/11/2023 | RITESH ENTERPRISE | 5.78 | 0 | 0 | 0
110 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing one no. 10 MT capacity truck & one no 32 BHP Capacity Tractor along with licensed driver on daily basis for Rig unit no. 41D/LMP/500 of MMSD(D) under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000841/2022-2023 | 366/JMD | 23/02/2023 | 15/03/2023 | M/S. SAMRIDDHI ENTERPRISE | 0.97 | 0 | 0 | 0
111 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kadokota Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000133/2023-2024 | 1825/JMD | 24/07/2023 | 21/11/2023 | BHABANI PRASAD MANNA | 5.78 | 0 | 0 | 0
112 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bara Jharia Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000117/2023-2024 | 1798/JMD | 24/07/2023 | 21/11/2023 | SWAPAN ENTERPRISE | 5.78 | 0 | 0 | 0
113 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Narda, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000113/2023-2024 | 1772/JMD | 19/07/2023 | 16/11/2023 | MAA BHABOTARINE ENTERPRISE | 5.78 | 0 | 0 | 0
114 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kul Diha, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000135/2023-2024 | 1827/JMD | 24/07/2023 | 21/11/2023 | RITESH ENTERPRISE | 5.78 | 0 | 0 | 0
115 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of 1(One) Nos. 150 mm X 100 mm X 135 Mtr. RBTW, for lowering of Submersible Pumping Machinery at Kamapukuria - II Village Stand Alone PWSS for Nayagram Block under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000108/2023-2024 | 653/JSD | 18/07/2023 | 17/08/2023 | PASCHIMANCHAL ADIBASI ENGINEERS CO-OPERATIVE SOCIETY LIMITED. | 4.32 | 0 | 0 | 0
116 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bhalia Chati Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000166/2023-2024 | 2022/JMD | 02/08/2023 | 30/11/2023 | A. G. ENTERPRISE | 5.78 | 0 | 0 | 0
117 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of 1(One) Nos. 150 mm X 100 mm X 135 Mtr. RBTW, for lowering of Submersible Pumping Machinery at Kamapukuria - V Village Stand Alone PWSS for Nayagram Block under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-III | ORD/000112/2023-2024 | 665/JSD | 24/07/2023 | 23/08/2023 | ANANGA MOHAN GHOSH | 4.3 | 0 | 0 | 0
118 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of 1(One) Nos. 150 mm X 100 mm X 135 Mtr. RBTW, for lowering of Submersible Pumping Machinery at Kamapukuria - VI Village Stand Alone PWSS for Nayagram Block under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-III | ORD/000113/2023-2024 | 666/JSD | 24/07/2023 | 23/08/2023 | GOUTAM KUMAR BOSE | 4.29 | 0 | 0 | 0
119 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dumuria, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000139/2023-2024 | 1831/JMD | 24/07/2023 | 21/11/2023 | ARATI ENGINEERING | 5.78 | 0 | 0 | 0
120 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Nandalalpur Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000145/2023-2024 | 1837/JMD | 24/07/2023 | 21/11/2023 | SUBHASIS ROY | 5.77 | 0 | 0 | 0
121 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dulki, Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000114/2023-2024 | 1795/JMD | 24/07/2023 | 21/11/2023 | BHABANI PRASAD MANNA | 5.78 | 0 | 0 | 0
122 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kalma Pukhuria, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000122/2023-2024 | 1804/JMD | 24/07/2023 | 21/11/2023 | SUBHASIS ROY | 5.77 | 0 | 0 | 0
123 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bankati Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000147/2023-2024 | 1839/JMD | 24/07/2023 | 21/11/2023 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD | 5.77 | 0 | 0 | 0
124 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bardhan Sola (G.P.- Kharikamathani), Tube Well no.-III Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000144/2023-2024 | 1836/JMD | 24/07/2023 | 21/11/2023 | M.D. ENTERPRISE | 5.77 | 0 | 0 | 0
125 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kuldiha Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000167/2023-2024 | 2032/JMD | 02/08/2023 | 30/11/2023 | EASTERN INDIA SALES AND SERVICE | 5.77 | 0 | 0 | 0
126 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Nara Singha Pur, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000119/2023-2024 | 1801/JMD | 24/07/2023 | 21/11/2023 | M/S. SAJAHAN CHOWDHURY | 5.78 | 0 | 0 | 0
127 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kalma Pukhuria, Tube Well no.-III Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000123/2023-2024 | 1805/JMD | 24/07/2023 | 21/11/2023 | SUBHASIS ROY | 5.77 | 0 | 0 | 0
128 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Khasjangal, Tube Well no.-III Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000158/2023-2024 | 1969/JMD | 31/07/2023 | 28/11/2023 | M/S B.M. ELECTRICAL | 5.78 | 0 | 0 | 0
129 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Nagri Pada, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000160/2023-2024 | 1971/JMD | 31/07/2023 | 28/11/2023 | SHOVAN KUMAR DAS | 5.78 | 5.09 | 87.97 | 95
130 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Sal Bani Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000141/2023-2024 | 1833/JMD | 24/07/2023 | 21/11/2023 | JAGANNATH ENTERPRISE | 5.78 | 5.11 | 88.42 | 96
131 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bardhan Sola (G.P.- Kharikamathani), Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000142/2023-2024 | 1834/JMD | 24/07/2023 | 21/11/2023 | P.K. ENGINEERING | 5.78 | 0 | 0 | 0
132 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bardhan Sola (G.P.- Kharikamathani), Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000143/2023-2024 | 1835/JMD | 24/07/2023 | 21/11/2023 | AMIT DAS | 5.77 | 0 | 0 | 0
133 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Nara Singha Pur, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000120/2023-2024 | 1802/JMD | 24/07/2023 | 21/11/2023 | DAS CONSTRUCTION | 5.78 | 0 | 0 | 0
134 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kukrasole, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000134/2023-2024 | 1826/JMD | 24/07/2023 | 21/11/2023 | SWAPAN ENTERPRISE | 5.78 | 0 | 0 | 0
135 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dumuria, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Driller-In-Charge | JE (M),Junior Engineer | ORD/000138/2023-2024 | 1830/JMD | 24/07/2023 | 21/11/2023 | A.S. ENTERPRISE | 5.78 | 0 | 0 | 0
136 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Malam, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000127/2023-2024 | 1819/JMD | 24/07/2023 | 21/11/2023 | DEBJYOTI BASU | 5.77 | 0 | 0 | 0
137 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of 1(One) Nos. 150 mm X 100 mm X 135 Mtr. RBTW, for lowering of Submersible Pumping Machinery at Kamapukuria - III Village Stand Alone PWSS for Nayagram Block under Jhargram Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000109/2023-2024 | 661/JSD | 20/07/2023 | 19/08/2023 | ANANGA MOHAN GHOSH | 4.33 | 0 | 0 | 0
138 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Swarup Narayanpur Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000148/2023-2024 | 1840/JMD | 24/07/2023 | 21/11/2023 | ECO ENTERPRISE | 5.78 | 3.78 | 65.46 | 95
139 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Bankra stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000879/2022-2023 | 3537/JMD | 29/11/2022 | 06/12/2022 | MONORANJAN DEY | 0.07 | 0 | 0 | 0
140 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Koima (Pal) T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000876/2022-2023 | 3467/JMD | 29/11/2022 | 06/12/2022 | M/S. EMMESS | 0.07 | 0 | 0 | 0
141 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Bara Khankri stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000874/2022-2023 | 3458/JMD | 29/11/2022 | 06/12/2022 | M/S. EMMESS | 0.07 | 0 | 0 | 0
142 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Narda stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000873/2022-2023 | 3450/JMD | 29/11/2022 | 06/12/2022 | ECO ENTERPRISE | 0.07 | 0 | 0 | 0
143 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under Jamboni Block location Id Jamboni_4_2 under Jhargram Division in the District of Jhargram. | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000182/2023-2024 | 1436/JHD | 24/08/2023 | 23/10/2023 | TAPAN KUMAR MANDAL | 19.76 | 0 | 0 | 0
144 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Lakhipara (School) T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000875/2022-2023 | 3466/JMD | 29/11/2022 | 06/12/2022 | MONORANJAN DEY | 0.07 | 0 | 0 | 0
145 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dhumsai T/W no. -III Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000877/2022-2023 | 3484/JMD | 29/11/2022 | 06/12/2022 | ECO ENTERPRISE | 0.07 | 0 | 0 | 0
146 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Koima (A.W.C.) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000878/2022-2023 | 3499/JMD | 29/11/2022 | 06/12/2022 | M/S. EMMESS | 0.07 | 0 | 0 | 0
147 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Kargonala stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000872/2022-2023 | 3442/JMD | 29/11/2022 | 06/12/2022 | ECO ENTERPRISE | 0.07 | 0 | 0 | 0
148 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Bankati mouza of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | Junior Engineer | ORD/000927/2021-2022 | 507/JMD | 23/12/2021 | 27/12/2021 | RSA ENTERPRISE | 2.62 | 0 | 0 | 0
149 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Bankati mouza of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000916/2021-2022 | 508/JMD | 23/12/2021 | 27/12/2021 | RSA ENTERPRISE | 0.33 | 0 | 0 | 0
150 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Dubrajpur stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000887/2022-2023 | 1419./JMD | 14/06/2022 | 12/10/2022 | SUJOY RANJAN BHOWMICK | 6.86 | 0.53 | 7.77 | 100
151 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Dubrajpur stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000888/2022-2023 | 1429./JMD | 14/06/2022 | 12/10/2022 | SUJOY RANJAN BHOWMICK | 6.86 | 0.53 | 7.77 | 100
152 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Nischinta stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000893/2022-2023 | 3508/JMD | 29/11/2022 | 06/12/2022 | S.S. GHORAI | 0.07 | 0 | 0 | 0
153 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Kalma Pukhuria stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000890/2022-2023 | 3457/JMD | 29/11/2022 | 06/12/2022 | S.S. GHORAI | 0.07 | 0 | 0 | 0
154 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Nara Singha Pur mouza , tube well no. 1 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000933/2021-2022 | 657/JMD | 31/12/2021 | 04/01/2022 | SAMARPITA ENGINEERING | 2.6 | 0 | 0 | 0
155 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Kalma Pukhuria mouza , tube well no. 2 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000934/2021-2022 | 673/JMD | 31/12/2021 | 04/01/2022 | SAMARPITA ENGINEERING | 2.6 | 0 | 0 | 0
156 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Nara Singha Pur mouza , tube well no. 2 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000941/2021-2022 | 660/JMD | 31/12/2021 | 04/01/2022 | SAMARPITA ENGINEERING | 0.33 | 0 | 0 | 0
157 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Dubrajpur stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000899/2022-2023 | 1419../JMD | 14/07/2022 | 11/11/2022 | SUJOY RANJAN BHOWMICK | 6.86 | 0.74 | 10.77 | 70
158 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Kalma Pukhuria mouza , tube well no. 2 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000938/2021-2022 | 674/JMD | 31/12/2021 | 04/01/2022 | SAMARPITA ENGINEERING | 0.33 | 0 | 0 | 0
159 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Nara Singha Pur mouza , tube well no. 1 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000939/2021-2022 | 658/JMD | 31/12/2021 | 04/01/2022 | SAMARPITA ENGINEERING | 0.33 | 0 | 0 | 0
160 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Rukhni Mara (Pry. School) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000892/2022-2023 | 3496/JMD | 29/11/2022 | 06/12/2022 | S.S. GHORAI | 0.07 | 0 | 0 | 0
161 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Shibanandapur T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000891/2022-2023 | 3465/JMD | 29/11/2022 | 06/12/2022 | BALAJI CONSTRUCTION | 0.07 | 0 | 0 | 0
162 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Dhengbahara mouza, tube well no.3 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000971/2021-2022 | 146/JMD | 31/01/2022 | 02/02/2022 | CHAKRABORTY MINING & ENGINEERING | 0.16 | 0 | 0 | 0
163 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Dhengbahara mouza, tube well no.3 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000952/2021-2022 | 145/JMD | 31/01/2022 | 02/02/2022 | CHAKRABORTY MINING & ENGINEERING | 0.71 | 0 | 0 | 0
164 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Narda mouza , tube well no. 2 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000955/2021-2022 | 652/JMD | 31/12/2021 | 04/01/2022 | M/S. SAMRIDDHI ENTERPRISE | 0.33 | 0 | 0 | 0
165 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Kadokata, tube well no. 1 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000902/2022-2023 | 1066/JMD | 01/06/2022 | 06/06/2022 | M/S. SAMRIDDHI ENTERPRISE | 0.33 | 0 | 0 | 0
166 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Chandabila mouza, tube well no.2 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000946/2021-2022 | 140/JMD | 31/01/2022 | 02/02/2022 | CHAKRABORTY MINING & ENGINEERING | 0.16 | 0 | 0 | 0
167 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Swarup Narayanpur mouza of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000964/2021-2022 | 516/JMD | 23/12/2021 | 27/12/2021 | RSA ENTERPRISE | 0.33 | 0 | 0 | 0
168 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Metyalsol mouza of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000965/2021-2022 | 506/JMD | 23/12/2021 | 27/12/2021 | RSA ENTERPRISE | 0.33 | 0 | 0 | 0
169 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Baradhansol mouza, tube well no.2 of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000966/2021-2022 | 504/JMD | 23/12/2021 | 27/12/2021 | RSA ENTERPRISE | 0.33 | 0 | 0 | 0
170 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Muniada mouza, tube well no.4 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000967/2021-2022 | 135/JMD | 31/01/2022 | 02/02/2022 | CHAKRABORTY MINING & ENGINEERING | 0.71 | 0 | 0 | 0
171 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Muniada mouza, tube well no.4 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000973/2021-2022 | 136/JMD | 31/01/2022 | 02/02/2022 | CHAKRABORTY MINING & ENGINEERING | 0.16 | 0 | 0 | 0
172 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Narda mouza , tube well no. 2 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000956/2021-2022 | 651/JMD | 31/12/2021 | 04/01/2022 | M/S. SAMRIDDHI ENTERPRISE | 2.62 | 0 | 0 | 0
173 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Baradhansol mouza, tube well no.1 of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000959/2021-2022 | 501/JMD | 23/12/2021 | 27/12/2021 | RSA ENTERPRISE | 2.62 | 0 | 0 | 0
174 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Metyalsol mouza of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000961/2021-2022 | 505/JMD | 30/12/2021 | 03/01/2022 | RSA ENTERPRISE | 2.62 | 0 | 0 | 0
175 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Muniada mouza, tube well no.3 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000968/2021-2022 | 133/JMD | 31/01/2022 | 02/02/2022 | CHAKRABORTY MINING & ENGINEERING | 0.71 | 0 | 0 | 0
176 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Dhengbahara mouza, tube well no.4 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000969/2021-2022 | 147/JMD | 31/01/2022 | 02/02/2022 | CHAKRABORTY MINING & ENGINEERING | 0.71 | 0 | 0 | 0
177 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Dhengbahara mouza, tube well no.4 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000970/2021-2022 | 148/JMD | 31/01/2022 | 02/02/2022 | CHAKRABORTY MINING & ENGINEERING | 0.16 | 0 | 0 | 0
178 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Kukrasol, tube well no. 1 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000912/2022-2023 | 1073/JMD | 01/06/2022 | 06/06/2022 | SAMARPITA ENGINEERING | 0.33 | 0 | 0 | 0
179 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Chandabila mouza, tube well no.2 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000951/2021-2022 | 139/JMD | 31/01/2022 | 02/02/2022 | CHAKRABORTY MINING & ENGINEERING | 0.71 | 0 | 0 | 0
180 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Muniada mouza, tube well no.3 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000972/2021-2022 | 134/JMD | 31/01/2022 | 02/02/2022 | CHAKRABORTY MINING & ENGINEERING | 0.16 | 0 | 0 | 0
181 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Baradhansol mouza, tube well no.2 of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000957/2021-2022 | 503/JMD | 23/12/2021 | 27/12/2021 | RSA ENTERPRISE | 2.62 | 0 | 0 | 0
182 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Swarup Narayanpur mouza of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000958/2021-2022 | 515/JMD | 23/12/2021 | 27/12/2021 | RSA ENTERPRISE | 2.62 | 0 | 0 | 0
183 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Kukrasol, tube well no. 1 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000907/2022-2023 | 1072/JMD | 01/06/2022 | 06/06/2022 | SAMARPITA ENGINEERING | 2.8 | 0 | 0 | 0
184 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Kadokata, tube well no. 1 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000908/2022-2023 | 1065/JMD | 01/06/2022 | 06/06/2022 | M/S. SAMRIDDHI ENTERPRISE | 2.8 | 0 | 0 | 0
185 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Nandalalpur mouza of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000960/2021-2022 | 481/JMD | 23/12/2021 | 27/12/2021 | RSA ENTERPRISE | 2.62 | 0 | 0 | 0
186 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Baradhansol mouza, tube well no.1 of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000962/2021-2022 | 502/JMD | 23/12/2021 | 27/12/2021 | RSA ENTERPRISE | 0.33 | 0 | 0 | 0
187 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Kukrasol, tube well no. 2 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000910/2022-2023 | 1075/JMD | 01/06/2022 | 06/06/2022 | SAMARPITA ENGINEERING | 0.33 | 0 | 0 | 0
188 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Nandalalpur mouza of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000963/2021-2022 | 482/JMD | 23/12/2021 | 27/12/2021 | RSA ENTERPRISE | 0.33 | 0 | 0 | 0
189 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Nara Singha Pur mouza , tube well no. 2 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000931/2021-2022 | 659/JMD | 31/12/2021 | 04/01/2022 | SAMARPITA ENGINEERING | 2.6 | 0 | 0 | 0
190 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Kukrasol, tube well no. 2 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000909/2022-2023 | 1074/JMD | 01/06/2022 | 06/06/2022 | SAMARPITA ENGINEERING | 2.8 | 0 | 0 | 0
191 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bara Mara Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000760/2022-2023 | 666/JMD | 24/03/2023 | 22/07/2023 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 5.78 | 5.21 | 90.26 | 95
192 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Hiring of Diesel driven Commercial Covered four wheeler vehicle on daily basis along with LMV licensed driver for official purpose of Assistant Engineer, Jhargram Mechanical Division under office of Executive Engineer, Jhargram Mechanical Division, PHE Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000645/2021-2022 | 340/JMD | 03/03/2022 | 28/02/2023 | SUBHASIS ROY | 1.68 | 1.22 | 72.38 | 100
193 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Bhalki Sol stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000170/2022-2023 | 1470/JMD | 19/07/2022 | 16/11/2022 | M/S. EMMESS | 6.83 | 4.83 | 70.61 | 100
194 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Baghmari stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000171/2022-2023 | 1471/JMD | 19/07/2022 | 16/11/2022 | SOUMEN ELECTRIC | 6.86 | 5.04 | 73.45 | 100
195 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Kulghagri stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000165/2022-2023 | 1465/JMD | 19/07/2022 | 16/11/2022 | SOUMEN ELECTRIC | 6.86 | 5.04 | 73.45 | 100
196 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply delivery of CIDF S/V for the work of Stand Alone Water Supply Scheme (269 nos.) for Binpur-II & Gopiballavpur-I Block area under Jhargram Sub Division within Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer Gopiballavpur-I block,Junior Engineer-II | ORD/000023/2022-2023 | 351/JSD | 12/07/2022 | 27/07/2022 | SANKAR KUMAR NAG | 4.72 | 4.72 | 100 | 1
197 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply delivery of CIDF S/V for the work of Stand Alone Water Supply Scheme (269 nos.) at Baligeria and Barakhakri GP of Nayagram Block area under Jhargram Sub Division within Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer Gopiballavpur-II block | ORD/000035/2022-2023 | 44/GPSD | 29/08/2022 | 13/09/2022 | DIPAK KUMAR BAKLY | 4.8 | 4.76 | 99.09 | 1
198 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply delivery of CIDF S/V for the work of Stand Alone Water Supply Scheme (269 nos.) at Chandabila and Patina GP of Nayagram Block area under Jhargram Sub Division within Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer Nayagram block | ORD/000032/2022-2023 | 43/GPSD | 29/08/2022 | 13/09/2022 | GOBINDA MAITY | 4.8 | 4.8 | 100 | 1
199 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply delivery of CIDF S/V for the work of Stand Alone Water Supply Scheme (269 nos.) for Binpur-I Block area under Jhargram Sub Division within Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer Binpur-I block | ORD/000024/2022-2023 | 354/JSD | 15/07/2022 | 30/07/2022 | BIDYUT KUMAR SANTRA | 4.8 | 4.8 | 100 | 1
200 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply delivery of CIDF S/V for the work of Stand Alone Water Supply Scheme (269 nos.) at Sankrail Block area under Jhargram Sub Division within Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer Sankrail block | ORD/000039/2022-2023 | 45/GPSD | 29/08/2022 | 13/09/2022 | DIPAK KUMAR BAKLY | 4.76 | 4.8 | 100.92 | 1
201 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Tiakati T/W no. I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000567/2022-2023 | 3167/JMD | 19/10/2022 | 16/02/2023 | AMIT DAS | 5.71 | 5.68 | 99.52 | 0
202 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Salgaria (Near School) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000555/2022-2023 | 3160/JMD | 19/10/2022 | 16/02/2023 | M/S MANABESH ROY | 5.71 | 5.68 | 99.53 | 0
203 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bachhur Khoyar (Ramchandrapur) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000553/2022-2023 | 3158/JMD | 19/10/2022 | 16/02/2023 | DEB KUMAR BASU | 5.71 | 5.69 | 99.74 | 0
204 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Gopiballavpir-I_2_1_B under Jhargram Division in the District of Jhargram. | Assistant Engineer | Junior Engineer Gopiballavpur-I block | ORD/000101/2022-2023 | 618/JHD | 25/11/2022 | 25/03/2023 | DEBABRATA DUTTA | 22.25 | 15.83 | 71.14 | 100
205 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Jirapara Stand Alone piped water supply scheme, tube well no-I of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000670/2022-2023 | 4209/JMD | 28/12/2022 | 27/04/2023 | ABHIJIT BASU | 5.78 | 5.21 | 90.19 | 0
206 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Jhargram_2_4_Dunder Jhargram Division in the District of Jhargram. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000066/2022-2023 | 345/JHD | 28/09/2022 | 26/01/2023 | NIMAI LAL GURIA | 22.16 | 19.69 | 88.84 | 1
207 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Topoban T/W no. -II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000532/2022-2023 | 3076/JMD | 28/09/2022 | 26/01/2023 | JAL PRAVAHIKA PVT. LTD. | 5.71 | 5.7 | 99.8 | 0
208 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Sankrail_3_1 under Jhargram Division in the District of Jhargram. | Assistant Engineer | Junior Engineer Sankrail block | ORD/000158/2022-2023 | 877/MD | 10/05/2022 | 06/11/2022 | EFFLUENT AND WATER TREATMENT ENGINEERS PVT. LTD. | 150.3 | 139.98 | 93.14 | 100
209 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Topoban T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000531/2022-2023 | 3075/JMD | 28/09/2022 | 26/01/2023 | M/S D.G.B. ENTERPRISE | 5.71 | 5.7 | 99.8 | 0
210 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Laying of Clear Water Rising Main & Distribution pipe line in Patharchakri Dakshin para under 269 stand alone in Jhargram Block within Jhargram District under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-III | ORD/000166/2022-2023 | 64/JHD | 16/01/2023 | 23/01/2023 | ENVOTECH INFRA SOLUTION | 4.76 | 4.39 | 92.19 | 0
211 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking and providing manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Degaria and others mouza of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer |  | ORD/000139/2021-2022 | 545/JMD | 23/12/2021 | 30/12/2021 | SUJOY RANJAN BHOWMICK | 11.37 | 11.37 | 100 | 1
212 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Shutpipal stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000739/2022-2023 | 3435/JMD | 29/11/2022 | 06/12/2022 | DEBJYOTI BASU | 0.07 | 0.07 | 100 | 100
213 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking and providing manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Jugi Bandh and others mouza, tube well no.1 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer |  | ORD/000140/2021-2022 | 571/JMD | 23/12/2021 | 30/12/2021 | CHAKRABORTY MINING & ENGINEERING | 11.59 | 11.59 | 100 | 1
214 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Baghmari stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000813/2022-2023 | 3511/JMD | 29/11/2022 | 06/12/2022 | SOUMEN ELECTRIC | 0.07 | 0.07 | 100 | 100
215 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Laying of Distribution pipe line , Construction of Valve Chember& Inter Connection at Rupai Habitation (Rupai Mouza) under Barasukjora W/S Scheme in Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000013/2023-2024 | 321/JSD | 27/04/2023 | 11/06/2023 | SHRI RANISATI VENTURES | 3.74 | 3.73 | 99.5 | 100
216 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Functional Household Tap Connection data uploading charges of different pwss under Jhargram District in JJM_IMIS portal under Jal Jeevan Mission for January-2023 and February-2023 under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000253/2022-2023 | 29A/JRWS | 28/12/2022 | 26/02/2023 | PROVAT KUMAR DE | 0.93 | 0.29 | 31.11 | 100
217 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Kulghagri stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000818/2022-2023 | 3505/JMD | 29/11/2022 | 06/12/2022 | SOUMEN ELECTRIC | 0.07 | 0.07 | 100 | 100
218 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Goal Danga stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000819/2022-2023 | 3440/JMD | 29/11/2022 | 06/12/2022 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 0.07 | 0.07 | 100 | 100
219 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Laying of Distribution pipe line , Construction of Valve Chember& Inter Connection at Baliguma Habitation (Rupai Mouza) under Barasukjora W/S Scheme in Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000012/2023-2024 | 320/JSD | 27/04/2023 | 11/06/2023 | SHRI RANISATI VENTURES | 4.06 | 4.06 | 100 | 100
220 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Continuation Work for Functional Household Tap Connection data uploading charges of different pwss under Jhargram District in JJM_IMIS portal under Jal Jeevan Mission for March-2023 to May-2023 under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000264/2022-2023 | 50A/JRWS | 28/02/2023 | 29/05/2023 | PROVAT KUMAR DE | 0.83 | 0.79 | 94.51 | 100
221 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Arra , tube well no. 2 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000854/2022-2023 | 1058/JMD | 01/06/2022 | 06/06/2022 | M/S. SAMRIDDHI ENTERPRISE | 2.78 | 1.97 | 71.09 | 100
222 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Arra, tube well no. 2 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000855/2022-2023 | 1059/JMD | 01/06/2022 | 06/06/2022 | M/S. SAMRIDDHI ENTERPRISE | 0.33 | 0.26 | 79.22 | 100
223 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply & delivery of upvc consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary / Combination Method at Dhengabahara, Tube Well no.-II under Jamboni Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | Assistant Engineer | JE (M) | ORD/000295/2023-2024 | 2634/JMD | 29/08/2023 | 02/09/2023 | CHAKRABORTY MINING & ENGINEERING | 3.37 | 2.31 | 68.34 | 100
224 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply and delivery of Bentonite Powder sodium based (Rajasthan Varity) at MMSD(D) store room for sinking of Rig Bored Tube Wells under MMSD(D) under JMD PHE Dte. | Assistant Engineer | JE (M) | ORD/000296/2023-2024 | 2635/JMD | 29/08/2023 | 08/09/2023 | DEBJYOTI BASU | 2.24 | 2.24 | 100 | 100
225 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Dingla mouza of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000917/2021-2022 | 528/JMD | 23/12/2021 | 27/12/2021 | RSA ENTERPRISE | 0.33 | 0.33 | 100 | 100
226 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Tikra Para mouza of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000921/2021-2022 | 705/JMD | 31/12/2021 | 04/01/2022 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 2.6 | 1.86 | 71.67 | 100
227 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Kalma Pukhuria mouza , tube well no. 3 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000919/2021-2022 | 676/JMD | 31/12/2021 | 04/01/2022 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 0.33 | 0.26 | 79.22 | 100
228 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply and Delivery of Ø 7-7/8 " Drag Bit with Tungsten Carbide insert for Mud Rotary Drilling at MMSD(D) store room for sinking of Rig Bored Tube Wells under MMSD(D) under JMD PHE Dte. | Assistant Engineer | JE (M) | ORD/000297/2023-2024 | 2636/JMD | 29/08/2023 | 08/09/2023 | B. P. TRADING CORPORATION | 2.77 | 2.77 | 100 | 100
229 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply and Delivery of Ø 9 " Drag Bit with Tungsten Carbide insert for Mud Rotary Drilling at MMSD(D) store room for sinking of Rig Bored Tube Wells under MMSD(D) under JMD PHE Dte. | Assistant Engineer | JE (M) | ORD/000298/2023-2024 | 2637/JMD | 29/08/2023 | 08/09/2023 | SUDIP ENGINEERING CO. | 1.5 | 1.5 | 100 | 100
230 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking and providing manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Dhadka and others mouza of Jamboni and others blocks block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | Junior Engineer-II | ORD/000179/2021-2022 | 543/JMD | 23/12/2021 | 22/04/2022 | CHAKRABORTY MINING & ENGINEERING | 10.58 | 10.19 | 96.28 | 100
231 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking and providing manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Amadubuand others mouza of Binpur-II and others blocks block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer |  | ORD/000180/2021-2022 | 93/JMD | 31/01/2022 | 31/05/2022 | DEBJYOTI BASU | 1.83 | 1.74 | 94.86 | 100
232 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Bali Muri mouza of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer |  | ORD/000181/2021-2022 | 707/JMD | 31/12/2021 | 10/01/2022 | M/S. BIKASH DE | 2.1 | 2.02 | 96.22 | 100
233 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking and providing manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Rangua and others mouza of Binpur-Iand others blocks block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer |  | ORD/000182/2021-2022 | 485/JMD | 23/12/2021 | 22/04/2022 | SUJOY RANJAN BHOWMICK | 3.5 | 3.41 | 97.51 | 100
234 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking and providing manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Bihankuriaand others mouza of Nayagram and others blocks block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer |  | ORD/000183/2021-2022 | 645/JMD | 31/12/2021 | 14/04/2025 | M/S. SAMRIDDHI ENTERPRISE | 6.7 | 6.68 | 99.75 | 100
235 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Bankisol mouza of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000915/2021-2022 | 493/JMD | 23/12/2021 | 27/12/2021 | RSA ENTERPRISE | 2.62 | 1.59 | 60.83 | 100
236 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Malam mouza , tube well no. 2 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000920/2021-2022 | 699/JMD | 31/12/2021 | 04/01/2022 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 2.6 | 1.76 | 67.83 | 100
237 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Dingla mouza of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000928/2021-2022 | 527/JMD | 23/12/2021 | 27/12/2021 | RSA ENTERPRISE | 2.62 | 1.58 | 60.27 | 100
238 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Lakshanpur stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000871/2022-2023 | 3436/JMD | 29/11/2022 | 06/12/2022 | M/S. EMMESS | 0.07 | 0.07 | 100 | 100
239 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Malam mouza , tube well no. 1 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000918/2021-2022 | 698/JMD | 31/12/2021 | 04/01/2022 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 0.33 | 0.26 | 79.22 | 100
240 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply & delivery of upvc consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary / Combination Method at Khatkura Junior High School under Jamboni Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000357/2023-2024 | 2785/JMD | 07/09/2023 | 11/09/2023 | CHAKRABORTY MINING & ENGINEERING | 3.37 | 2.1 | 62.1 | 100
241 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Bankisol mouza of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000926/2021-2022 | 494/JMD | 23/12/2021 | 27/12/2021 | RSA ENTERPRISE | 0.33 | 0.33 | 100 | 100
242 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Dismantling the differential gear portion of HALCO Rig unit under Bankura Mechanical Division (BMD) and carrying the same from BMD to Jhargram Mechanical Division (JMD) for fitting fixing in 238/AR/HALCO Rig unit under MMSD(D) under JMD, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000433/2021-2022 | 350/JMD | 04/03/2022 | 14/03/2022 | CHAKRABORTY MINING & ENGINEERING | 0.14 | 0.14 | 98.51 | 100
243 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Gopiballavpir-I_2_1_A under Jhargram Division in the District of Jhargram. | Assistant Engineer | Junior Engineer Gopiballavpur-I block | ORD/000100/2022-2023 | 617/JHD | 25/11/2022 | 25/03/2023 | J.S.S. ENTERPRISE | 22.26 | 16.03 | 72 | 100
244 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Midnapore Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Nayagram_4_4 under Jhargram Division in the District of Jhargram. |  |  | ORD/000056/2022-2023 | 876/MD | 10/05/2022 | 06/11/2022 | EFFLUENT AND WATER TREATMENT ENGINEERS PVT. LTD. | 177.59 | 0 | 0 | 0
245 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Midnapore Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Nayagram_4_14 under Jhargram Division in the District of Jhargram. |  |  | ORD/000645/2021-2022 | 186/MD | 01/02/2022 | 31/07/2022 | GOBINDA MAITY | 177.71 | 29.53 | 16.61 | 1
246 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Midnapore Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Jhargram_2_2 under Jhargram Division in the District of Jhargram. |  |  | ORD/000706/2021-2022 | 302/MD | 15/02/2022 | 14/08/2022 | LALIT BIHARI MAITY | 132.67 | 24.19 | 18.23 | 1
247 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Midnapore Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Gopiballavpur-II_2_1 under Jhargram Division in the District of Jhargram. |  |  | ORD/000705/2021-2022 | 301/MD | 15/02/2022 | 14/08/2022 | ASIS KUMAR SARANGI | 135.09 | 47.93 | 35.48 | 1
248 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Midnapore Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Nayagram_1_2 under Jhargram Division in the District of Jhargram. |  |  | ORD/000649/2021-2022 | 190/MD | 01/02/2022 | 31/07/2022 | SUJATA CONSTRUCTION | 106.99 | 0 | 0 | 1
249 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Midnapore Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Nayagram_1_1 under Jhargram Division in the District of Jhargram. |  |  | ORD/000648/2021-2022 | 189/MD | 01/02/2022 | 31/07/2022 | PROVAT KUMAR DE | 106.64 | 0 | 0 | 0
250 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Midnapore Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Nayagram_4_5 under Jhargram Division in the District of Jhargram. |  |  | ORD/000644/2021-2022 | 185/MD | 01/02/2022 | 31/07/2022 | GOBINDA MAITY | 177.73 | 33.3 | 18.74 | 0
251 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Midnapore Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Jhargram_2_3 under Jhargram Division in the District of Jhargram. |  |  | ORD/000655/2021-2022 | 196/MD | 01/02/2022 | 31/07/2022 | SUNIL DULE | 134.69 | 32.54 | 24.16 | 1
252 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Midnapore Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Jhargram_2_1 under Jhargram Division in the District of Jhargram. |  |  | ORD/000654/2021-2022 | 195/MD | 01/02/2022 | 31/07/2022 | KISHORE GHOSH | 133.21 | 24.88 | 18.68 | 0
253 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Midnapore Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Nayagram_1_7 under Jhargram Division in the District of Jhargram. |  |  | ORD/000652/2021-2022 | 193/MD | 01/02/2022 | 31/07/2022 | DIPAK KUMAR BAKLY | 108.29 | 0 | 0 | 0
254 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Midnapore Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Nayagram_4_15 under Jhargram Division in the District of Jhargram. |  |  | ORD/000646/2021-2022 | 187/MD | 01/02/2022 | 31/07/2022 | GOBINDA MAITY | 177.7 | 25.53 | 14.36 | 1
255 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Midnapore Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Material Requisition To Resource Division |  |  | RTOR000007/2022-2023 | 1851/MD | 07/09/2022 | 07/09/2022 | Resource Division | 30.75 | 0 | 0 | 0
256 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Midnapore Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Material Requisition To Resource Division |  |  | RTOR000008/2022-2023 | 1868/MD | 08/09/2022 | 08/09/2022 | Resource Division | 30.75 | 0 | 0 | 0
257 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Material Requisition To Resource Division |  |  | RTOR000112/2023-2024 | 963-JHD | 23/06/2023 | 23/06/2023 | Resource Division | 142.21 | 0 | 0 | 0
258 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | New service connection charges. |  |  | BILL/00047/2022-2023 | 8/JMD//PFMS/JAN | 11/01/2023 | 11/01/2023 | WBSEDCL | 2.5 | 0 | 0 | 0
259 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | New service connection charges. |  |  | BILL/00027/2022-2023 | 27/JMD/PFMS/DEC | 20/12/2022 | 20/12/2022 | WBSEDCL | 0.21 | 0 | 0 | 0
260 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Charges for WBSEDCL new service connection. |  |  | BILL/00007/2022-2023 | 7/JMD/PFMS/DEC | 07/12/2022 | 07/12/2022 | WBSEDCL | 3.54 | 0 | 0 | 0
261 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | WBSEDCL payment for new service connection |  |  | BILL/00039/2022-2023 | 39/JMD/PFMS/DEC | 29/12/2022 | 29/12/2022 | WBSEDCL | 19.57 | 0 | 0 | 0
262 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Fuel & Lubricant bill for supporting truck & Departmental Rig. Units for construction of Rig Bore tube wells under 269 mini scheme at different block of Jhargram district under P.H.E. Dte. (Scheme code:- SM/09915) |  |  | BILL/00160/2022-2023 | BP-2022-23-155 | 01/03/2023 | 01/03/2023 | SURAJ SERVICE STATION | 24 | 0 | 0 | 0
263 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Midnapore Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Transfer to EE/JSD, PHE Dte. ( Standalone PWSS) |  |  | BILL/00612/2022-2023 |  | 20/12/2022 | 20/12/2022 | EXECUTIVE ENGINEER, JHARGRAM CIVIL DIVISION, PHE DTE. | 102.67 | 0 | 0 | 0
264 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Midnapore Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Transfer to EE/JSD, PHE Dte. ( Standalone PWSS) |  |  | BILL/00667/2022-2023 | BP-2022-23-465 | 24/12/2022 | 24/12/2022 | EXECUTIVE ENGINEER, JHARGRAM CIVIL DIVISION, PHE DTE. | 94.84 | 0 | 0 | 0
265 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Fuel and lubricant bill for Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Salika and others mouza of Jamboni and others blocks under stand alone piped water supply scheme (SM/09915) of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. |  |  | BILL/00317/2023-2024 | BP-2023-24-195B | 15/09/2023 | 15/09/2023 | SURAJ SERVICE STATION | 1.1 | 0 | 0 | 0
266 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | For new service connection charges for Goyaldanga, t/w-II w/s scheme. |  |  | BILL/00006/2022-2023 | 6/JMD/PFMS/DEC | 01/12/2022 | 01/12/2022 | WBSEDCL | 0.21 | 0 | 0 | 0
267 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | New service connection charges |  |  | BILL/00264/2022-2023 | 15/JMD/PFMS/MAR | 06/03/2023 | 06/03/2023 | WBSEDCL | 1.46 | 0 | 0 | 0
268 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing Fuel & Lubricants for construction of RBTW under 269 Stand Alone mini PWSS. |  |  | BILL/00048/2022-2023 | BP-2022-23-81 | 17/12/2022 | 17/12/2022 | SURAJ SERVICE STATION | 14.34 | 0 | 0 | 0
269 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Fuel and lubricant bill for Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Tukurya and others mouza of Jamboni and others blocks under stand alone piped water supply scheme (SM/09915) of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. |  |  | BILL/00319/2023-2024 | BP-2023-24-204 | 24/09/2023 | 24/09/2023 | SURAJ SERVICE STATION | 9.93 | 0 | 0 | 0
270 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Fuel & Lubricant bill for Supply & delivery of upvc consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary / Combination Method at Dhengabahara, Tube Well no.-II and others under Jamboni and other Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. |  |  | BILL/00559/2023-2024 | BP-2023-24-286 | 08/11/2023 | 08/11/2023 | SURAJ SERVICE STATION | 6.39 | 0 | 0 | 0
271 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Fuel & Lubricant bill for supporting truck & Departmental Rig. Units for construction of Rig Bore tube wells under 269 mini scheme at different block of Jhargram district under P.H.E. Dte. (Scheme code:- SM/09915) |  |  | BILL/00192/2022-2023 | BP-2022-23-204 | 30/03/2023 | 30/03/2023 | SURAJ SERVICE STATION | 8.68 | 0 | 0 | 0
272 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | New service connection charges under 269 mini pwss (Scheme code:- SM/09915) |  |  | BILL/00280/2022-2023 | 16/JMD/PFMS/MAR | 06/03/2023 | 06/03/2023 | WBSEDCL | 3.15 | 0 | 0 | 0
273 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | New service connection |  |  | BILL/00387/2023-2024 | 22/AUG | 25/08/2023 | 25/08/2023 | WBSEDCL | 0.21 | 0 | 0 | 0
274 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | New service connection. |  |  | BILL/00627/2023-2024 | 10/JMD | 11/10/2023 | 11/10/2023 | WBSEDCL | 0.21 | 0 | 0 | 0
275 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing PVC pipes and fittings for sinking of tube wells under Stand Alone Piped water supply scheme (SM/09915). |  |  | BILL/00563/2023-2024 | BP-2023-24-294 | 17/11/2023 | 17/11/2023 | DURGAPUR POLYMERS PVT. LTD. | 4.89 | 0 | 0 | 0
276 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | New service connection charges. |  |  | BILL/00058/2022-2023 | 17JMD//PFMS/JAN | 20/01/2023 | 20/01/2023 | WBSEDCL | 0.21 | 0 | 0 | 0
277 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | New service connection charges. |  |  | BILL/00013/2022-2023 | 13/JMD/PFMS/DEC | 17/12/2022 | 17/12/2022 | WBSEDCL | 0.62 | 0 | 0 | 0
278 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Fuel and lubricant bill for Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Dhadka and others mouza of Jamboni and others blocks block under stand alone piped water supply scheme (SM/09915) of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. |  |  | BILL/00283/2023-2024 | BP-2023-24-195 | 12/09/2023 | 12/09/2023 | SURAJ SERVICE STATION | 4.5 | 0 | 0 | 0
279 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Midnapore Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Sankrail_3_1 under Jhargram Division in the District of Jhargram. |  |  | ORD/000057/2022-2023 | 877/MD | 10/05/2022 | 06/11/2022 | EFFLUENT AND WATER TREATMENT ENGINEERS PVT. LTD. | 150.3 | 0 | 0 | 99
280 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply delivery of CIDF S/V for the work of Stand Alone Water Supply Scheme (269 nos.) at Bara Negui and Kharikamathani GP of Nayagram Block area under Jhargram Sub Division within Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer Nayagram block | ORD/000022/2022-2023 | 350/JSD | 12/07/2022 | 27/07/2022 | GOBINDA MAITY | 4.8 | 4.8 | 100 | 100
281 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Logistic and other support activities for training in 08 (eight) Blocks of Jhargram District for Skilling of Manpower to Generate Employment Opportunities and to Support Implementation of Jal Jeevan Mission under Jhargram Division P.H.E Dte. (1st Phase) | Assistant Engineer Headquarter | Junior Engineer | ORD/000047/2022-2023 | 168/JHD | 05/08/2022 | 01/02/2023 | J.S.S. ENTERPRISE | 4.94 | 1.49 | 30.16 | 100
282 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Nayagram_4_5 under Jhargram Division in the District of Jhargram. | Assistant Engineer | Junior Engineer-II | ORD/000105/2021-2022 | 185/MD | 01/02/2022 | 28/02/2026 | GOBINDA MAITY | 177.73 | 72.69 | 40.9 | 100
283 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Nayagram_4_15 under Jhargram Division in the District of Jhargram. | Assistant Engineer | Junior Engineer-II | ORD/000106/2021-2022 | 187/MD | 01/02/2022 | 28/02/2026 | GOBINDA MAITY | 177.7 | 60.36 | 33.97 | 20
284 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Nayagram_1_9 under Jhargram Division in the District of Jhargram. | Assistant Engineer | Junior Engineer Nayagram block | ORD/000092/2021-2022 | 284/MD | 15/02/2022 | 14/08/2022 | SRIMANTA KUMAR DE | 72.19 | 65.54 | 90.79 | 70
285 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Binpur-I_1_4 under Jhargram Division in the District of Jhargram. | Assistant Engineer | Junior Engineer Binpur-I block | ORD/000003/2021-2022 | 283/MD | 15/02/2022 | 14/08/2022 | M/S. D.K.H.CONSTRUCTION | 72.23 | 68.62 | 95.01 | 90
286 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Amlasol T/W no. -I & II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000517/2022-2023 | 3065/JMD | 28/09/2022 | 26/01/2023 | P.K. ENGINEERING | 6.79 | 6.09 | 89.72 | 0
287 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Salika Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000659/2022-2023 | 4198/JMD | 28/12/2022 | 27/04/2023 | DIPALI CONSTRUCTION | 5.78 | 5.16 | 89.39 | 80
288 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Nargi Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000661/2022-2023 | 4200/JMD | 28/12/2022 | 27/04/2023 | A. G. ENTERPRISE | 5.77 | 0 | 0 | 75
289 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply,delivery, installation, commisioning & trial run of submersible pumping machinary and other Electro Mechanical accessories for Chandabila Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000655/2022-2023 | 4194/JMD | 28/12/2022 | 27/04/2023 | BINAPANI ENTERPRISE | 5.78 | 5.04 | 87.09 | 80
290 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Khanderpara T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000551/2022-2023 | 3098/JMD | 28/09/2022 | 26/01/2023 | SANJIB SAHA | 5.72 | 4.79 | 83.8 | 90
291 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Nayagram_4_14 under Jhargram Division in the District of Jhargram. | Assistant Engineer | Junior Engineer-II | ORD/000110/2021-2022 | 186/MD | 01/02/2022 | 28/02/2026 | GOBINDA MAITY | 177.71 | 89.01 | 50.09 | 67
292 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Nayagram_4_10 under Jhargram Division in the District of Jhargram. | Assistant Engineer | Junior Engineer Nayagram block,Junior Engineer-III | ORD/000111/2021-2022 | 305/MD | 16/02/2022 | 15/08/2022 | ODISSI INNOVATIONS ENGINEERS PRIVATE LIMITED | 177.75 | 90.8 | 51.08 | 51
293 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Jhargram_2_2 under Jhargram Division in the District of Jhargram. | Assistant Engineer Headquarter | Junior Engineer Jhargram Dev. Block | ORD/000010/2021-2022 | 302/MD | 15/02/2022 | 14/08/2022 | LALIT BIHARI MAITY | 132.67 | 102.88 | 77.54 | 100
294 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Jamboni_1_1 under Jhargram Division in the District of Jhargram. | Assistant Engineer | Junior Engineer-II | ORD/000112/2021-2022 | 188/MD | 01/02/2022 | 28/09/2025 | SUNIL DULE | 108 | 59.06 | 54.69 | 85
295 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Jhargram_2_4_C under Jhargram Division in the District of Jhargram. | Assistant Engineer Headquarter | Junior Engineer Jhargram Dev. Block | ORD/000052/2022-2023 | 276/JHD | 13/09/2022 | 11/01/2023 | DHUMKETU ENGINEERING PRIVATE LIMITED | 20.52 | 19.34 | 94.24 | 100
296 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bam Diha T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | Junior Engineer | ORD/000534/2022-2023 | 3078/JMD | 28/09/2022 | 26/01/2023 | BIJAN ENTERPRISE | 5.7 | 3.78 | 66.28 | 80
297 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Nayagram_1_7 under Jhargram Division in the District of Jhargram. | Assistant Engineer | Junior Engineer Nayagram block | ORD/000006/2021-2022 | 193/MD | 01/02/2022 | 31/07/2022 | DIPAK KUMAR BAKLY | 108.29 | 73.75 | 68.11 | 95
298 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Binpur-I_1_3 under Jhargram Division in the District of Jhargram. | Assistant Engineer | Junior Engineer Binpur-I block | ORD/000143/2021-2022 | 292/MD | 15/02/2022 | 14/08/2022 | BIDYUT KUMAR SANTRA | 89.66 | 66.78 | 74.49 | 90
299 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Gopiballavpur-I_4_2 under Jhargram Division in the District of Jhargram. | Assistant Engineer | Junior Engineer Gopiballavpur-I block | ORD/000134/2021-2022 | 217/MD | 03/02/2022 | 02/08/2022 | MAHAVIR PUMPS MFG. PVT. LTD. | 118.44 | 46.17 | 38.98 | 30
300 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Binpur-I_3_2 under Jhargram Division in the District of Jhargram. | Assistant Engineer | Junior Engineer Binpur-I block | ORD/000138/2021-2022 | 197/MD | 01/02/2022 | 31/07/2022 | MAHAVIR PUMPS MFG. PVT. LTD. | 100.58 | 31.91 | 31.72 | 40
301 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Jamboni_1_2 under Jhargram Division in the District of Jhargram. | Assistant Engineer | Junior Engineer-I | ORD/000144/2021-2022 | 424/MD | 04/03/2022 | 31/08/2022 | MIDNAPUR PIPE CONCERN | 104.95 | 62.69 | 59.74 | 50
302 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bali Muri Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Driller-In-Charge | Junior Engineer | ORD/000714/2022-2023 | 264/JMD | 03/02/2023 | 03/06/2023 | P.K. ENGINEERING | 5.78 | 4.15 | 71.76 | 80
303 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Binpur-II_1_1 under Jhargram Division in the District of Jhargram. | Assistant Engineer | Junior Engineer-II | ORD/000133/2021-2022 | 299/MD | 15/02/2022 | 14/08/2022 | SAIKAT DANDAPAT | 100.15 | 71.88 | 71.78 | 100
304 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Hanri Bhanga stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Driller-In-Charge | Junior Engineer | ORD/000743/2022-2023 | 3504/JMD | 29/11/2022 | 06/12/2022 | PRANAB KUMAR DAS | 0.07 | 0 | 0 | 0
305 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Binpur-II_3_1 under Jhargram Division in the District of Jhargram. | Assistant Engineer | Junior Engineer-II | ORD/000145/2021-2022 | 198/MD | 01/02/2022 | 31/07/2022 | FIDERE MARINE SERVICES PVT. LTD. | 161 | 29.7 | 18.45 | 80
306 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Phul Berya stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000703/2022-2023 | 3538/JMD | 29/11/2022 | 06/12/2022 | DEB KUMAR BASU | 0.07 | 0 | 0 | 100
307 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bachhur Khoyar (Bardanga) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Driller-In-Charge | Junior Engineer | ORD/000735/2022-2023 | 3488/JMD | 29/11/2022 | 06/12/2022 | SUJOY RANJAN BHOWMICK | 0.07 | 0 | 0 | 0
308 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dhulaburari T/W no. I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Driller-In-Charge | JE (M) | ORD/000736/2022-2023 | 3529/JMD | 29/11/2022 | 06/12/2022 | SUJOY RANJAN BHOWMICK | 0.07 | 0 | 0 | 0
309 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Binpur-I_1_1 under Jhargram Division in the District of Jhargram. | Assistant Engineer | Junior Engineer Binpur-I block | ORD/000119/2021-2022 | 291/MD | 15/02/2022 | 14/08/2022 | NIRMAL DUTTA | 89.46 | 62.7 | 70.08 | 80
310 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Maubhandar, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Driller-In-Charge | JE (M),Junior Engineer | ORD/000731/2022-2023 | 462/JMD | 09/03/2023 | 07/07/2023 | DEY ENTERPRISE | 5.78 | 3.92 | 67.85 | 100
311 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Paika T/W no. I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Driller-In-Charge | Junior Engineer | ORD/000738/2022-2023 | 3487/JMD | 29/11/2022 | 06/12/2022 | DEBJYOTI BASU | 0.07 | 0 | 0 | 0
312 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kankrajhor T/W no. -I & II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Driller-In-Charge | Junior Engineer | ORD/000742/2022-2023 | 3446/JMD | 29/11/2022 | 06/12/2022 | DEBJYOTI BASU | 0.07 | 0 | 0 | 0
313 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Nayagram_1_4 under Jhargram Division in the District of Jhargram. | Assistant Engineer | Junior Engineer, Jhargram Sub-Division,Junior Engineer-III | ORD/000147/2021-2022 | 191/MD | 01/02/2022 | 31/07/2022 | FIDERE MARINE SERVICES PVT. LTD. | 107.15 | 42.16 | 39.35 | 100
314 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Baksa Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Driller-In-Charge | Junior Engineer | ORD/000759/2022-2023 | 665/JMD | 24/03/2023 | 22/07/2023 | MENAKA ENTERPRISE | 5.78 | 5.16 | 89.33 | 95
315 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Totasai, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000755/2022-2023 | 661/JMD | 24/03/2023 | 03/01/2024 | AMIT DAS | 5.77 | 3.78 | 65.51 | 70
316 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Thuria, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000014/2023-2024 | 962/JMD | 25/04/2023 | 23/08/2023 | A.S. ENGINEERING | 5.78 | 3.78 | 65.43 | 90
317 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Nayagram_1_3 under Jhargram Division in the District of Jhargram. | Assistant Engineer | Junior Engineer-II | ORD/000151/2021-2022 | 300/MD | 15/02/2022 | 09/02/2025 | ASIS KUMAR SARANGI | 108.29 | 44.45 | 41.05 | 50
318 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Ramkrishnapur, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000017/2023-2024 | 965/JMD | 25/04/2023 | 23/08/2023 | SUBHASIS ROY | 5.77 | 4.96 | 85.95 | 95
319 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Thuria, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000013/2023-2024 | 961/JMD | 25/04/2023 | 23/08/2023 | GOENKA ENTERPRISE | 5.78 | 4.01 | 69.32 | 90
320 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kadam Diha, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000016/2023-2024 | 964/JMD | 25/04/2023 | 23/08/2023 | TAPAN BISWAS | 5.77 | 5.1 | 88.37 | 95
321 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, Delivery & fitting fixing of fast moving spares (Air filter, ELGI Air lube plus) for preventive maintenance of compressor unit (Model:- 600-200, Make:- ELGI) attached with DR/DTH -500 (make:- KLR) rig unit under MMSD(D) under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000785/2022-2023 | 363/JMD | 23/02/2023 | 02/03/2023 | B. P. TRADING CORPORATION | 0.82 | 0 | 0 | 0
322 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Jamboni_3_1 under Jhargram Division in the District of Jhargram. | Assistant Engineer | Junior Engineer, Jhargram Division | ORD/000152/2021-2022 | 426/MD | 04/03/2022 | 13/02/2026 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 125.73 | 16.51 | 13.14 | 14
323 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Jamboni_3_2 under Jhargram Division in the District of Jhargram. | Assistant Engineer | Junior Engineer, Jhargram Division | ORD/000153/2021-2022 | 427/MD | 04/03/2022 | 13/02/2026 | JDJ ENTERPRISE (A UNIT OF JDJ TRADERS PRIVATE LIMITED) | 100.58 | 22.72 | 22.59 | 25
324 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Nayagram_4_13 under Jhargram Division in the District of Jhargram. | Assistant Engineer | Junior Engineer Nayagram block,Junior Engineer-II | ORD/000154/2021-2022 | 431/MD | 04/03/2022 | 10/08/2026 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 177.59 | 23.19 | 13.06 | 40
325 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kankrajhor T/W no. -IV Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Driller-In-Charge | JE (M),Junior Engineer | ORD/000095/2023-2024 | 1711/JMD | 13/07/2023 | 09/01/2024 | MASSK ENGINEERING WORKS | 5.98 | 5.26 | 88.01 | 100
326 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Gohalberya T/W no. -I & II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000083/2023-2024 | 1706/JMD | 13/07/2023 | 09/01/2024 | DEBJYOTI BASU | 6.89 | 6.84 | 99.23 | 100
327 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Nischintapur T/W no. -I & II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Driller-In-Charge | Junior Engineer | ORD/000086/2023-2024 | 1709/JMD | 13/07/2023 | 09/01/2024 | M/S. EMMESS | 6.89 | 2.94 | 42.7 | 80
328 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Rajpahari Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000102/2023-2024 | 1762/JMD | 19/07/2023 | 16/11/2023 | ASHOKE ADHIKARY | 5.76 | 5.08 | 88.17 | 95
329 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Damodarpur Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000103/2023-2024 | 1763/JMD | 19/07/2023 | 16/11/2023 | RS ELECTROMECHANICAL CORPORATION | 5.78 | 3.78 | 65.38 | 90
330 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Panisol Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Driller-In-Charge | JE (M),Junior Engineer | ORD/000098/2023-2024 | 1758/JMD | 19/07/2023 | 16/11/2023 | K.S.P. ENTERPRISE | 5.74 | 3.89 | 67.85 | 75
331 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Rai Gani, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000099/2023-2024 | 1759/JMD | 19/07/2023 | 16/11/2023 | DEBJYOTI BASU | 5.77 | 5.1 | 88.45 | 92
332 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dumaria Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Driller-In-Charge | Junior Engineer | ORD/000101/2023-2024 | 1761/JMD | 19/07/2023 | 16/11/2023 | S. PATHAK & CO. | 5.76 | 5.18 | 89.96 | 95
333 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Tikra Para Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Driller-In-Charge | Junior Engineer | ORD/000129/2023-2024 | 1821/JMD | 24/07/2023 | 21/11/2023 | JIBON GHOSH | 5.78 | 3.78 | 65.43 | 80
334 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Pathar Bandh, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Driller-In-Charge | Junior Engineer | ORD/000131/2023-2024 | 1823/JMD | 24/07/2023 | 21/11/2023 | CHAKRABORTY MINING & ENGINEERING | 5.77 | 5.11 | 88.54 | 100
335 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Pathar Bandh, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Driller-In-Charge | JE (M),Junior Engineer | ORD/000130/2023-2024 | 1822/JMD | 24/07/2023 | 14/03/2025 | ECO ENTERPRISE | 5.77 | 0 | 0 | 80
336 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Tiyakati, Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Driller-In-Charge | Junior Engineer | ORD/000159/2023-2024 | 1970/JMD | 31/07/2023 | 28/11/2023 | SUBHAM ENTERPRISE | 5.78 | 2.76 | 47.65 | 60
337 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Jadabpur Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Driller-In-Charge | Junior Engineer | ORD/000121/2023-2024 | 1803/JMD | 24/07/2023 | 21/11/2023 | PADMA ENGINEERING CO. | 5.78 | 3.78 | 65.43 | 80
338 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Malam, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000128/2023-2024 | 1820/JMD | 24/07/2023 | 21/11/2023 | ABHIJIT BASU | 5.78 | 4.15 | 71.76 | 70
339 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Khas Jangal (G.P. - Malam) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000163/2023-2024 | 1974/JMD | 31/07/2023 | 28/11/2023 | J.K. ENGINEERING CO. | 5.78 | 3.91 | 67.59 | 90
340 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution pipeline with Community Tank & provision of FHTC for drought like situation situation prone area at different location under location ID Binpur_I_1_2 under Jhargram Division, in the district of Jhargram. | Assistant Engineer | Junior Engineer Binpur-I block | ORD/000263/2022-2023 | 868/MD | 10/05/2022 | 06/11/2022 | SUBRATA DAS | 89.83 | 29.82 | 33.19 | 40
341 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Arra, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Driller-In-Charge | Junior Engineer | ORD/000137/2023-2024 | 1829/JMD | 24/07/2023 | 21/11/2023 | SRI KRISHNA NIRMAN | 5.78 | 5.04 | 87.21 | 80
342 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Gokhur Pal Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Driller-In-Charge | Junior Engineer | ORD/000116/2023-2024 | 1797/JMD | 24/07/2023 | 21/11/2023 | BUSR ENGINEERING | 5.77 | 5.15 | 89.17 | 95
343 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kalma Pukhuria, Tube Well no.-IV Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Driller-In-Charge | Junior Engineer | ORD/000124/2023-2024 | 1806/JMD | 24/07/2023 | 21/11/2023 | M/S. EMMESS | 5.78 | 3.78 | 65.4 | 90
344 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kalma Pukhuria, Tube Well no.-V Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer | ORD/000125/2023-2024 | 1807/JMD | 24/07/2023 | 21/11/2023 | SOUMEN ELECTRIC | 5.78 | 5.2 | 90.1 | 100
345 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply & delivery of upvc consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary / Combination Method at Kuldiha under Jamboni Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | Assistant Engineer,Driller-In-Charge | JE (M),Junior Engineer | ORD/000219/2023-2024 | 2286/JMD | 10/08/2023 | 01/01/2025 | CHAKRABORTY MINING & ENGINEERING | 3.37 | 0 | 0 | 100
346 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of 1(One) Nos. 150 mm X 100 mm X 135 Mtr. RBTW, for lowering of Submersible Pumping Machinery at Kamapukuria - IV Village Stand Alone PWSS for Nayagram Block under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-III | ORD/000110/2023-2024 | 662/JSD | 20/07/2023 | 19/08/2023 | GOUTAM KUMAR BOSE | 4.26 | 0 | 0 | 100
347 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Gohalberya mouza, tube well no.3 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M),Junior Engineer | ORD/000912/2021-2022 | 122/JMD | 31/01/2022 | 01/03/2025 | DEBJYOTI BASU | 0.15 | 0 | 0 | 100
348 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Gohalberya mouza, tube well no.4 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M),Junior Engineer | ORD/000913/2021-2022 | 123/JMD | 31/01/2022 | 14/12/2024 | DEBJYOTI BASU | 0.71 | 0 | 0 | 100
349 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Gohalberya mouza, tube well no.3 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M),Junior Engineer | ORD/000911/2021-2022 | 121/JMD | 31/01/2022 | 01/03/2025 | DEBJYOTI BASU | 0.71 | 0 | 0 | 100
350 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Gohalberya mouza, tube well no.4 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M),Junior Engineer | ORD/000914/2021-2022 | 124/JMD | 31/01/2022 | 24/03/2025 | DEBJYOTI BASU | 0.15 | 0 | 0 | 100
351 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Nischintapur mouza, tube well no.2 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M),Junior Engineer | ORD/000949/2021-2022 | 127/JMD | 31/01/2022 | 01/03/2025 | DEBJYOTI BASU | 0.71 | 0 | 0 | 100
352 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Nischintapur mouza, tube well no.2 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | Junior Engineer | ORD/000945/2021-2022 | 128/JMD | 31/01/2022 | 01/03/2025 | DEBJYOTI BASU | 0.16 | 0 | 0 | 100
353 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Hiring of 1 (one) no Motor Cab (standard) Commercial with Catalytic Converter attachment with Bharat Stage as per prevalent applicable standard compliant new not older than 30 thirty) months from the date of 1st registration on daily hire rate basis for 04 (Four) months only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Assistant Engineer, Jhargram Sub-Division, PHE Dte. (from 01.05.2023 to 31.08.2023). | Assistant Engineer | Junior Engineer, Jhargram Division,Junior Engineer-III | ORD/000354/2023-2024 | 318/JSD | 26/04/2023 | 26/08/2023 | BIDYUT KUMAR SANTRA | 0.69 | 1.53 | 222.1 | 100
354 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Hiring of 1 (one) no, Motor Cab (standard) Commercial with Catalytic Converter attachment with Bharat Stage as per prevalent applicable standard compliant new /not older than 30 (thirty) months from the date of Ist registration on daily hire rate basis for 6 (Six) months [from 01.08.2023 to 31.01.2024] only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Assistant Engineer, Jhargram H.Q./RWS/Gopiballavpur Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000364/2023-2024 | 680/JSD | 27/07/2023 | 27/01/2024 | JAGOMOHAN SETUA | 0.98 | 2.18 | 222.56 | 100
355 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Continuation work order for Providing one no. 10 MT capacity truck & one no 32 BHP Capacity Tractor along with licensed driver on daily basis for Rig unit no. 41D/LMP/500 of MMSD(D) under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | Junior Engineer | ORD/000923/2022-2023 | 716/JMD | 28/03/2023 | 17/04/2023 | M/S. SAMRIDDHI ENTERPRISE | 0.97 | 0 | 0 | 0
356 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Logistic and other support activities for training in 08 (eight) Blocks of Jhargram District for Skilling of Manpower to Generate Employment Opportunities and to Support Implementation of Jal Jeevan Mission under Jhargram Division P.H.E Dte. (2nd Phase) | Assistant Engineer | Junior Engineer-II | ORD/000444/2023-2024 | 1367/JHD | 14/08/2023 | 09/10/2023 | J.S.S. ENTERPRISE | 4.3 | 0 | 0 | 100
357 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | "Hire charges of Bharat Stage-II / III Diesel Motor Cabs (Luxury Taxi) / Maruti Omni (Standard-Non-Air Conditioned) having Contract Carriage Permit from the Regional Transport Authority for the Office of the Executive Engineer, Jhargram Division, PHE Dte. for the period of 2 (Two) Month's, from 01.05.2023 to 30.06.2023. | Assistant Engineer | Junior Engineer-II | ORD/000450/2023-2024 | 319/JSD | 27/04/2023 | 27/06/2023 | SUNIL DULE | 0.29 | 0.77 | 265.36 | 100
358 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Installation of Iron Elimination Plant including PCC Concrete Platform at Maju Gora Stand Alone PWSS of Binpir-II Block under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000213/2024-2025 | 2291/JHD | 04/12/2024 | 02/02/2025 | TREATAQUA | 7.1 | 0 | 0 | 0
359 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Hiring of 1 (one) no, Motor Cab (standard) Commercial with Catalytic Converter attachment with Bharat Stage as per prevalent applicable standard compliant new /not older than 30 (thirty) months from the date of 1st registration on daily hire rate basis for 02 (Two) months only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Assistant Engineer, Jhargram H.Q./ RWS /Gopiballavpur Sub- Division PHE Dte.(from 01.05.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer-II | ORD/000040/2024-2025 | 507/JSD | 30/04/2024 | 30/06/2024 | JAGOMOHAN SETUA | 0.32 | 0.76 | 233 | 100
360 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Balance FHTC Work of Augmentation of Khamar Piped Water Supply Scheme in Binpur-II Block within Jhargram District under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000571/2023-2024 | 209/JSD | 13/03/2024 | 03/04/2024 | SAIKAT DANDAPAT | 1.32 | 0 | 0 | 0
361 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Bhararu mouza of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Driller-In-Charge | Junior Engineer | ORD/000975/2021-2022 | 542/JMD | 23/12/2021 | 27/12/2021 | DEBJYOTI BASU | 0.33 | 0 | 0 | 0
362 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under Binpur-II Block location Id Binpur-II_3_2_C under Jhargram Division in the District of Jhargram. | Assistant Engineer | Junior Engineer RWS, Binpur-II Devlopment Block. | ORD/000573/2023-2024 | 445/JHD | 14/03/2024 | 13/05/2024 | KOUSIK MONDAL | 19.87 | 0 | 0 | 20
363 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Hudhudi T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000958/2022-2023 | 3518/JMD | 29/11/2022 | 06/12/2022 | RMD TRADING | 0.07 | 0 | 0 | 0
364 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under Jamboni Block location Id Jamboni_4_1 under Jhargram Division in the District of Jhargram. 3rd Call (Ref: 1st Call eNIT_39 of 2022-23, SL No.-1, 2nd Call eNIT_11 of EE/JHD of 2023-24, SL No.-13) | Assistant Engineer | Junior Engineer-III | ORD/000127/2024-2025 | 1133/JHD | 06/08/2024 | 05/10/2024 | RUPKUMAR KARMAKAR | 19.2 | 0 | 0 | 0
365 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Sankisol stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000182/2022-2023 | 1587/JMD | 27/07/2022 | 24/11/2022 | DEB KUMAR BASU | 6.86 | 6.83 | 99.51 | 100
366 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Sonamui stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000184/2022-2023 | 1589/JMD | 27/07/2022 | 24/11/2022 | P.K. ENGINEERING | 6.86 | 6.31 | 91.91 | 10
367 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Purna Pani stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000185/2022-2023 | 1590/JMD | 27/07/2022 | 24/11/2022 | SUBHASIS ROY | 6.86 | 6.85 | 99.79 | 100
368 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Baghjhapa stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000186/2022-2023 | 1591/JMD | 27/07/2022 | 24/11/2022 | M/S. SAMRIDDHI ENTERPRISE | 7.02 | 7.01 | 99.82 | 100
369 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Narcha stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer | JE (M) | ORD/000137/2022-2023 | 1411/JMD | 14/07/2022 | 11/11/2022 | ABHIJIT BASU | 6.86 | 6.85 | 99.74 | 50
370 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Nischinta stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000168/2022-2023 | 1468/JMD | 19/07/2022 | 16/11/2022 | S.S. GHORAI | 6.86 | 6.81 | 99.18 | 100
371 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Nischinta stand alone piped water supply scheme, tube well no.-II of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000169/2022-2023 | 1469/JMD | 19/07/2022 | 16/11/2022 | RITESH ENTERPRISE | 6.89 | 6.34 | 91.96 | 95
372 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Paschim Gholai stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000173/2022-2023 | 1473/JMD | 19/07/2022 | 16/11/2022 | M/S. NABIN GOPAL SENGUPTA | 6.87 | 6.79 | 98.81 | 100
373 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Tungadhua stand alone piped water supply scheme, tube well no.-II of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000167/2022-2023 | 1467/JMD | 19/07/2022 | 16/11/2022 | DEY ENTERPRISE | 6.79 | 6.25 | 91.95 | 95
374 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Sri Ram Pur stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000162/2022-2023 | 1462/JMD | 19/07/2022 | 16/11/2022 | MENAKA ENTERPRISE | 6.87 | 6.85 | 99.74 | 100
375 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Damujana stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000143/2022-2023 | 1417/JMD | 14/07/2022 | 11/11/2022 | SUBHASIS ROY | 6.87 | 6.84 | 99.62 | 100
376 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Goal Danga stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000144/2022-2023 | 1418/JMD | 14/07/2022 | 11/11/2022 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 7.02 | 7.02 | 100 | 100
377 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Jarkasol stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000147/2022-2023 | 1452/JMD | 19/07/2022 | 16/11/2022 | BUSR ENGINEERING | 6.86 | 6.83 | 99.48 | 100
378 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Rai Sol stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000152/2022-2023 | 1457/JMD | 19/07/2022 | 16/11/2022 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 6.87 | 6.84 | 99.58 | 100
379 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Phul Berya stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000148/2022-2023 | 1453/JMD | 19/07/2022 | 16/11/2022 | DEB KUMAR BASU | 6.86 | 6.83 | 99.47 | 100
380 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Chanda Bila stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000135/2022-2023 | 1409/JMD | 14/07/2022 | 11/11/2022 | DEBJYOTI BASU | 6.84 | 6.83 | 99.74 | 85
381 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Madhabpur stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000136/2022-2023 | 1410/JMD | 14/07/2022 | 11/11/2022 | SUJOY RANJAN BHOWMICK | 6.86 | 5.56 | 81.06 | 95
382 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Bankra stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000149/2022-2023 | 1454/JMD | 19/07/2022 | 16/11/2022 | MONORANJAN DEY | 6.86 | 5.04 | 73.42 | 10
383 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Garra stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000138/2022-2023 | 1412/JMD | 14/07/2022 | 11/11/2022 | DEBJYOTI BASU | 6.84 | 4.05 | 59.15 | 98
384 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Bhadai stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000151/2022-2023 | 1456/JMD | 19/07/2022 | 16/11/2022 | P.K. ENGINEERING | 6.86 | 6.83 | 99.47 | 100
385 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Kumarbandh stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000139/2022-2023 | 1413/JMD | 14/07/2022 | 11/11/2022 | BHABANI PRASAD MANNA | 6.86 | 4.79 | 69.82 | 95
386 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Tungadhua stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000166/2022-2023 | 1466/JMD | 19/07/2022 | 16/11/2022 | T.N. BANERJEE | 6.86 | 6.81 | 99.27 | 100
387 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Shutpipal stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000261/2022-2023 | 1728/JMD | 17/08/2022 | 15/12/2022 | DEBJYOTI BASU | 6.84 | 6.82 | 99.68 | 100
388 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Kargonala stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000262/2022-2023 | 1729/JMD | 17/08/2022 | 15/12/2022 | ECO ENTERPRISE | 6.87 | 6.85 | 99.76 | 100
389 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Bag Doba stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000263/2022-2023 | 1730/JMD | 17/08/2022 | 15/12/2022 | SHOVAN KUMAR DAS | 6.87 | 6.84 | 99.62 | 100
390 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Jhaurishol stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000270/2022-2023 | 1737/JMD | 17/08/2022 | 15/12/2022 | S.K. ENTERPRISE | 6.85 | 6.83 | 99.57 | 100
391 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Chilkigar stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000183/2022-2023 | 1588/JMD | 27/07/2022 | 24/11/2022 | DIPALI CONSTRUCTION | 6.79 | 6.77 | 99.62 | 95
392 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Bhurkundi stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000187/2022-2023 | 1592/JMD | 27/07/2022 | 24/11/2022 | M/S. SAJAHAN CHOWDHURY | 6.82 | 6.77 | 99.3 | 100
393 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Jamda Hara stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000269/2022-2023 | 1736/JMD | 17/08/2022 | 15/12/2022 | MASSK ENGINEERING WORKS | 6.86 | 6.84 | 99.64 | 100
394 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply delivery of CIDF S/V for the work of Stand Alone Water Supply Scheme (269 nos.) at Arrah and Malam GP of Nayagram Block area under Jhargram Sub Division within Jhargram Division, PHE Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division,Junior Engineer-II | ORD/000040/2022-2023 | 46/GPSD | 29/08/2022 | 13/09/2022 | MAKALI ENGG. CORPORATION | 4.8 | 0 | 0 | 100
395 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply delivery of CIDF S/V for the work of Stand Alone Water Supply Scheme (269 nos.) for Jhargram & Gopiballavpur-II Block area under Jhargram Sub Division within Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000025/2022-2023 | 355/JSD | 15/07/2022 | 30/07/2022 | MAKALI ENGG. CORPORATION | 4.8 | 0 | 0 | 100
396 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Kalma Pukhuria stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000264/2022-2023 | 1731/JMD | 17/08/2022 | 15/12/2022 | S.S. GHORAI | 6.86 | 6.84 | 99.62 | 100
397 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Bara Khankri stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000265/2022-2023 | 1732/JMD | 17/08/2022 | 15/12/2022 | M/S. EMMESS | 6.83 | 6.82 | 99.78 | 0
398 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Chhota Khankri stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000267/2022-2023 | 1733/JMD | 17/08/2022 | 15/12/2022 | A. G. ENTERPRISE | 6.85 | 6.81 | 99.36 | 95
399 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Amtalia stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000180/2022-2023 | 1585/JMD | 27/07/2022 | 24/11/2022 | MENAKA ENTERPRISE | 6.87 | 6.84 | 99.6 | 90
400 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Baghakhondar stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000181/2022-2023 | 1586/JMD | 27/07/2022 | 24/11/2022 | ABHIJIT BASU | 6.86 | 6.83 | 99.55 | 90
401 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Chhota Jharia T/W no. -II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000615/2022-2023 | 3625/JMD | 07/12/2022 | 06/04/2023 | RITESH ENTERPRISE | 5.71 | 5.69 | 99.73 | 100
402 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dhulaburari T/W no. I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000591/2022-2023 | 3324/JMD | 14/11/2022 | 14/03/2023 | SUJOY RANJAN BHOWMICK | 5.71 | 5.7 | 99.83 | 100
403 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Niramishpur T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000610/2022-2023 | 3620/JMD | 07/12/2022 | 06/04/2023 | BUSR ENGINEERING | 5.7 | 5.68 | 99.79 | 100
404 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Koima (Pal) T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000524/2022-2023 | 3072/JMD | 28/09/2022 | 26/01/2023 | M/S. EMMESS | 5.71 | 5.68 | 99.56 | 100
405 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Nuagarh T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000540/2022-2023 | 3083/JMD | 28/09/2022 | 26/01/2023 | CHAKRABORTY MINING & ENGINEERING | 5.7 | 5.69 | 99.89 | 100
406 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Goal Danga T/W no. -II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000611/2022-2023 | 3621/JMD | 07/12/2022 | 06/04/2023 | MAA TARA ENTERPRISE | 5.72 | 5.69 | 99.5 | 100
407 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bara Khankri T/W no. -II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000612/2022-2023 | 3622/JMD | 07/12/2022 | 06/04/2023 | PRANAB KUMAR DAS | 5.7 | 5.68 | 99.67 | 95
408 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Chhota Khankri T/W no. -II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000613/2022-2023 | 3623/JMD | 07/12/2022 | 06/04/2023 | BHABANI PRASAD MANNA | 5.72 | 5.7 | 99.79 | 100
409 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Rajpara T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000552/2022-2023 | 3097/JMD | 28/09/2022 | 26/01/2023 | DEB KUMAR BASU | 5.75 | 5.74 | 99.88 | 100
410 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Jugi Bandh T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000622/2022-2023 | 3628/JMD | 07/12/2022 | 06/04/2023 | SUBHAM ENTERPRISE | 5.73 | 5.71 | 99.54 | 100
411 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Rangamatia T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000536/2022-2023 | 3079/JMD | 28/09/2022 | 26/01/2023 | J.K. ENGINEERING CO. | 5.7 | 5.67 | 99.46 | 100
412 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Gopiballavpir-I_2_1_C under Jhargram Division in the District of Jhargram. | Assistant Engineer | The Junior Engineer-IV Jhargram Sub-Division | ORD/000067/2022-2023 | 346/JHD | 28/09/2022 | 26/01/2023 | BISHNU PADA NANDI | 22.38 | 18.28 | 81.69 | 1
413 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bara Didiha T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000541/2022-2023 | 3086/JMD | 28/09/2022 | 26/01/2023 | BEE GEE CONSTRUCTION | 5.7 | 5.7 | 99.86 | 100
414 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Jamboni T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000578/2022-2023 | 3192/JMD | 28/10/2022 | 25/02/2023 | ARATI ENGINEERING | 5.72 | 5.7 | 99.66 | 100
415 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Gaida Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000662/2022-2023 | 4201/JMD | 28/12/2022 | 27/04/2023 | A.S. ENTERPRISE | 5.78 | 5.75 | 99.43 | 100
416 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Degaria Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000657/2022-2023 | 4196/JMD | 28/12/2022 | 27/04/2023 | CHATTERJEE CONSTRUCTION | 5.78 | 5.75 | 99.45 | 100
417 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Jamboni_1_3 under Jhargram Division in the District of Jhargram. | Assistant Engineer | Junior Engineer-II | ORD/000109/2021-2022 | 318/MD | 17/02/2022 | 16/08/2022 | ASIS KUMAR SARANGI | 90.24 | 72.58 | 80.43 | 40
418 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Pathar Chakri T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000528/2022-2023 | 3084/JMD | 28/09/2022 | 26/01/2023 | B. P. TRADING CORPORATION | 5.71 | 5.7 | 99.86 | 100
419 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Chilkigarh Stand Alone piped water supply scheme, tube well no-II of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000667/2022-2023 | 4206/JMD | 28/12/2022 | 27/04/2023 | BUSR ENGINEERING | 5.77 | 5.73 | 99.32 | 100
420 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Brindabanpur T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000543/2022-2023 | 3088/JMD | 28/09/2022 | 26/01/2023 | A.S. ENTERPRISE | 5.7 | 5.7 | 99.83 | 100
421 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Murakati T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000533/2022-2023 | 3077/JMD | 28/09/2022 | 26/01/2023 | A. G. ENTERPRISE | 5.7 | 5.68 | 99.55 | 100
422 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Salgaria (Near Club) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000544/2022-2023 | 3089/JMD | 28/09/2022 | 26/01/2023 | SAMARPITA ENGINEERING | 5.72 | 5.68 | 99.32 | 100
423 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dhumsai T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000545/2022-2023 | 3090/JMD | 28/09/2022 | 26/01/2023 | SUBHASIS ROY | 5.7 | 5.64 | 98.99 | 100
424 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bachhur Khoyar (Purba Para) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000548/2022-2023 | 3094/JMD | 28/09/2022 | 26/01/2023 | DEB KUMAR BASU | 5.71 | 5.69 | 99.65 | 100
425 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bhaluk Chua T/W no. -II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000542/2022-2023 | 3087/JMD | 28/09/2022 | 26/01/2023 | S.K. ENTERPRISE | 5.71 | 5.68 | 99.51 | 100
426 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Jhargram_2_4_A under Jhargram Division in the District of Jhargram. | Assistant Engineer | The Junior Engineer-IV Jhargram Sub-Division | ORD/000068/2022-2023 | 347/JHD | 28/09/2022 | 26/01/2023 | M/S. SANKAR KUMAR NAG | 22.33 | 18.24 | 81.7 | 100
427 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dhumsai T/W no. -II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000546/2022-2023 | 3091/JMD | 28/09/2022 | 26/01/2023 | M/S. SAMRIDDHI ENTERPRISE | 5.71 | 5.69 | 99.55 | 100
428 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dhumsai T/W no. -III Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000547/2022-2023 | 3092/JMD | 28/09/2022 | 26/01/2023 | ECO ENTERPRISE | 5.71 | 5.69 | 99.76 | 100
429 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bachhur Khoyar (Kutisai) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000554/2022-2023 | 3159/JMD | 19/10/2022 | 16/02/2023 | ABHIJIT BASU | 5.71 | 5.69 | 99.66 | 100
430 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Baradhan Sola T/W no. I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000566/2022-2023 | 3166/JMD | 19/10/2022 | 16/02/2023 | M.D. ENTERPRISE | 5.7 | 5.67 | 99.35 | 0
431 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Rukhni Mara (Village) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000526/2022-2023 | 3093/JMD | 28/09/2022 | 26/01/2023 | CHATTERJEE CONSTRUCTION | 5.71 | 5.69 | 99.74 | 100
432 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Khanakul T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000527/2022-2023 | 3085/JMD | 28/09/2022 | 26/01/2023 | RSA ENTERPRISE | 5.71 | 5.68 | 99.52 | 0
433 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Antapati T/W no. I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000568/2022-2023 | 3168/JMD | 19/10/2022 | 16/02/2023 | R.K. ENTERPRISES | 5.7 | 5.69 | 99.79 | 0
434 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kalinagar T/W no. I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000569/2022-2023 | 3169/JMD | 19/10/2022 | 16/02/2023 | SHIVAM ENTERPRISE | 5.7 | 5.69 | 99.72 | 0
435 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Koima (A.W.C.) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000570/2022-2023 | 3170/JMD | 19/10/2022 | 16/02/2023 | M/S. EMMESS | 5.7 | 5.68 | 99.57 | 100
436 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Tukurya Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000660/2022-2023 | 4199/JMD | 28/12/2022 | 27/04/2023 | RADHARANI ENTERPRISE | 5.77 | 5.16 | 89.48 | 100
437 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kiajharia T/W no. I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000558/2022-2023 | 3163/JMD | 19/10/2022 | 16/02/2023 | M/S. CHANDRANATH MUKHERJEE | 5.71 | 5.67 | 99.28 | 95
438 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Paika T/W no. I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000549/2022-2023 | 3156/JMD | 19/10/2022 | 16/02/2023 | DEBJYOTI BASU | 5.71 | 5.68 | 99.56 | 100
439 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bachhur Khoyar (Bardanga) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000580/2022-2023 | 3194/JMD | 28/10/2022 | 25/02/2023 | SUJOY RANJAN BHOWMICK | 5.71 | 5.7 | 99.92 | 100
440 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Jhargram_2_4_B under Jhargram Division in the District of Jhargram. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000053/2022-2023 | 320/JHD | 21/09/2022 | 19/01/2023 | RAMENDRA NATH KAR | 22.3 | 21.27 | 95.36 | 100
441 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Murar, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000690/2022-2023 | 146/JMD | 19/01/2023 | 19/05/2023 | MAA BHABOTARINE ENTERPRISE | 5.77 | 5.75 | 99.7 | 100
442 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Naharia, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000695/2022-2023 | 150/JMD | 19/01/2023 | 19/05/2023 | SUBHASIS ROY | 5.77 | 5.77 | 99.83 | 100
443 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Jhargram_2_1 under Jhargram Division in the District of Jhargram. | Assistant Engineer Headquarter | Junior Engineer Jhargram Dev. Block | ORD/000159/2022-2023 | 195/MD | 28/12/2022 | 26/06/2023 | KISHORE GHOSH | 133.21 | 103.05 | 77.36 | 100
444 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Nayagram_4_4 under Jhargram Division in the District of Jhargram. | Assistant Engineer | Junior Engineer Nayagram block | ORD/000056/2022-2023 | 876/MD | 10/05/2022 | 06/11/2022 | EFFLUENT AND WATER TREATMENT ENGINEERS PVT. LTD. | 177.59 | 167.62 | 94.38 | 100
445 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Jamboni Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000709/2022-2023 | 259/JMD | 03/02/2023 | 03/06/2023 | DEB KUMAR BASU | 5.78 | 5.75 | 99.5 | 95
446 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Parashia, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000712/2022-2023 | 262/JMD | 03/02/2023 | 03/06/2023 | RSA ENTERPRISE | 5.78 | 5.75 | 99.59 | 100
447 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Parashia, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000713/2022-2023 | 263/JMD | 03/02/2023 | 03/06/2023 | RSA ENTERPRISE | 5.78 | 5.75 | 99.59 | 100
448 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Hudhudi T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000521/2022-2023 | 3069/JMD | 28/09/2022 | 26/01/2023 | RMD TRADING | 5.7 | 5.69 | 99.68 | 100
449 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Shibanandapur T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000522/2022-2023 | 3070/JMD | 28/09/2022 | 26/01/2023 | BALAJI CONSTRUCTION | 5.71 | 5.68 | 99.57 | 100
450 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Lakhipara (School) T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000523/2022-2023 | 3071/JMD | 28/09/2022 | 26/01/2023 | MONORANJAN DEY | 5.71 | 5.68 | 99.56 | 100
451 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Ram Chandra Pur Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M),Junior Engineer | ORD/000688/2022-2023 | 144/JMD | 19/01/2023 | 19/05/2023 | SUJOY RANJAN BHOWMICK | 5.78 | 5.17 | 89.54 | 10
452 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Sahari Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000664/2022-2023 | 4203/JMD | 28/12/2022 | 27/04/2023 | PINTU DEY | 5.78 | 5.75 | 99.51 | 100
453 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kandnashol, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000707/2022-2023 | 257/JMD | 03/02/2023 | 03/06/2023 | M/S. EMMESS | 5.78 | 5.76 | 99.54 | 100
454 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Paika, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000716/2022-2023 | 267/JMD | 03/02/2023 | 03/06/2023 | DEBJYOTI BASU | 5.77 | 5.15 | 89.27 | 10
455 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bara Menia Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000706/2022-2023 | 256/JMD | 03/02/2023 | 03/06/2023 | M/S A.D. CONCERN | 5.78 | 5.71 | 98.72 | 95
456 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Biriberia Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000708/2022-2023 | 258/JMD | 03/02/2023 | 03/06/2023 | MAA TARA ENTERPRISE | 5.78 | 5.75 | 99.47 | 100
457 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dhumsai, Tube Well no.-IV Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000715/2022-2023 | 266/JMD | 03/02/2023 | 03/06/2023 | ABHIJIT BASU | 5.78 | 5.75 | 99.59 | 100
458 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Naharia, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000684/2022-2023 | 136/JMD | 18/01/2023 | 18/05/2023 | SOUMEN ELECTRIC | 5.78 | 5.76 | 99.72 | 0
459 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Harki Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000685/2022-2023 | 137/JMD | 18/01/2023 | 18/05/2023 | PADMA ENGINEERING CO. | 5.78 | 5.76 | 99.71 | 100
460 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Madhabpur stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,DIC(D)_MMSD(D) | Junior Engineer | ORD/000733/2022-2023 | 3431/JMD | 29/11/2022 | 06/12/2022 | SUJOY RANJAN BHOWMICK | 0.07 | 0.07 | 100 | 100
461 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Chanda Bila stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000741/2022-2023 | 3443/JMD | 29/11/2022 | 06/12/2022 | DEBJYOTI BASU | 0.07 | 0.07 | 100 | 100
462 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dhansola Chhota Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000728/2022-2023 | 311/JMD | 09/02/2023 | 09/06/2023 | RADHARANI ENTERPRISE | 5.77 | 5.75 | 99.55 | 95
463 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Murar, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000689/2022-2023 | 145/JMD | 19/01/2023 | 19/05/2023 | DEBJYOTI BASU | 5.77 | 5.1 | 88.44 | 97
464 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Dubrajpur stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,DIC(D)_MMSD(D) | Junior Engineer | ORD/000734/2022-2023 | 3444/JMD | 29/11/2022 | 06/12/2022 | SUJOY RANJAN BHOWMICK | 0.07 | 0.07 | 100 | 100
465 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Narendrapur Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000692/2022-2023 | 148/JMD | 19/01/2023 | 19/05/2023 | CHATTERJEE CONSTRUCTION | 5.77 | 5.75 | 99.6 | 100
466 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bara Khankri T/W no. -II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Driller-In-Charge | Junior Engineer | ORD/000744/2022-2023 | 3500/JMD | 29/11/2022 | 06/12/2022 | PRANAB KUMAR DAS | 0.07 | 0.07 | 100 | 100
467 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Garra stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000740/2022-2023 | 3433/JMD | 29/11/2022 | 06/12/2022 | DEBJYOTI BASU | 0.07 | 0.07 | 100 | 100
468 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Maubhandar, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000705/2022-2023 | 255/JMD | 03/02/2023 | 03/06/2023 | DEY ENTERPRISE | 5.78 | 5.75 | 99.51 | 100
469 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Nargi mouza of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000877/2021-2022 | 569/JMD | 23/12/2021 | 27/12/2021 | CHAKRABORTY MINING & ENGINEERING | 2.77 | 0 | 0 | 100
470 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bihankuria Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Driller-In-Charge | Junior Engineer | ORD/000751/2022-2023 | 657/JMD | 24/03/2023 | 22/07/2023 | SHIVAM ENTERPRISE | 5.75 | 5.72 | 99.54 | 100
471 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bara Ningui, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000752/2022-2023 | 658/JMD | 24/03/2023 | 22/07/2023 | DEBJYOTI BASU | 5.77 | 5.75 | 99.58 | 95
472 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Totasai, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000756/2022-2023 | 662/JMD | 24/03/2023 | 22/07/2023 | M.D. ENTERPRISE | 5.78 | 5.76 | 99.65 | 80
473 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Astia Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000758/2022-2023 | 664/JMD | 24/03/2023 | 22/07/2023 | B. P. TRADING CORPORATION | 5.78 | 5.76 | 99.55 | 100
474 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bara Ningui, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000753/2022-2023 | 659/JMD | 24/03/2023 | 22/07/2023 | DEBJYOTI BASU | 5.77 | 5.75 | 99.58 | 95
475 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bhalia Ghati, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000754/2022-2023 | 660/JMD | 24/03/2023 | 22/07/2023 | P.K. ENGINEERING | 5.78 | 5.75 | 99.43 | 95
476 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Khasjangal, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000009/2023-2024 | 957/JMD | 25/04/2023 | 23/08/2023 | MENAKA ENTERPRISE | 5.78 | 5.74 | 99.4 | 95
477 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Deulbar, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000011/2023-2024 | 959/JMD | 25/04/2023 | 23/08/2023 | DEB KUMAR BASU | 5.78 | 5.75 | 99.47 | 95
478 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Sankarbani Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000005/2023-2024 | 953/JMD | 25/04/2023 | 23/08/2023 | SRI KRISHNA NIRMAN | 5.78 | 5.76 | 99.72 | 100
479 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Continuation Work Order For "Hire charges of Bharat Stage-II / III Diesel Motor Cabs (Luxury Taxi) / Maruti Omni (Standard-Non-Air Conditioned) having Contract Carriage Permit from the Regional Transport Authority for the Office of the Executive Engineer, Jhargram Division, PHE Dte. for the period of 2 (Two) Month's, from 01.03.2023 to 30.04.2023. | Assistant Engineer |  | ORD/000242/2022-2023 | 146/JSD | 27/02/2023 | 27/04/2023 | SUNIL DULE | 0.29 | 0.75 | 257.3 | 99
480 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Ramkrishnapur, Tube Well no.-III Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000019/2023-2024 | 967/JMD | 25/04/2023 | 23/08/2023 | SOUMEN ELECTRIC | 5.78 | 5.75 | 99.63 | 100
481 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Paira Kuli, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000007/2023-2024 | 955/JMD | 25/04/2023 | 23/08/2023 | A.K. SIKDAR | 5.77 | 5.68 | 98.47 | 100
482 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Khasjangal, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000008/2023-2024 | 956/JMD | 25/04/2023 | 23/08/2023 | P.K. ENGINEERING | 5.78 | 5.75 | 99.59 | 95
483 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Nargi mouza of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000880/2021-2022 | 570/JMD | 23/12/2021 | 27/12/2021 | CHAKRABORTY MINING & ENGINEERING | 0.33 | 0 | 0 | 100
484 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Hire charges of Bharat Stage-II / III Diesel Motor Cabs (Luxury Taxi) / Maruti Omni (Standard-Non-Air Conditioned) having Contract Carriage Permit from the Regional Transport Authority valid for the State of West Bengal not older than 2 years from the date of 1st Registration on daily Hire rate basis for the period from 01.12.2022 to 15.05.2023. for the Movement of Junior Engineer (RWS) under Jhargram Division, PHE Dte. The cost inclusive of all charges due to the wages of Driver, Taxes, Insurance, fees etc., as applicable. Diesel-12KM/Lit. Mobil-500KM/Lit. | Assistant Engineer |  | ORD/000236/2022-2023 | 664 | 28/11/2022 | 13/05/2023 | TAPAN KUMAR UPADHYAY | 0.93 | 1.71 | 183.25 | 80
485 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kadam Diha, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000015/2023-2024 | 963/JMD | 25/04/2023 | 23/08/2023 | M/S. P.P. ELECTRICALS | 5.77 | 5.73 | 99.21 | 95
486 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Paira Kuli, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000006/2023-2024 | 954/JMD | 25/04/2023 | 23/08/2023 | SINHA ELECTRICALS | 5.62 | 5.56 | 98.91 | 95
487 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kandnashol, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer |  | ORD/000055/2023-2024 | 1359/JMD | 06/06/2023 | 04/10/2023 | MONORANJAN DEY | 5.77 | 5.74 | 99.39 | 95
488 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Jagannathpur Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000028/2023-2024 | 1206/JMD | 25/05/2023 | 22/09/2023 | MASSK ENGINEERING WORKS | 5.78 | 5.72 | 99.12 | 95
489 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Chandabila, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000029/2023-2024 | 1207/JMD | 25/05/2023 | 22/09/2023 | M/S. EMMESS | 5.78 | 4.13 | 71.56 | 95
490 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bhararu T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Driller-In-Charge | JE (M),Junior Engineer | ORD/000096/2023-2024 | 1712/JMD | 13/07/2023 | 10/11/2023 | SOUMEN ELECTRIC | 5.98 | 5.94 | 99.27 | 100
491 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Amadubi T/W no. -I & II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000077/2023-2024 | 985/JMD | 26/04/2023 | 23/10/2023 | ABHIJIT BASU | 6.89 | 6.78 | 98.43 | 95
492 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Andharisol, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000053/2023-2024 | 987/JMD | 26/04/2023 | 24/08/2023 | SHOVAN KUMAR DAS | 5.78 | 5.76 | 99.66 | 95
493 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Pukhuria, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000087/2023-2024 | 1727/JMD | 14/07/2023 | 11/11/2023 | SAMARPITA ENGINEERING | 5.78 | 5.75 | 99.36 | 95
494 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Pukhuria, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000088/2023-2024 | 1728/JMD | 14/07/2023 | 11/11/2023 | M/S. SAMRIDDHI ENTERPRISE | 5.78 | 5.03 | 86.99 | 100
495 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Sanuningui, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000089/2023-2024 | 1729/JMD | 14/07/2023 | 11/11/2023 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 5.78 | 5.03 | 86.92 | 95
496 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Sanuningui, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000090/2023-2024 | 1730/JMD | 14/07/2023 | 11/11/2023 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 5.78 | 5.76 | 99.56 | 95
497 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kankrajhor T/W no. -III Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000078/2023-2024 | 986/JMD | 24/04/2023 | 22/08/2023 | DEB KUMAR BASU | 5.98 | 5.85 | 97.71 | 95
498 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Rai Gani, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000100/2023-2024 | 1760/JMD | 19/07/2023 | 16/11/2023 | ABHIJIT BASU | 5.78 | 5.74 | 99.28 | 100
499 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Deulbar, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Driller-In-Charge | Junior Engineer | ORD/000112/2023-2024 | 1771/JMD | 19/07/2023 | 16/11/2023 | ABHIJIT BASU | 5.78 | 5.75 | 99.44 | 100
500 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Rangua T/W no. -II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000165/2023-2024 | 2021/JMD | 02/08/2023 | 30/11/2023 | MENAKA ENTERPRISE | 5.78 | 5.44 | 94.24 | 100
501 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bankisol Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M),Junior Engineer | ORD/000146/2023-2024 | 1838/JMD | 24/07/2023 | 21/11/2023 | MENAKA ENTERPRISE | 5.78 | 5.19 | 89.89 | 100
502 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dingla Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000149/2023-2024 | 1841/JMD | 24/07/2023 | 21/11/2023 | A.M.S. ENTERPRISE | 5.75 | 5.72 | 99.51 | 100
503 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank and provision of FHTC for drought like situation prone areas at different location under Binpur-II Block location Id Binpur-II_3_2_A under Jhargram Division in the District of Jhargram. | Assistant Engineer | Junior Engineer-II | ORD/000105/2023-2024 | 1205/JHD | 26/07/2023 | 24/09/2023 | MANISHIKA CONSTRUCTION | 19.86 | 17.68 | 89.01 | 100
504 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Khatkura Jr. High School Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000294/2023-2024 | 2633/JMD | 29/08/2023 | 27/12/2023 | MOUSUMI BANERJEE | 5.77 | 5.74 | 99.48 | 100
505 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Malam mouza , tube well no. 1 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000929/2021-2022 | 697/JMD | 31/12/2021 | 04/01/2022 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 2.6 | 1.75 | 67.53 | 100
506 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Kalma Pukhuria mouza , tube well no. 3 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000930/2021-2022 | 675/JMD | 31/12/2021 | 04/01/2022 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 2.6 | 2 | 76.98 | 100
507 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Kalma Pukhuria , tube well no. 4 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000897/2022-2023 | 1052/JMD | 01/06/2022 | 06/06/2022 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 2.78 | 1.77 | 63.88 | 100
508 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Jadabpur mouza of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000923/2021-2022 | 664/JMD | 31/12/2021 | 04/01/2022 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 0.33 | 0.26 | 79.22 | 100
509 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Malam mouza , tube well no. 2 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000924/2021-2022 | 700/JMD | 31/12/2021 | 04/01/2022 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 0.33 | 0.26 | 79.22 | 100
510 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Tikra Para mouza of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000925/2021-2022 | 706/JMD | 31/12/2021 | 04/01/2022 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 0.33 | 0.26 | 79.22 | 100
511 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Jadabpur mouza of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000936/2021-2022 | 663/JMD | 31/12/2021 | 04/01/2022 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 2.6 | 1.76 | 67.81 | 100
512 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Kalma Pukhuria mouza , tube well no. 4 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000898/2022-2023 | 1053/JMD | 01/06/2022 | 06/06/2022 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 0.33 | 0.26 | 79.22 | 100
513 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Organizing Inauguration Ceremony of Different Commissioned Piped Water Supply Schemes for IEC Activities in Different Places within Jhargram District under Jhargram Division, PHE Dte. (Location ID_1) | Assistant Engineer |  | ORD/000302/2023-2024 | 341/JSD | 11/05/2023 | 25/06/2023 | NRIPENDRA NATH SINGHA | 0.69 | 0.69 | 100 | 100
514 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Narda stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000153/2022-2023 | 1458/JMD | 19/07/2022 | 16/11/2022 | ECO ENTERPRISE | 6.87 | 6.85 | 99.78 | 100
515 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Chilkigar mouza, tube well no.4 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000953/2021-2022 | 565/JMD | 23/12/2021 | 27/12/2021 | CHAKRABORTY MINING & ENGINEERING | 2.62 | 1.56 | 59.62 | 100
516 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Chilkigar mouza, tube well no.4 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000954/2021-2022 | 566/JMD | 23/12/2021 | 27/12/2021 | CHAKRABORTY MINING & ENGINEERING | 0.33 | 0.33 | 100 | 100
517 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply & delivery of upvc consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary / Combination Method at Panisol Primary School under Gopiballavpur-I Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000583/2023-2024 | 2984/JMD | 16/10/2023 | 20/10/2023 | CHAKRABORTY MINING & ENGINEERING | 3.37 | 0 | 0 | 100
518 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Tiyakati mouza of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000932/2021-2022 | 647/JMD | 31/12/2021 | 04/01/2022 | SAMARPITA ENGINEERING | 2.6 | 1.68 | 64.68 | 100
519 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Tiyakati mouza of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000940/2021-2022 | 648/JMD | 31/12/2021 | 04/01/2022 | SAMARPITA ENGINEERING | 0.33 | 0.26 | 79.22 | 100
520 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing additional FHTC under Stand Alone PWSS, in Shankarbani Mouza, Jhargram Block under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000375/2023-2024 | 1988/JHD | 29/11/2023 | 29/12/2023 | ASHIS SHEE | 0.87 | 0.82 | 94.59 | 100
521 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Extension of distribution pipe line and its allied works at different location under location Id Jhargram_2_2 for 269 Stand alone PWSS under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer Jhargram Dev. Block | ORD/000397/2023-2024 | 3078/JHD | 26/12/2023 | 25/01/2024 | LALIT BIHARI MAITY | 3.35 | 3.12 | 93.15 | 100
522 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Hanri Bhanga stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000164/2022-2023 | 1464/JMD | 19/07/2022 | 16/11/2022 | PRANAB KUMAR DAS | 6.86 | 6.78 | 98.8 | 100
523 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Installation of Display Bord for JJM works at different piped water supply scheme within Gopiballavpur-I Block under Jhargram Division, PHE dte. (1st Phase) | Assistant Engineer Headquarter | Junior Engineer, Gopiballavpur Sub Division | ORD/000410/2023-2024 | 53/JHD | 10/01/2024 | 24/02/2024 | MANOJ KUMAR MAHATA | 0.91 | 0.87 | 95.92 | 100
524 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Installation of Display Bord for JJM works at different piped water supply scheme within Binpur-II Block under Jhargram Division, PHE dte. (1st Phase) | Assistant Engineer Headquarter | Junior Engineer, Gopiballavpur Sub Division | ORD/000409/2023-2024 | 52/JHD | 10/01/2024 | 24/02/2024 | PRINT PREVIEW | 0.91 | 0.87 | 95.92 | 100
525 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply delivery of CIDF S/V , CI Specials, Jiffy Coupler etc. for the work of O & M of Different Water Supply Scheme under Jhargram Sub Division within Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000403/2023-2024 | 977/JSD | 17/11/2023 | 24/11/2023 | NRIPENDRA NATH SINGHA | 0.96 | 0.96 | 100 | 100
526 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Khatkhura T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000621/2022-2023 | 3627/JMD | 07/12/2022 | 06/04/2023 | SHOVAN KUMAR DAS | 5.72 | 4.15 | 72.55 | 10
527 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Installation of Display Bord for JJM works at different piped water supply scheme within Gopiballavpur-II Block under Jhargram Division, PHE dte. (1st Phase) | Assistant Engineer Headquarter | Junior Engineer, Gopiballavpur Sub Division | ORD/000411/2023-2024 | 54/JHD | 10/01/2024 | 24/02/2024 | MANOJ KUMAR MAHATA | 0.91 | 0.87 | 95.92 | 100
528 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Continuation Work for Uploading, Development upgradation of all collected FHTC data and special features alongwith reorientation of JJM_ IMIS Dashboard. (including all charges i.e. contructor profit etc.) for September-2023 to November-2023 under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram Sub-Division | ORD/000416/2023-2024 | 194/JRWS | 29/08/2023 | 27/11/2023 | GOPAL JANA | 0.83 | 0.62 | 74.91 | 100
529 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Installation of Display Bord for JJM works at different piped water supply scheme within Binpur-I Block under Jhargram Division, PHE dte. (1st Phase) | Assistant Engineer Headquarter | Junior Engineer, Gopiballavpur Sub Division | ORD/000408/2023-2024 | 51/JHD | 10/01/2024 | 24/02/2024 | PRINT PREVIEW | 0.91 | 0.87 | 95.92 | 100
530 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Continuation Work for Functional Household Tap Connection data uploading charges of different PWSS under Jhargram District in JJM_IMIS portal under Jal Jeevan Mission from 01.02.2024 to 15.02.2024 under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000693/2023-2024 | 374/JRWS | 29/01/2024 | 13/02/2024 | JAGOMOHAN SETUA | 0.63 | 0.58 | 92.17 | 100
531 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Functional Household Tap Connection data uploading charges of different PWSS under Jhargram District in JJM_IMIS portal under Jal Jeevan Mission for December 2023 under Jhargram Division PHE Dte | Assistant Engineer | Junior Engineer-II | ORD/000643/2023-2024 | 285/JRWS | 28/11/2023 | 29/12/2023 | JAGOMOHAN SETUA | 0.95 | 0.87 | 92.31 | 100
532 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional (90 mm) pipeline distribution and associated works for Standalone PWSS at Nuagarh in Bandhgora GP under Jhargram division, Phe Dte. | Assistant Engineer Headquarter | Junior Engineer, Jhargram Sub-Division | ORD/000155/2024-2025 | 1968/JHD | 21/10/2024 | 20/11/2024 | ASHIS SHEE | 0.49 | 0.49 | 100 | 100
533 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional (63 mm) pipeline distribution and associated works for Standalone PWSS at Nuagarh in Bandhgora GP under Jhargram division, Phe Dte. | Assistant Engineer Headquarter | Junior Engineer, Jhargram Sub-Division | ORD/000156/2024-2025 | 1969/JHD | 21/10/2024 | 20/11/2024 | ASHIS SHEE | 0.84 | 0.84 | 100 | 100
534 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Chhota Jharia T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Driller-In-Charge | Junior Engineer | ORD/000946/2022-2023 | 3501/JMD | 29/11/2022 | 06/12/2022 | M/S B.M. ELECTRICAL | 0.07 | 0 | 0 | 100
535 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Chhota Jharia T/W no. -II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Driller-In-Charge | Junior Engineer | ORD/000947/2022-2023 | 3502/JMD | 29/11/2022 | 06/12/2022 | RITESH ENTERPRISE | 0.07 | 0.07 | 100 | 100
536 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Arra stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Driller-In-Charge | Junior Engineer | ORD/000945/2022-2023 | 3455/JMD | 29/11/2022 | 06/12/2022 | M/S B.M. ELECTRICAL | 0.07 | 0.04 | 52.96 | 100
537 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Continuation work for Functional Household Tap Connection data uploading charges of different PWSS under Jhargram District in JJM_IMIS portal under Jal Jeevan Mission for January 2024 under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000692/2023-2024 | 338/JRWS | 29/12/2023 | 29/01/2024 | JAGOMOHAN SETUA | 0.89 | 0.89 | 99.73 | 100
538 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of 150 X 100 mm dia. X 150 Mtr. Depth Rig bored Tube well-2 (Location ID Jamboni_4_2) at Mouza- Dumuria in Jamboni Block of Jhargram District under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-III | ORD/000018/2024-2025 | 1039/JHD | 22/07/2024 | 21/08/2024 | FIROJ KHAN | 5.32 | 3.47 | 65.2 | 100
539 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of 150 X 100 mm dia. X 150 Mtr. Depth Rig bored Tube well-2 (Location ID Jamboni_4_3) at Mouza- Dumuria in Jamboni Block of Jhargram District under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-III | ORD/000014/2024-2025 | 923/JHD | 09/07/2024 | 08/08/2024 | BISHNU PADA NANDI | 5.63 | 3.67 | 65.24 | 100
540 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Fuel and lubricant bill for Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at different blocks under stand alone piped water supply scheme (SM/09915) of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. |  |  | BILL/00984/2023-2024 | BP-2023-24-600 | 30/03/2024 | 30/03/2024 | SURAJ SERVICE STATION | 0.63 | 0 | 0 | 0
541 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply of 10 nos. DSC - Class 3 Combo - 2 years under Jhargram Division, PHE Dte. |  |  | BILL/00549/2024-2025 | BP-2024-25-297 | 10/12/2024 | 10/12/2024 | GOPAL JANA | 0.31 | 0 | 0 | 0
542 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Fuel and lubricant bill for Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Khatkura and others mouza of Jamboni and others blocks under stand alone piped water supply scheme (SM/09915) of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. |  |  | BILL/00902/2023-2024 | BP-2023-24-524 | 12/03/2024 | 12/03/2024 | SURAJ SERVICE STATION | 1.62 | 0 | 0 | 0
543 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Charges for periodical filing of various statutory deductions viz. GST, IT, Cess, Revenue, P.Tax etc. under Jhargram Division, PHE Dte. Period |  |  | BILL/00550/2024-2025 | BP-2024-25-296 | 10/12/2024 | 10/12/2024 | NIGAM CONSULTANCY SERVICES | 0.96 | 0 | 0 | 0
544 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Gopiballavpir-I_2_1_D under Jhargram Division in the District of Jhargram. | Assistant Engineer | Junior Engineer,Junior Engineer Gopiballavpur-I block | ORD/000091/2022-2023 | 455/JHD | 11/11/2022 | 11/03/2023 | ASSOCIATED ENGINEERS & TRADERS | 22.38 | 16.46 | 73.54 | 100
545 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Jhargram_2_3 under Jhargram Division in the District of Jhargram. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000009/2021-2022 | 196/MD | 01/02/2022 | 31/07/2022 | SUNIL DULE | 134.69 | 110 | 81.66 | 90
546 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Jugi Bandh T/W no. -II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000623/2022-2023 | 3629/JMD | 07/12/2022 | 31/03/2024 | COMBINE ENTERPRISES | 5.71 | 5.1 | 89.4 | 100
547 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Muniada T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000620/2022-2023 | 3626/JMD | 07/12/2022 | 31/03/2024 | R.N.S. TRADING | 5.73 | 0 | 0 | 100
548 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bhaluka Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000666/2022-2023 | 4205/JMD | 28/12/2022 | 31/03/2024 | COMBINE ENTERPRISES | 5.78 | 5.17 | 89.5 | 95
549 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Nayagram_1_1 under Jhargram Division in the District of Jhargram. | Assistant Engineer | Junior Engineer Nayagram block | ORD/000002/2021-2022 | 189/MD | 01/02/2022 | 31/07/2022 | PROVAT KUMAR DE | 106.64 | 99.96 | 93.74 | 100
550 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Nayagram_4_3 under Jhargram Division in the District of Jhargram. | Assistant Engineer | Junior Engineer Nayagram block | ORD/000137/2021-2022 | 218/MD | 03/02/2022 | 02/08/2022 | MAHAVIR PUMPS MFG. PVT. LTD. | 177.75 | 106.43 | 59.87 | 75
551 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Nayagram_4_6 under Jhargram Division in the District of Jhargram. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division | Junior Engineer | ORD/000210/2022-2023 | 1013/MD | 27/05/2022 | 16/05/2025 | MONDAL PRECISION PRIVATE LIMITED | 176.7 | 152.03 | 86.04 | 82
552 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Nayagram_4_7 under Jhargram Division in the District of Jhargram. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division | Junior Engineer | ORD/000211/2022-2023 | 1014/MD | 27/05/2022 | 26/03/2025 | MONDAL PRECISION PRIVATE LIMITED | 176.7 | 168.69 | 95.47 | 86
553 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Nayagram_4_9 under Jhargram Division in the District of Jhargram. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division | Junior Engineer | ORD/000212/2022-2023 | 1015/MD | 27/05/2022 | 16/05/2025 | MONDAL PRECISION PRIVATE LIMITED | 177.73 | 124.52 | 70.06 | 81
554 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bachhur Khoyar (Kutisai) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000718/2022-2023 | 3491/JMD | 29/11/2022 | 06/12/2022 | ABHIJIT BASU | 0.07 | 0 | 0 | 0
555 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Narcha stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000700/2022-2023 | 3432/JMD | 29/11/2022 | 31/12/2024 | ABHIJIT BASU | 0.07 | 0 | 0 | 100
556 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Baghakhondar stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000720/2022-2023 | 3542/JMD | 29/11/2022 | 06/12/2022 | ABHIJIT BASU | 0.07 | 0 | 0 | 100
557 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Nayagram_4_11 under Jhargram Division in the District of Jhargram. | Assistant Engineer | Junior Engineer Nayagram block | ORD/000129/2021-2022 | 219/MD | 03/02/2022 | 02/08/2022 | SANYUKTA ENGINEERING PVT. LTD. | 177.68 | 78.69 | 44.29 | 40
558 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Jamboni_3_3 under Jhargram Division in the District of Jhargram. | Assistant Engineer | Junior Engineer-I | ORD/000146/2021-2022 | 199/MD | 01/02/2022 | 31/07/2022 | FIDERE MARINE SERVICES PVT. LTD. | 161.08 | 59.14 | 36.71 | 75
559 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Nayagram_1_8 under Jhargram Division in the District of Jhargram. | Assistant Engineer | Junior Engineer Nayagram block,Junior Engineer-III | ORD/000132/2021-2022 | 194/MD | 01/02/2022 | 03/02/2025 | PALCON | 107.05 | 51.08 | 47.72 | 50
560 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Nayagram_4_12 under Jhargram Division in the District of Jhargram. | Assistant Engineer | Junior Engineer Nayagram block,Junior Engineer-III | ORD/000149/2021-2022 | 220/MD | 03/02/2022 | 03/11/2024 | CARBON SERVICES INDIA | 176.88 | 146.4 | 82.77 | 50
561 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Binpur-I_3_1 under Jhargram Division in the District of Jhargram. | Assistant Engineer | Junior Engineer Binpur-I block | ORD/000148/2021-2022 | 303/MD | 15/02/2022 | 05/02/2025 | ODISSI INNOVATIONS ENGINEERS PRIVATE LIMITED | 100.66 | 30.77 | 30.57 | 70
562 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Nayagram_4_8 under Jhargram Division in the District of Jhargram. | Assistant Engineer | Junior Engineer Nayagram block | ORD/000159/2021-2022 | 430/MD | 04/03/2022 | 10/08/2026 | JDJ ENTERPRISE (A UNIT OF JDJ TRADERS PRIVATE LIMITED) | 177.59 | 53.07 | 29.88 | 45
563 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Nayagram_4_1 under Jhargram Division in the District of Jhargram. | Assistant Engineer | Junior Engineer Nayagram block,Junior Engineer-II | ORD/000156/2021-2022 | 428/MD | 04/03/2022 | 10/08/2026 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 177.59 | 27.46 | 15.46 | 40
564 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Nayagram_4_2 under Jhargram Division in the District of Jhargram. | Assistant Engineer | Junior Engineer Nayagram block,Junior Engineer, Jhargram Division | ORD/000158/2021-2022 | 429/MD | 04/03/2022 | 10/08/2026 | JDJ ENTERPRISE (A UNIT OF JDJ TRADERS PRIVATE LIMITED) | 177.59 | 33.54 | 18.89 | 50
565 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Patina, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Driller-In-Charge | JE (M) | ORD/000111/2023-2024 | 1770/JMD | 19/07/2023 | 14/12/2024 | SUJOY RANJAN BHOWMICK | 5.78 | 3.78 | 65.43 | 70
566 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Phulbani, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Driller-In-Charge | Junior Engineer | ORD/000105/2023-2024 | 1765/JMD | 19/07/2023 | 30/04/2025 | M/S D.G.B. ENTERPRISE | 5.78 | 3.78 | 65.42 | 70
567 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Panchami Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000840/2022-2023 | 265/JMD | 03/02/2023 | 31/12/2023 | BALAJI CONSTRUCTION | 5.78 | 5 | 86.49 | 100
568 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bara Kati Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Driller-In-Charge | JE (M),Junior Engineer | ORD/000132/2023-2024 | 1824/JMD | 24/07/2023 | 04/03/2025 | PRANAB KUMAR DAS | 5.78 | 0 | 0 | 100
569 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Nagri Pada, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Driller-In-Charge | JE (M),Junior Engineer | ORD/000161/2023-2024 | 1972/JMD | 31/07/2023 | 11/09/2025 | S.S. GHORAI | 5.78 | 0 | 0 | 100
570 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Kalma Pukhuria , tube well no. 5 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000895/2022-2023 | 1054/JMD | 01/06/2022 | 01/06/2025 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 2.78 | 0 | 0 | 100
571 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Nischintapur mouza, tube well no.1 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M),Junior Engineer | ORD/000950/2021-2022 | 125/JMD | 31/01/2022 | 01/03/2025 | DEBJYOTI BASU | 0.71 | 0 | 0 | 100
572 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Lekraanchra mouza, tube well no.2 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M),Junior Engineer | ORD/000947/2021-2022 | 107/JMD | 31/01/2022 | 21/05/2023 | DEBJYOTI BASU | 0.71 | 0 | 0 | 100
573 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Kankrajhor mouza, tube well no.4 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M),Junior Engineer | ORD/000948/2021-2022 | 91/JMD | 31/01/2022 | 01/10/2023 | DEBJYOTI BASU | 0.71 | 0 | 0 | 100
574 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Nayagram_1_2 under Jhargram Division in the District of Jhargram | Assistant Engineer | Junior Engineer Nayagram block | ORD/000005/2021-2022 | 190/MD | 01/02/2022 | 31/07/2022 | SUJATA CONSTRUCTION | 106.99 | 61.68 | 57.65 | 70
575 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Nischintapur mouza, tube well no.1 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M),Junior Engineer | ORD/000942/2021-2022 | 126/JMD | 31/01/2022 | 01/03/2025 | DEBJYOTI BASU | 0.16 | 0 | 0 | 100
576 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Kankrajhor mouza, tube well no.4 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M),Junior Engineer | ORD/000943/2021-2022 | 92/JMD | 31/01/2022 | 01/10/2023 | DEBJYOTI BASU | 0.16 | 0 | 0 | 100
577 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Providing different manpower for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Lekraanchra mouza, tube well no.2 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M),Junior Engineer | ORD/000944/2021-2022 | 108/JMD | 31/01/2022 | 21/05/2023 | DEBJYOTI BASU | 0.16 | 0 | 0 | 100
578 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Hiring of 1 (one) no Additional Motor Cab (standard) commercial with Catalatyic Converter attachement with Bharat Stage as per prevalent applicable standard compliant new not older than 30 (Thirty) months from the date of 1st registration on daily hire rate basis for 12 (Twelve) months only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Assistant Engineer, Gopiballavpur Sub-Division, PHE Dte. for monitoring of JJM Works (One Year). | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000445/2023-2024 | 58/GPSD | 06/02/2024 | 06/02/2025 | SUJOY RANJAN BHOWMICK | 2.05 | 3.79 | 184.85 | 0
579 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Hiring of 1 (one) no Additional Motor Cab (standard) commercial with Catalytic Converter Attachment with Bharat Stage as per prevalent applicable standard compliant new not older than 30 (Thirty) months from the date of 1st registration on daily hire rate basis for 12 (Twelve) months only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Assistant Engineer, Jhargram Sub-Division, PHE Dte. for monitoring of JJM Works (One Year). (4th Call) [Ref: 3rd Call of e-NIQ-01 of AE/JSD of 2024-2025, SL. No.-01] | Assistant Engineer | Junior Engineer-II | ORD/000214/2024-2025 | 1132/JSD | 10/12/2024 | 10/12/2025 | A.K. SIKDAR | 2.05 | 1.27 | 62.1 | 0
580 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under Binpur-II Block location Id Binpur-II_3_2_B under Jhargram Division in the District of Jhargram. 3rd (Ref: 1st Call eNIT_39 of 2022-23, SL No.-5, 2nd Call eNIT_11 of EE/JHD of 2023-24, SL No.-14) | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division | Junior Engineer RWS, Binpur-II Devlopment Block.,Junior Engineer-II | ORD/000093/2024-2025 | 1276/JHD | 03/09/2024 | 02/11/2024 | A R CONSTRUCTION | 20.38 | 0 | 0 | 55
581 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Hiring of 1 (one) no Additional Motor Cab (standard) commercial with Catalytic Converter Attachment with Bharat Stage as per prevalent applicable standard compliant new not older than 30 (Thirty) months from the date of 1st registration on daily hire rate basis for 12 (Twelve) months only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Assistant Engineer, Jhargram Sub-Division, PHE Dte. (Priods from 1.11.2024 to 31.10.2025) | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division | Junior Engineer-III | ORD/000170/2024-2025 | 1008/JSD | 30/10/2024 | 30/10/2025 | BIDYUT KUMAR SANTRA | 2.05 | 1.35 | 65.86 | 0
582 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Installation of Iron Elimination Plant including PCC Concrete Platform at Bamundiha Stand Alone PWSS of Binpir-II Block under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000253/2024-2025 | 41/JHD | 07/01/2025 | 08/03/2025 | PALCON | 7.47 | 0 | 0 | 0
583 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Hire charges of Bharat Stage-II / III Diesel Motor Cabs (Luxury Taxi) / Maruti Omni (Standard-Non-Air Conditioned) having Contract Carriage Permit from the Regional Transport Authority valid for the State of West Bengal not older than 2 years from the date of 1st Registration on daily Hire rate basis for the period from 01.07.2024 to 31.12.2024. for the Movement of Junior Engineer (RWS) under Jhargram Division, PHE Dte. The cost inclusive of all charges due to the wages of Driver, Taxes, Insurance, fees etc., as applicable. ( For 6 months) | Assistant Engineer | Junior Engineer-II | ORD/000110/2024-2025 | 170/JRWS | 28/06/2024 | 29/12/2024 | RAHUL DEY | 0.87 | 2.17 | 248.18 | 0
584 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Nayagram_1_5 under Jhargram Division in the District of Jhargram. | Assistant Engineer | Junior Engineer Nayagram block | ORD/000196/2021-2022 | 425/MD | 04/03/2022 | 31/08/2022 | RELIABLE SANITARY & PLUMBING CO. | 107.26 | 14.59 | 13.61 | 60
585 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Pathar Chakri T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000948/2022-2023 | 3521/JMD | 29/11/2022 | 06/12/2022 | B. P. TRADING CORPORATION | 0.07 | 0 | 0 | 100
586 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | preparation of documents for uploading in Parivesh Portal for clearance of forest land proposed for 269 Stand Alone PWSS under Jhargram Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000833/2023-2024 | 700/JSD | 04/08/2023 | 03/09/2023 | CARTO | 0.41 | 0 | 0 | 100
587 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Installation of Iron Elimination Plant including PCC Concrete Platform at Charakpahari Stand Alone PWSS of Binpir-II Block under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000241/2024-2025 | 03/JHD | 02/01/2025 | 01/07/2025 | NEER UDYOG | 7.47 | 0 | 0 | 0
588 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Hiring of 1 (one) no Motor Cab (standard) commercial with Catalytic Converter Attachment with Bharat Stage as per prevalent applicable standard compliant new not older than 30 (Thirty) months from the date of 1st registration on daily hire rate basis for 12 (Twelve) months only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Assistant Engineer, Jhargram RWS Sub-Division, PHE Dte. for monitoring of JJM Works (For One Year)(1st August 2024 to 31st July2025) . | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000012/2024-2025 | 219/JRWS | 22/07/2024 | 22/07/2025 | JAGOMOHAN SETUA | 2.05 | 3.03 | 148.09 | 0
589 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Continuation Order for Hire charges of Bharat Stage-II / III Diesel Motor Cabs (Luxury Taxi) / Maruti Omni (Standard-Non-Air Conditioned) having Contract Carriage Permit from the Regional Transport Authority valid for the State of West Bengal not older than 2 years from the date of 1st Registration on daily Hire rate basis for the period from 01.07.2024 to 31.07.2024. for the Movement of Junior Engineer (RWS) under Jhargram Division, PHE Dte. The cost inclusive of all charges due to the wages of Driver, Taxes, Insurance, fees etc., as applicable. (For 1 months) | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-II | ORD/000226/2024-2025 | 636/JSD | 28/06/2024 | 29/07/2024 | JAGOMOHAN SETUA | 0.17 | 0.4 | 229.68 | 0
590 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Hire charges of Bharat Stage-II / III Diesel Motor Cabs (Luxury Taxi) / Maruti Omni (Standard-Non-Air Conditioned) having Contract Carriage Permit from the Regional Transport Authority valid for the State of West Bengal not older than 2 years from the date of 1st Registration on daily Hire rate basis for the period from 01.01.2025 to 30.06.2025. for the Movement of Junior Engineer (RWS) under Jhargram Sub-Division, PHE Dte. The cost inclusive of all charges due to the wages of Driver, Taxes, Insurance, fees etc., as applicable. (For 6 months) | Assistant Engineer | Junior Engineer-II | ORD/000327/2024-2025 | 547/JRWS | 30/12/2024 | 29/06/2025 | RAHUL DEY | 0.86 | 1.9 | 220.85 | 0
591 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Arra stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000163/2022-2023 | 1463/JMD | 19/07/2022 | 27/06/2024 | M/S B.M. ELECTRICAL | 6.86 | 5.04 | 73.42 | 100
592 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dhengbahara Stand Alone piped water supply scheme, tube well no-I of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000663/2022-2023 | 4202/JMD | 28/12/2022 | 31/01/2025 | SUBHRA ENTERPRISE | 5.78 | 3.78 | 65.42 | 100
593 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Chhota Jharia T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000614/2022-2023 | 3624/JMD | 07/12/2022 | 27/06/2024 | M/S B.M. ELECTRICAL | 5.7 | 5.01 | 87.82 | 100
594 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dhadka Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000656/2022-2023 | 4195/JMD | 28/12/2022 | 01/01/2025 | J.K. ENGINEERING CO. | 5.78 | 3.92 | 67.9 | 100
595 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Sankrail_1_1 under Jhargram Division in the District of Jhargram. [Location of Work Site - (1) Mouza - Tungadhua, J.L. - 127, No. of Unit - 1, (2) Mouza - Bhurkundi, J.L. - 128, No. of Unit - 1, (3) Mouza - Bara Kanya Diha, J.L. - 129, No. of Unit - 1 & (4) Mouza - Nischinta, J.L. - 139, No. of Unit - 2, Total = 5 Units] | Assistant Engineer | Junior Engineer Sankrail block | ORD/000016/2021-2022 | 172/MD | 01/02/2022 | 31/07/2022 | DIPAK KUMAR BAKLY | 90.06 | 75.46 | 83.79 | 95
596 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kankrajhor T/W no. -I & II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000518/2022-2023 | 3066/JMD | 28/09/2022 | 10/08/2024 | DEBJYOTI BASU | 6.79 | 4.4 | 64.9 | 100
597 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Gopiballavpur-II_2_1 under Jhargram Division in the District of Jhargram. | Assistant Engineer | Junior Engineer Gopiballavpur-II block,Junior Engineer-II | ORD/000085/2021-2022 | 301/MD | 15/02/2022 | 14/08/2022 | ASIS KUMAR SARANGI | 135.09 | 96.79 | 71.65 | 100
598 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Benachapra Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M),Junior Engineer | ORD/000693/2022-2023 | 149/JMD | 19/01/2023 | 21/03/2025 | ABHIJIT MUKHERJEE | 5.78 | 0 | 0 | 100
599 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bara Sol, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000710/2022-2023 | 260/JMD | 03/02/2023 | 29/04/2024 | M/S D.G.B. ENTERPRISE | 5.78 | 5.19 | 89.78 | 100
600 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Patina, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000010/2023-2024 | 958/JMD | 25/04/2023 | 13/12/2024 | SUJOY RANJAN BHOWMICK | 5.78 | 4.11 | 71.21 | 100
601 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Muniada T/W no. -II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000156/2023-2024 | 1967/JMD | 31/07/2023 | 07/03/2024 | RUBY ENTERPRISE | 5.78 | 5.17 | 89.45 | 100
602 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Jari Ghati Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Driller-In-Charge | Junior Engineer | ORD/000140/2023-2024 | 1832/JMD | 24/07/2023 | 19/10/2024 | SUJOY RANJAN BHOWMICK | 5.78 | 4.15 | 71.8 | 80
603 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kul Diha, Tube Well no.-III Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Driller-In-Charge | Junior Engineer | ORD/000136/2023-2024 | 1828/JMD | 24/07/2023 | 27/06/2025 | B. P. TRADING CORPORATION | 5.78 | 3.78 | 65.4 | 90
604 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kul Diha, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer | ORD/000162/2023-2024 | 1973/JMD | 31/07/2023 | 20/03/2025 | SOUMEN ELECTRIC | 5.78 | 4.15 | 71.73 | 100
605 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kalma Pukhuria, Tube Well no.-VI Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer | ORD/000126/2023-2024 | 1808/JMD | 24/07/2023 | 20/11/2024 | DEB KUMAR BASU | 5.78 | 0 | 0 | 100
606 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Gorur Ghata Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Driller-In-Charge | JE (M),Junior Engineer | ORD/000115/2023-2024 | 1796/JMD | 24/07/2023 | 20/03/2024 | BEE GEE CONSTRUCTION | 5.78 | 5.19 | 89.86 | 96
607 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Andharisol, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000157/2023-2024 | 1968/JMD | 31/07/2023 | 01/06/2024 | BALAJI CONSTRUCTION | 5.78 | 5.07 | 87.62 | 100
608 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under Jamboni Block location Id Jamboni_4_3 under Jhargram Division in the District of Jhargram. | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000149/2023-2024 | 1333/JHD | 10/08/2023 | 07/12/2024 | BISHNU PADA NANDI | 19.81 | 0 | 0 | 100
609 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Mechanical Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dhengbahara Stand Alone piped water supply scheme, tube well no-II of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000665/2022-2023 | 4204/JMD | 28/12/2022 | 01/10/2024 | M/S. NABIN GOPAL SENGUPTA | 5.78 | 0 | 0 | 100
610 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Repair of FHTC and others allied works of Bachurkhoyar PWSS (out of 45 Mini PWSS) under Nayagram Block within Jhargram Division,PHE Dte. | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000071/2024-2025 | 535/GPSD | 20/08/2024 | 10/09/2024 | TAPAS KUMAR JANA | 4.13 | 0 | 0 | 50
611 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 | New | Functional Household Tap Connection data uploading changes of different PWSS under Jhargram District in JJM_IMIS portal under Jal Jeevan Mission for July 2024 to November 2024 under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer-III | ORD/000005/2024-2025 | 128/JRWS | 12/06/2024 | 12/11/2024 | MANDAL ENTERPRISE | 4.05 | 1.67 | 41.32 | 100
Total | [13 empty] | 10756.1 | 4975.25 | 46.26