## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Midnapore Division | Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block-Gopiballavpur-I, District - Jhargram | SM/10064 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000018/2022-2023 | 2472/MD | 06/12/2022 | 06/12/2022 | Resource Division | 61.6 | 0 | 0 | 0
2 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block-Gopiballavpur-I, District - Jhargram | SM/10064 | Augmentation | Laying distribution pipe line, Providing FHTC, soil test & construction of RCC OHR of capacity 600 cum and staging height 20.00 mtr. with allied work for Augmentation of Gopiballavpur PWSS within Gopiballavpur-I Block under Jhargram Division, PHE Dte. |  |  | VCH/000028/2022-2023 |  | 26/08/2022 | 26/08/2022 | GOBINDA MAITY | 26.65 | 0 | 0 | 0
3 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block-Gopiballavpur-I, District - Jhargram | SM/10064 | Augmentation | Payment for new service connection of WBSEDCL. |  |  | VCH/000847/2022-2023 | 21/JMD/PFMS/SEP | 29/09/2022 | 29/09/2022 | WBSEDCL | 1.63 | 0 | 0 | 0
4 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block-Gopiballavpur-I, District - Jhargram | SM/10064 | Augmentation | Laying distribution pipe line,Providing FHTC, soil test & construction of R.C.C. Over Head Reservoir of capacity 600 Cum and staging height 20.00 mtr. with allied work For Augmentation of Gopiballavpur PWSS within Gopiballavpur-I Block Under Jhargram Division, P.H.E. Dte. |  |  | VCH/000021/2022-2023 |  | 12/08/2022 | 12/08/2022 | GOBINDA MAITY | 57 | 0 | 0 | 0
5 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block-Gopiballavpur-I, District - Jhargram | SM/10064 | Augmentation | Laying distribution pipe line,Providing FHTC, soil test & construction of R.C.C. Over Head Reservoir of capacity 600 Cum and staging height 20.00 mtr. with allied work For Augmentation of Gopiballavpur PWSS within Gopiballavpur-I Block Under Jhargram Division, P.H.E. Dte. |  |  | VCH/000010/2022-2023 |  | 03/08/2022 | 03/08/2022 | GOBINDA MAITY | 172.34 | 0 | 0 | 0
6 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block-Gopiballavpur-I, District - Jhargram | SM/10064 | Augmentation | Functional Household Tap Connection data uploading charges of different pwss under Jhargram District in JJM_IMIS portal under Jal Jeevan Mission for January-2023 and February-2023 under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000253/2022-2023 | 29A/JRWS | 28/12/2022 | 26/02/2023 | PROVAT KUMAR DE | 0.93 | 0.31 | 33.16 | 100
7 | JHARGRAM |  | Midnapore Division | Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block-Gopiballavpur-I, District - Jhargram | SM/10064 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000002/2022-2023 | 1044/MD | 01/06/2022 | 01/06/2022 | Resource Division | 157.59 | 0 | 0 | 0
8 | JHARGRAM |  | Midnapore Division | Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block-Gopiballavpur-I, District - Jhargram | SM/10064 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000039/2021-2022 | 498/MD | 15/03/2022 | 15/03/2022 | Resource Division | 30.36 | 0 | 0 | 0
9 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block-Gopiballavpur-I, District - Jhargram | SM/10064 | Augmentation | Restoration work due to laying pipeline along the road providing by PHE Jhargram Division under Jhargram Highway Division in the district of Jhargram. |  |  | BILL/00498/2023-2024 | BP-2023-24-346 | 22/12/2023 | 22/12/2023 | EXECUTIVE ENGINEER, PWD (ROADS) JHARGRAM | 52.47 | 0 | 0 | 0
10 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block-Gopiballavpur-I, District - Jhargram | SM/10064 | Augmentation | Restoration work for laying pipeline along the roads provided by PHE Jhargram under Jhargram Highway Division in the district of Jhargram |  |  | BILL/00054/2022-2023 | BP-2022-23-91 | 30/12/2022 | 30/12/2022 | EXECUTIVE ENGINEER, PWD (ROADS) JHARGRAM | 30 | 0 | 0 | 0
11 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block-Gopiballavpur-I, District - Jhargram | SM/10064 | Augmentation | Supply delivery of Different dia CIDF S/V for the work of ¿ Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block Gopiballavpur - I under Gopiballavpur Sub Division within Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000054/2022-2023 | 60/GPSD | 22/09/2022 | 07/10/2022 | GOBINDA MAITY | 4.79 | 4.79 | 100 | 100
12 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block-Gopiballavpur-I, District - Jhargram | SM/10064 | Augmentation | Continuation work order for Hiring of Diesel driven Commercial Covered four wheeler vehicle on daily basis along with LMV licensed driver for official purpose of Executive Engineer, Jhargram Mechanical Division, PHE Dte. | Assistant Engineer,Driller-In-Charge | JE (M),Junior Engineer | ORD/000793/2022-2023 | 641/JMD | 22/03/2023 | 22/03/2024 | SUJOY RANJAN BHOWMICK | 1.74 | 0.87 | 50 | 100
13 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block-Gopiballavpur-I, District - Jhargram | SM/10064 | Augmentation | Laying Additional Distribution Pipe line for Augmentation of Gopiballavpur PWSS to accommodate FHTC in Gopiballavpur -I Block within Jhargram District under Jhargram Division, PHE Dte. (Total Length 9615.00 Mtr. ) | Assistant Engineer | Junior Engineer-II | ORD/000121/2023-2024 | 1332/JHD | 10/08/2023 | 09/10/2023 | GOBINDA MAITY | 41.57 | 37.79 | 90.92 | 42
14 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block-Gopiballavpur-I, District - Jhargram | SM/10064 | Augmentation | Providing solarization of WBSEDCL energised pumping installation at Gopiballavpur w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | Driller-In-Charge | Junior Engineer | ORD/001369/2023-2024 | 2986/JMD | 13/03/2024 | 12/04/2024 | SAMARPITA ENGINEERING | 6.26 | 0 | 0 | 0
15 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block-Gopiballavpur-I, District - Jhargram | SM/10064 | Augmentation | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro mechanical accessories at newly sunk tube well no. I as part of augmentation of Gopiballavpur w/s scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000589/2022-2023 | 3322/JMD | 14/11/2022 | 14/03/2023 | ORIENTAL ENGINEERING CO. | 11.03 | 10.97 | 99.52 | 100
16 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block-Gopiballavpur-I, District - Jhargram | SM/10064 | Augmentation | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro mechanical accessories at newly sunk tube well no. II as part of augmentation of Gopiballavpur w/s scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000590/2022-2023 | 3323/JMD | 14/11/2022 | 14/03/2023 | DEBJYOTI BASU | 11.04 | 10.9 | 98.75 | 100
17 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block-Gopiballavpur-I, District - Jhargram | SM/10064 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Gopiballavpur PWSS (Part-II) in Gopiballavpur Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000084/2021-2022 | 275/JSD | 07/10/2021 | 22/10/2021 | M/S R. DUTTA & CO | 4.52 | 0 | 0 | 100
18 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block-Gopiballavpur-I, District - Jhargram | SM/10064 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Gopiballavpur PWSS (Part-I) in Gopiballavpur Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000083/2021-2022 | 274/JSD | 07/10/2021 | 22/10/2021 | M/S R. DUTTA & CO | 4.44 | 0 | 0 | 100
19 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block-Gopiballavpur-I, District - Jhargram | SM/10064 | Augmentation | Supply, delivery & installation of various electro-mechanical accessories for repairing & rejuvenation of pump house no.-I of Gopiballavpur w/s scheme in the dist. of Jhargram under Jhargram Mechanical Division P.H.E Dte. | Driller-In-Charge | Junior Engineer | ORD/001376/2023-2024 | 3058/JMD | 14/03/2024 | 13/04/2024 | S.S. GHORAI | 8.81 | 8.41 | 95.46 | 100
20 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block-Gopiballavpur-I, District - Jhargram | SM/10064 | Augmentation | Supply, delivery & installation of various electro-mechanical accessories for repairing & rejuvenation of pump house no.-II of Gopiballavpur w/s scheme in the dist. of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Driller-In-Charge | Junior Engineer | ORD/001370/2023-2024 | 2987/JMD | 13/03/2024 | 12/04/2024 | SOUMEN ELECTRIC | 8.81 | 8.51 | 96.7 | 100
21 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block-Gopiballavpur-I, District - Jhargram | SM/10064 | Augmentation | Laying distribution pipe line,Providing FHTC, soil test & construction of R.C.C. Over Head Reservoir of capacity 600 Cum and staging height 20.00 mtr. with allied work For Augmentation of Gopiballavpur PWSS within Gopiballavpur-I Block Under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000044/2022-2023 | 818/MD | 29/04/2022 | 28/01/2026 | GOBINDA MAITY | 732.35 | 660.65 | 90.21 | 100
Total | [13 empty] | 1425.93 | 743.22 | 52.12