## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. | SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At NAYAGRAM NO-07 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte. (LocationID : AWC_Nayagram_17_38) | Assistant Engineer | Junior Engineer Nayagram block | ORD/000204/2022-2023 | 222/JHD | 16/02/2023 | 18/03/2023 | GAUTAM SENAPATI | 11.47 | 10.22 | 89.13 | 0
2 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. | SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At ARRHA NO-11 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte. (LocationID : AWC_Nayagram_27_38) | Assistant Engineer | The Junior Engineer-IV Jhargram Sub-Division | ORD/000200/2022-2023 | 204/JHD | 10/02/2023 | 27/03/2023 | DHUMKETU ENGINEERING PRIVATE LIMITED | 32.68 | 28.24 | 86.42 | 0
3 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. | SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At PATINA NO-01 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Nayagram_36_38) | Assistant Engineer | The Junior Engineer-IV Jhargram Sub-Division | ORD/000183/2022-2023 | 164/GPSD | 20/01/2023 | 19/02/2023 | KOUSIK PATRA | 3.15 | 2.5 | 79.33 | 0
4 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. | SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At PATINA NO-01 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Nayagram_31_38) | Assistant Engineer | The Junior Engineer-IV Jhargram Sub-Division | ORD/000175/2022-2023 | 159/GPSD | 20/01/2023 | 19/02/2023 | HYDRO TECH ASSOCIATES | 4.04 | 2.77 | 68.51 | 95
5 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. | SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At MALAM NO-04 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Nayagram_12_38) | Assistant Engineer | The Junior Engineer-IV Jhargram Sub-Division | ORD/000171/2022-2023 | 155/GPSD | 20/01/2023 | 19/02/2023 | TAPAS PAL | 4.04 | 3.08 | 76.29 | 0
6 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. | SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At NAYAGRAM NO-07 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte. (LocationID : AWC_Nayagram_16_38) | Assistant Engineer |  | ORD/000201/2022-2023 | 216/JHD | 15/02/2023 | 01/04/2023 | ASIS KUMAR SARANGI | 31.61 | 10.76 | 34.04 | 60
7 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. | SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At BARA KHAKRI NO-03 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Nayagram_7_38) | Assistant Engineer | The Junior Engineer-IV Jhargram Sub-Division | ORD/000202/2022-2023 | 217/JHD | 15/02/2023 | 01/04/2023 | ASSOCIATED ENGINEERS & TRADERS | 20.91 | 11.93 | 57.06 | 62
8 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. | SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At BARA NEGUI NO-05 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Nayagram_14_38) | Assistant Engineer | The Junior Engineer-IV Jhargram Sub-Division | ORD/000172/2022-2023 | 156/GPSD | 20/01/2023 | 19/02/2023 | M/S. R.K.TRADERS | 3.96 | 2.91 | 73.49 | 0
9 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. | SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At PATINA NO-01 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Nayagram_32_38) | Assistant Engineer | The Junior Engineer-IV Jhargram Sub-Division | ORD/000181/2022-2023 | 160/GPSD | 20/01/2023 | 19/02/2023 | M/S SAGAR SAIKAT PARIA | 3.15 | 2.92 | 92.49 | 100
10 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. | SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At BARA KHAKRI NO-03 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Nayagram_8_38) | Assistant Engineer | The Junior Engineer-IV Jhargram Sub-Division | ORD/000168/2022-2023 | 152/GPSD | 20/01/2023 | 19/02/2023 | IMRAN KHAN | 4.52 | 0 | 0 | 0
11 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. | SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At MALAM NO-04 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Nayagram_10_38) | Assistant Engineer | The Junior Engineer-IV Jhargram Sub-Division | ORD/000169/2022-2023 | 153/GPSD | 20/01/2023 | 19/02/2023 | S.R. ENTERPRISE | 4.02 | 3.58 | 88.98 | 0
12 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. | SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At PATINA NO-01 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Nayagram_35_38) | Assistant Engineer | The Junior Engineer-IV Jhargram Sub-Division | ORD/000182/2022-2023 | 163/GPSD | 20/01/2023 | 19/02/2023 | JULFIKAR ALI KHAN | 3.15 | 2.44 | 77.32 | 100
13 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. | SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At CHANDABILA GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(Location ID : AWC_Nayagram_4_38) | Assistant Engineer |  | ORD/000193/2022-2023 | 212/JHD | 15/02/2023 | 17/03/2023 | MAHAVIR SAMPARK PVT. LTD. | 11.56 | 9.23 | 79.81 | 100
14 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. | SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At JAMIRAPAL NO-08 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte. (LocationID : AWC_Nayagram_19_38) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000225/2022-2023 | 434/JHD | 22/03/2023 | 06/05/2023 | TAPAN KUMAR UPADHYAY | 15.16 | 13.28 | 87.65 | 0
15 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. | SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At BALIGERIA NO-10 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Nayagram_24_38) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000022/2023-2024 | 852/JHD | 08/06/2023 | 23/07/2023 | ASIS KUMAR SARANGI | 77.99 | 39.07 | 50.1 | 65
16 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. | SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At CHANDABILA GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Nayagram_5_38) | Assistant Engineer | The Junior Engineer-IV Jhargram Sub-Division | ORD/000167/2022-2023 | 151/GPSD | 20/01/2023 | 19/02/2023 | MAA LAXMI ENTERPRISE | 3.13 | 2.32 | 74.08 | 100
17 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. | SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At PATINA NO-01 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte. (LocationID : AWC_Nayagram_38_38) | Assistant Engineer |  | ORD/000205/2022-2023 | 223/JHD | 16/02/2023 | 02/04/2023 | BRAJENDRANATH SENAPATI | 25.55 | 23.34 | 91.32 | 100
18 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. | SM/10349 | Anganwadi | Water Supply Arrangement for AnganwadiCenters At BALIGERIANO-10 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Nayagram_25_38) | Assistant Engineer |  | ORD/000194/2022-2023 | 213/JHD | 15/02/2023 | 01/04/2023 | PROVAT KUMAR DE | 20.48 | 17.89 | 87.36 | 100
19 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. | SM/10349 | Anganwadi | Water Supply Arrangement for AnganwadiCentersAt CHANDABILA GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(Location ID : AWC_Nayagram_1_38) | Assistant Engineer | The Junior Engineer-IV Jhargram Sub-Division | ORD/000198/2022-2023 | 214/JHD | 15/02/2023 | 17/03/2023 | BIDYUT KUMAR SANTRA | 12.97 | 11.62 | 89.6 | 100
20 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. | SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At JAMIRAPAL NO-08 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Nayagram_20_38) v | Assistant Engineer | The Junior Engineer-IV Jhargram Sub-Division | ORD/000173/2022-2023 | 157/GPSD | 20/01/2023 | 19/02/2023 | KOUSIK MUKHERJEE | 3.06 | 2.85 | 93.04 | 100
21 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. | SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At MALAM NO-04 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Nayagram_11_38) | Assistant Engineer |  | ORD/000170/2022-2023 | 154/GPSD | 20/01/2023 | 19/02/2023 | BRAJENDRANATH SENAPATI | 4 | 3.6 | 90 | 100
22 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. | SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At PATINA NO-01 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Nayagram_37_38) | Assistant Engineer | The Junior Engineer-IV Jhargram Sub-Division | ORD/000184/2022-2023 | 165/GPSD | 20/01/2023 | 19/02/2023 | SOURAV MASANTA | 3.16 | 2.4 | 76.01 | 100
23 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. | SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At CHANDABILA GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Nayagram_3_38) | Assistant Engineer | The Junior Engineer-IV Jhargram Sub-Division | ORD/000189/2022-2023 | 146/JHD | 03/02/2023 | 05/03/2023 | ENVOTECH INFRA SOLUTION | 12.11 | 8.69 | 71.78 | 0
24 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. | SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers at ARRHA No-11 GP under Nayagram block in Jhargram District under Jhargram Division PHE Dte. (Location ID: AWC_Nayagram _26_38) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000018/2023-2024 | 792/JHD | 31/05/2023 | 15/07/2023 | PROVAT KUMAR DE | 51.49 | 46.4 | 90.11 | 66
25 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. | SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At PATINA NO-01 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Nayagram_34_38) | Assistant Engineer | The Junior Engineer-IV Jhargram Sub-Division | ORD/000178/2022-2023 | 162/GPSD | 20/01/2023 | 19/02/2023 | ASHIS SHEE | 3.14 | 2.33 | 74.09 | 0
26 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. | SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At BERAJAL NO-09 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte. (LocationID : AWC_Nayagram_21_38) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000215/2022-2023 | 345/JHD | 10/03/2023 | 24/04/2023 | LALIT BIHARI MAITY | 52.61 | 45.25 | 86.02 | 100
27 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. | SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At KHARIKAMATHANI NO-06 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte. (LocationID : AWC_Nayagram_29_38) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000027/2023-2024 | 855/JHD | 08/06/2023 | 23/07/2023 | SRIMANTA KUMAR DE | 50.58 | 44.04 | 87.06 | 100
28 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. | SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At BERAJAL NO-09 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Nayagram_22_38) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000023/2023-2024 | 853/JHD | 08/06/2023 | 08/07/2023 | RITESH AGARWALL | 11.53 | 10.5 | 91.06 | 50
29 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. | SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At BARA KHAKRI NO-03 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Nayagram_6_38) | Assistant Engineer | Junior Engineer Nayagram block | ORD/000002/2023-2024 | 565/JHD | 24/04/2023 | 08/06/2023 | SAI TUBE CO. | 52.05 | 43.74 | 84.04 | 80
30 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. | SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At CHANDRAREKHA NO-12 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte. (LocationID : AWC_Nayagram_23_38) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000075/2023-2024 | 1112/JHD | 18/07/2023 | 01/09/2023 | M/S BLUE BIRD | 20.54 | 18.7 | 91.05 | 100
31 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. | SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At KHARIKAMATHANI NO-06 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte. (LocationID : AWC_Nayagram_30_38) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000065/2023-2024 | 1092/JHD | 14/07/2023 | 28/08/2023 | SAI TUBE CO. | 52.7 | 48.65 | 92.31 | 100
32 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. | SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At PATINA NO-01 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Nayagram_33_38) | Assistant Engineer |  | ORD/000177/2022-2023 | 161/GPSD | 20/01/2023 | 19/02/2023 | DEBDATTA MANNA | 3 | 2.93 | 97.66 | 0
33 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. | SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At CHANDABILA GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Nayagram_2_38) | Assistant Engineer | Junior Engineer-II | ORD/000207/2022-2023 | 267/JHD | 21/02/2023 | 23/03/2023 | TAPAS KUMAR JANA | 12.1 | 10.68 | 88.26 | 100
34 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. | SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At BARA NEGUI NO-05 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Nayagram_13_38) ) 3rd Call,( Ref eNIT_14 of 2022-23 2nd Call , SL No.-2 ) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000342/2023-2024 | 1883/JHD | 03/11/2023 | 18/12/2023 | SUJOY RANJAN BHOWMICK | 53.17 | 42.62 | 80.15 | 100
35 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. | SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At MALAM NO-04 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Nayagram_9_38) 3rd Call, ( Ref eNIT_14 of 2022-23 2nd Call , SL No.-1 ) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000388/2023-2024 | 2071/JHD | 08/12/2023 | 22/01/2024 | TAPAN KUMAR MANDAL | 42.47 | 37.02 | 87.18 | 100
36 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. | SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At NAYAGRAM NO-07 GP under Nayagram Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Nayagram_15_38) ) 3rd Call,( Ref eNIT_14 of 2022-23 2nd Call , SL No.-3 ) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000352/2023-2024 | 1952/JHD | 22/11/2023 | 06/01/2024 | JOY GURU TRADING | 31.6 | 17.8 | 56.31 | 70
37 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(304 nos.) within Nayagram Block under Jhargram District. | SM/10349 | Anganwadi | Water Supply Arrangement for Anganwadi Centers 1 1 At JAMIRAPAL NO-08 GP under Nayagram Block in Jhargram District Jhargram Division PHE Dte. (LocationID: AWC_Nayagram_18_38) (Ref. eNit No._14 of 2022-23 2nd call SL-4) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000359/2023-2024 | 1995/JHD | 01/12/2023 | 15/01/2024 | THE BUSINESS ENGINEERS INDIA | 32.29 | 25.48 | 78.93 | 100
Total | [13 empty] | 785.18 | 611.8 | 77.92