## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers (137 nos.) within Gopiballavpur-II Block under Jhargram District. | SM/10352 | Anganwadi | Water Supply Arrangement for 137 Nos Anganwadi Centers At Gopiballavpur-II Block in Jhargram District under Jhargarm Division, PHE Dte. | Assistant Engineer | Junior Engineer Gopiballavpur-II block | ORD/000079/2022-2023 | 432/JHD | 04/11/2022 | 02/02/2023 | CHAKRABORTTI ENTERPRISE | 186.54 | 166.69 | 89.36 | 100
Total | [13 empty] | 186.54 | 166.69 | 89.36