## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. | SM/10353 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At DUBRA GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Jamboni_16_32) | Assistant Engineer | Junior Engineer-I,Junior Engineer-II | ORD/000144/2022-2023 | 616/JHD | 24/11/2022 | 24/12/2022 | MASUM CONSTRUCTION | 10.01 | 8.05 | 80.44 | 0
2 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. | SM/10353 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At KAPGARI GP under Jamboni block in Jhargram Division PHE Dte. (Location ID : AWC_jamboni_21_32) | Assistant Engineer | Junior Engineer-I,Junior Engineer-II | ORD/000148/2022-2023 | 675/JHD | 13/12/2022 | 27/01/2023 | TAPAN KUMAR MANDAL | 22.57 | 22.56 | 99.94 | 0
3 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. | SM/10353 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At JAMBONI GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Jamboni_22_32)" | Assistant Engineer | Junior Engineer-I,Junior Engineer-II | ORD/000134/2022-2023 | 641/JSD | 23/11/2022 | 23/12/2022 | M/S ANKITA CONSTRUCTION | 2.37 | 1.68 | 70.66 | 0
4 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. | SM/10353 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At CHICHIRA GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Jamboni_4_32)" | Assistant Engineer | Junior Engineer-I,Junior Engineer-II | ORD/000126/2022-2023 | 634/JSD | 23/11/2022 | 23/12/2022 | ENVOTECH INFRA SOLUTION | 4.38 | 4.31 | 98.55 | 0
5 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. | SM/10353 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At JAMBONI GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Jamboni_27_32) | Assistant Engineer | Junior Engineer-I,Junior Engineer-II | ORD/000090/2022-2023 | 454/JHD | 11/11/2022 | 11/12/2022 | A.R. ENTERPRISE | 5 | 4.31 | 86.19 | 0
6 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. | SM/10353 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At CHILKIGARH GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Jamboni_6_32)" | Assistant Engineer | Junior Engineer-I,Junior Engineer-II | ORD/000128/2022-2023 | 636/JSD | 23/11/2022 | 23/12/2022 | M/S MILAN DATTA | 3.19 | 3.01 | 94.21 | 0
7 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. | SM/10353 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At CHILKIGARH GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Jamboni_5_32)" | Assistant Engineer | Junior Engineer-I,Junior Engineer-II | ORD/000127/2022-2023 | 635/JSD | 23/11/2022 | 23/12/2022 | M/S TARUN MAHATA | 3.19 | 2.63 | 82.25 | 0
8 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. | SM/10353 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At DUBRA GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Jamboni_17_32) | Assistant Engineer | Junior Engineer-I,Junior Engineer-II | ORD/000119/2022-2023 | 626/JHD | 28/11/2022 | 28/12/2022 | M/S BAKLY CONSTRUCTION | 5.69 | 5.54 | 97.29 | 0
9 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. | SM/10353 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At KENDANGRI GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte. (LocationID : AWC_Jamboni_29_32) | Assistant Engineer | Junior Engineer-I,Junior Engineer-II | ORD/000155/2022-2023 | 702/JHD | 15/12/2022 | 29/01/2023 | JYOTY SOLAR POWER | 18.01 | 14.36 | 79.76 | 0
10 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. | SM/10353 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At JAMBONI GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Jamboni_23_32)" |  | Junior Engineer-I,Junior Engineer-II | ORD/000135/2022-2023 | 642/JSD | 23/11/2022 | 23/12/2022 | TAPAS PAL | 2.98 | 1.54 | 51.76 | 0
11 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. | SM/10353 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At CHILKIGARH GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Jamboni_12_32) |  | Junior Engineer-I,Junior Engineer-II | ORD/000117/2022-2023 | 630/JHD | 28/11/2022 | 28/12/2022 | DEBASISH DOGRA | 6.19 | 5.24 | 84.64 | 0
12 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. | SM/10353 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At CHICHIRA GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Jamboni_3_32)" |  | Junior Engineer-I,Junior Engineer-II | ORD/000125/2022-2023 | 633/JSD | 23/11/2022 | 23/12/2022 | S.R. ENTERPRISE | 3.77 | 3.35 | 88.77 | 0
13 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. | SM/10353 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At PARIHATI GP under Jamboni Block in Jhargram District under Jhargram Division P.H.E Dte. ( Location ID : AWC_Jamboni_32_32) | Assistant Engineer | Junior Engineer-I | ORD/000152/2022-2023 | 678/JHD | 13/12/2022 | 12/01/2023 | SUNIL KUMAR MANDAL | 15.88 | 6.91 | 43.53 | 0
14 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. | SM/10353 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At CHILKIGARH GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Jamboni_9_32)" | Assistant Engineer |  | ORD/000132/2022-2023 | 639/JSD | 23/11/2022 | 23/12/2022 | TAPAS KUMAR JANA | 3.69 | 2.48 | 67.35 | 0
15 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. | SM/10353 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At JAMBONI GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Jamboni_24_32)" | Assistant Engineer |  | ORD/000136/2022-2023 | 643/JSD | 23/11/2022 | 23/12/2022 | SUTANU DE | 2.99 | 1.98 | 66.21 | 0
16 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. | SM/10353 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At CHILKIGARH GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Jamboni_8_32)" | Assistant Engineer |  | ORD/000131/2022-2023 | 638/JSD | 23/11/2022 | 23/12/2022 | KARTIK DUTTA | 3.18 | 2.42 | 76.13 | 0
17 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. | SM/10353 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At CHICHIRA GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Jamboni_2_32)" | Assistant Engineer |  | ORD/000124/2022-2023 | 632/JSD | 23/11/2022 | 23/12/2022 | SUBHAMAY DANDAPAT | 3.59 | 3.27 | 91.04 | 0
18 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. | SM/10353 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At CHICHIRA GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Jamboni_1_32)" | Assistant Engineer |  | ORD/000114/2022-2023 | 631/JSD | 23/11/2022 | 23/12/2022 | IMRAN KHAN | 3.89 | 0 | 0 | 0
19 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. | SM/10353 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At KAPGARI GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte. (LocationID : AWC_Jamboni_20_32) | Assistant Engineer | Junior Engineer-II | ORD/000156/2022-2023 | 703/JHD | 15/12/2022 | 29/01/2023 | SUJOY RANJAN BHOWMICK | 25.93 | 19.82 | 76.44 | 0
20 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. | SM/10353 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At CHILKIGARH GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte.(Location ID : AWC_Jamboni_11_32) | Assistant Engineer | Junior Engineer-I,Junior Engineer-II | ORD/000089/2022-2023 | 453/JHD | 11/11/2022 | 11/12/2022 | ENVOTECH INFRA SOLUTION | 5.7 | 5.32 | 93.37 | 0
21 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. | SM/10353 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At JAMBONI GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Jamboni_26_32)" | Assistant Engineer |  | ORD/000138/2022-2023 | 645/JSD | 23/11/2022 | 23/12/2022 | DEBABRATA DUTTA | 3.18 | 1.8 | 56.55 | 0
22 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. | SM/10353 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At JAMBONI GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Jamboni_25_32)" | Assistant Engineer |  | ORD/000137/2022-2023 | 644/JSD | 23/11/2022 | 23/12/2022 | HRITWIK DUTTA | 3.09 | 1.73 | 55.91 | 0
23 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. | SM/10353 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At CHILKIGARH GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Jamboni_7_32)" | Assistant Engineer |  | ORD/000130/2022-2023 | 637/JSD | 23/11/2022 | 23/12/2022 | ARUSHI CONSTRUCTION | 3.09 | 3.09 | 99.97 | 100
24 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. | SM/10353 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At KENDANGRI GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Jamboni_30_32) | Assistant Engineer | Junior Engineer-I,Junior Engineer-II | ORD/000121/2022-2023 | 631/JHD | 28/11/2022 | 12/01/2023 | MANISHIKA CONSTRUCTION | 33.51 | 25.88 | 77.22 | 100
25 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. | SM/10353 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At DHARSA GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte.(Location ID : AWS_Jamboni_13_32) |  | Junior Engineer-I,Junior Engineer-II | ORD/000149/2022-2023 | 674/JHD | 13/12/2022 | 27/01/2023 | GARHBETA-1 UNEMPLOYED YOUTH ENGINEERS CO-OPERATIVE SOCIETY LTD. | 19.41 | 15.48 | 79.76 | 90
26 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. | SM/10353 | Anganwadi | Water Supply Arrangement for Anganwadi Centers at JAMBONI GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer-I,Junior Engineer-II | ORD/000162/2022-2023 | 767/JHD | 30/12/2022 | 13/02/2023 | NRIPENDRA NATH SINGHA | 21.73 | 13.73 | 63.17 | 100
27 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. | SM/10353 | Anganwadi | Water Supply Arrangement for Anganwadi centers At LALBANDH GP under jamboni Block in Jhargram District under Jhargram Division PHE Dte.(Location ID : AWC_Jamboni_15_32) | Assistant Engineer | Junior Engineer-I,Junior Engineer-II | ORD/000164/2022-2023 | 768/JHD | 30/12/2022 | 29/01/2023 | NIRMAL DUTTA | 20.13 | 11.21 | 55.69 | 100
28 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. | SM/10353 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At DURBA GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte (Location : AWC_Jamboni_18_32) | Assistant Engineer | Junior Engineer-I,Junior Engineer-II | ORD/000116/2022-2023 | 628/JHD | 28/11/2022 | 12/01/2023 | BIDYUT KUMAR SANTRA | 17.28 | 8.75 | 50.62 | 100
29 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. | SM/10353 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At PARIHATI GP under Jamboni block in Jhargram Division PHE Dte. (Location ID : AWC_jamboni_31_32) | Assistant Engineer | Junior Engineer-II | ORD/000150/2022-2023 | 677/JHD | 13/12/2022 | 12/01/2023 | J.S.S. ENTERPRISE | 13.49 | 7.8 | 57.83 | 100
30 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. | SM/10353 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At DUBRA GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Jamboni_14_32)" | Assistant Engineer | Junior Engineer-II | ORD/000133/2022-2023 | 640/JSD | 23/11/2022 | 23/12/2022 | M/S R.K. CONTRACTORY | 3.67 | 0.87 | 23.69 | 50
31 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(236 nos) within Jamboni Block under Jhargram District. | SM/10353 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At GIDHNI GP under Jamboni Block in Jhargram District under Jhargram Division PHE Dte.(LocationID : AWC_Jamboni_19_32) | Assistant Engineer | Junior Engineer-II | ORD/000120/2022-2023 | .625/JHD | 28/11/2022 | 12/01/2023 | BISHNU PADA NANDI | 27.91 | 9.24 | 33.09 | 70
Total | [13 empty] | 318.7 | 218.35 | 68.51