## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. | SM/10355 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At DAHIJURI GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Binpur-I_13_20)" | Assistant Engineer | Junior Engineer-III | ORD/000108/2022-2023 | 626/JSD | 23/11/2022 | 23/12/2022 | ASHIS SHEE | 3.03 | 2.42 | 79.87 | 0
2 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. | SM/10355 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At DAHIJURI GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Binpur-I_10_20)" |  | Junior Engineer-III | ORD/000139/2022-2023 | 623/JSD | 23/11/2022 | 23/12/2022 | M/S PIJUSH PAL | 3.1 | 2.25 | 72.51 | 0
3 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. | SM/10355 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At DAHIJURI GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Binpur-I_8_20)" | Assistant Engineer | Junior Engineer Binpur-I block | ORD/000104/2022-2023 | 621/JSD | 23/11/2022 | 23/12/2022 | MAHAVIR SAMPARK PVT. LTD. | 2.96 | 0 | 0 | 0
4 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. | SM/10355 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At BINPUR GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Binpur-I_2_20) | Assistant Engineer | Junior Engineer Binpur-I block,Junior Engineer-III | ORD/000122/2022-2023 | 624/JHD | 28/11/2022 | 28/12/2022 | DHUMKETU ENGINEERING PRIVATE LIMITED | 10.99 | 8.59 | 78.13 | 0
5 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. | SM/10355 | Anganwadi | Acceptance-Cum-Work Order "Water Supply Arrangement for Anganwadi Centers At DAHIJURI GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Binpur-I_11_20)" | Assistant Engineer | Junior Engineer Binpur-I block | ORD/000106/2022-2023 | 624/JSD | 23/11/2022 | 23/12/2022 | BHOWMIK CONSTRUCTION | 3.19 | 3.01 | 94.36 | 100
6 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. | SM/10355 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At BELATIKRI GP under Binpur-I Block in Jhargram District under Jhargrm Division PHE Dte. (Location ID : AWS_Binpur-I_5_20) | Assistant Engineer | Junior Engineer Binpur-I block,Junior Engineer-III | ORD/000151/2022-2023 | 676/JHD | 13/12/2022 | 27/01/2023 | NIMAI HAZRA | 57.24 | 40.02 | 69.92 | 80
7 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. | SM/10355 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At BINPUR GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte.(Location ID : AWC_Binpur-I_4_20) | Assistant Engineer | Junior Engineer Binpur-I block,Junior Engineer-III | ORD/000118/2022-2023 | 629/JHD | 28/11/2022 | 12/01/2023 | NIMAI LAL GURIA | 16.92 | 14.63 | 86.44 | 100
8 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. | SM/10355 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At ANDHARIA GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte.(Location ID : AWC_Binpur-I_6_20) | Assistant Engineer | Junior Engineer Binpur-I block,Junior Engineer-III | ORD/000085/2022-2023 | 450/JHD | 11/11/2022 | 26/12/2022 | SUNIL DULE | 51.83 | 26.14 | 50.43 | 25
9 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. | SM/10355 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At DAHIJURI GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Binpur-I_14_20)" | Assistant Engineer | Junior Engineer-III | ORD/000109/2022-2023 | 627/JSD | 23/11/2022 | 23/12/2022 | MANDAL ENTERPRISE | 3.16 | 1.49 | 47.12 | 100
10 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. | SM/10355 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At DAHIJURI GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Binpur-I_15_20)" | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000110/2022-2023 | 628/JSD | 23/11/2022 | 23/12/2022 | SANKAR KUMAR NAG | 3.68 | 1.73 | 46.91 | 100
11 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. | SM/10355 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At DAHIJURI GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Binpur-I_17_20)" | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000112/2022-2023 | 630/JSD | 23/11/2022 | 23/12/2022 | SAUBHIK KUMAR NAG | 4.52 | 2.21 | 48.86 | 100
12 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. | SM/10355 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At DAHIJURI GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Binpur-I_9_20)" | Assistant Engineer | Junior Engineer Binpur-I block,Junior Engineer-III | ORD/000105/2022-2023 | 622/JSD | 23/11/2022 | 23/12/2022 | SAMIR PATRA | 3.06 | 3.06 | 99.96 | 100
13 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. | SM/10355 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At DAHIJURI GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Binpur-I_16_20)" | Assistant Engineer | Junior Engineer Binpur-I block | ORD/000111/2022-2023 | 629/JSD | 23/11/2022 | 23/12/2022 | S.B.TRADERS | 4.03 | 0.99 | 24.53 | 90
14 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. | SM/10355 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At LALGARH and SIJUA GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte.(Location ID : AWC_Binpur-I_19_20) | Assistant Engineer | Junior Engineer Binpur-I block,Junior Engineer-III | ORD/000086/2022-2023 | 451/JHD | 11/11/2022 | 26/12/2022 | SUNIL DULE | 62.36 | 27.09 | 43.45 | 70
15 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. | SM/10355 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At RAMGARH GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte.(Location ID : AWC_Binpur-I_20_20) | Assistant Engineer | Junior Engineer Binpur-I block,Junior Engineer-III | ORD/000087/2022-2023 | 452/JHD | 11/11/2022 | 26/12/2022 | SUNIL DULE | 63.21 | 27.78 | 43.95 | 70
16 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. | SM/10355 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At BINPUR GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Binpur-I_1_20)" | Assistant Engineer | Junior Engineer Binpur-I block | ORD/000097/2022-2023 | 619/JSD | 23/11/2022 | 23/12/2022 | SOURABH KAR | 4.71 | 4.56 | 96.82 | 100
17 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. | SM/10355 | Anganwadi | Acceptance-Cum-Work Order For Water Supply Arrangement for Anganwadi Centers At DAHIJURI GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Binpur-I_7_20) | Assistant Engineer | Junior Engineer Binpur-I block | ORD/000103/2022-2023 | 620/JSD | 23/11/2022 | 23/12/2022 | M/S S.R. & COMPANY | 3.18 | 3.11 | 97.86 | 100
18 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. | SM/10355 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At DAHIJURI GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Binpur-I_12_20)" | Assistant Engineer | Junior Engineer Binpur-I block | ORD/000107/2022-2023 | 625/JSD | 23/11/2022 | 23/12/2022 | RAMENDRA NATH KAR | 3.16 | 3.06 | 96.8 | 100
19 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. | SM/10355 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At BINPUR GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Binpur-I_3_20) | Assistant Engineer | Junior Engineer Binpur-I block | ORD/000113/2022-2023 | 623/JHD | 28/11/2022 | 12/01/2023 | BIDYUT KUMAR SANTRA | 16.29 | 6.65 | 40.84 | 90
20 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. | SM/10355 | Anganwadi | Water Supply Arrangement for Anganwadi Centers at NEPURA, BAITA and DHARAMPUR GP under Binpur-I Block in Jhargram District under Jhargram Division, PHE Dte. ( Location ID L AWC_Binpur-I_18_20) | Assistant Engineer | Junior Engineer-III | ORD/000092/2023-2024 | 1144/JHD | 21/07/2023 | 04/09/2023 | SAIKAT DANDAPAT | 75.97 | 12.39 | 16.31 | 50
Total | [13 empty] | 396.6 | 191.18 | 48.2