## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. | SM/10355 | Anganwadi | Acceptance-Cum-Work Order "Water Supply Arrangement for Anganwadi Centers At DAHIJURI GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Binpur-I_11_20)" | Assistant Engineer | Junior Engineer Binpur-I block | ORD/000106/2022-2023 | 624/JSD | 23/11/2022 | 23/12/2022 | BHOWMIK CONSTRUCTION | 3.19 | 0 | 0 | 100
2 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. | SM/10355 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At BELATIKRI GP under Binpur-I Block in Jhargram District under Jhargrm Division PHE Dte. (Location ID : AWS_Binpur-I_5_20) | Assistant Engineer | Junior Engineer Binpur-I block,Junior Engineer-III | ORD/000151/2022-2023 | 676/JHD | 13/12/2022 | 27/01/2023 | NIMAI HAZRA | 57.24 | 24.81 | 43.35 | 80
3 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. | SM/10355 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At DAHIJURI GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Binpur-I_13_20)" | Assistant Engineer | Junior Engineer-III | ORD/000108/2022-2023 | 626/JSD | 23/11/2022 | 23/12/2022 | ASHIS SHEE | 3.03 | 2.42 | 79.87 | 0
4 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. | SM/10355 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At DAHIJURI GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Binpur-I_10_20)" |  | Junior Engineer-III | ORD/000139/2022-2023 | 623/JSD | 23/11/2022 | 23/12/2022 | M/S PIJUSH PAL | 3.1 | 2.25 | 72.51 | 0
5 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. | SM/10355 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At BINPUR GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Binpur-I_2_20) | Assistant Engineer | Junior Engineer Binpur-I block,Junior Engineer-III | ORD/000122/2022-2023 | 624/JHD | 28/11/2022 | 28/12/2022 | DHUMKETU ENGINEERING PRIVATE LIMITED | 10.99 | 8.59 | 78.13 | 0
6 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. | SM/10355 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At DAHIJURI GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Binpur-I_9_20)" | Assistant Engineer | Junior Engineer Binpur-I block,Junior Engineer-III | ORD/000105/2022-2023 | 622/JSD | 23/11/2022 | 23/12/2022 | SAMIR PATRA | 3.06 | 3.06 | 99.96 | 100
7 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. | SM/10355 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At DAHIJURI GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Binpur-I_14_20)" | Assistant Engineer | Junior Engineer-III | ORD/000109/2022-2023 | 627/JSD | 23/11/2022 | 23/12/2022 | MANDAL ENTERPRISE | 3.16 | 1.49 | 47.12 | 100
8 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. | SM/10355 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At DAHIJURI GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Binpur-I_16_20)" | Assistant Engineer | Junior Engineer Binpur-I block | ORD/000111/2022-2023 | 629/JSD | 23/11/2022 | 23/12/2022 | S.B.TRADERS | 4.03 | 0 | 0 | 100
9 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. | SM/10355 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At ANDHARIA GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte.(Location ID : AWC_Binpur-I_6_20) | Assistant Engineer | Junior Engineer Binpur-I block,Junior Engineer-III | ORD/000085/2022-2023 | 450/JHD | 11/11/2022 | 26/12/2022 | SUNIL DULE | 51.83 | 14.83 | 28.61 | 25
10 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. | SM/10355 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At LALGARH and SIJUA GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte.(Location ID : AWC_Binpur-I_19_20) | Assistant Engineer | Junior Engineer Binpur-I block,Junior Engineer-III | ORD/000086/2022-2023 | 451/JHD | 11/11/2022 | 26/12/2022 | SUNIL DULE | 62.36 | 17.8 | 28.54 | 80
11 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. | SM/10355 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At BINPUR GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Binpur-I_1_20)" | Assistant Engineer | Junior Engineer Binpur-I block | ORD/000097/2022-2023 | 619/JSD | 23/11/2022 | 23/12/2022 | SOURABH KAR | 4.71 | 4.56 | 96.82 | 100
12 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. | SM/10355 | Anganwadi | Acceptance-Cum-Work Order For Water Supply Arrangement for Anganwadi Centers At DAHIJURI GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Binpur-I_7_20) | Assistant Engineer | Junior Engineer Binpur-I block | ORD/000103/2022-2023 | 620/JSD | 23/11/2022 | 23/12/2022 | M/S S.R. & COMPANY | 3.18 | 3.11 | 97.86 | 100
13 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. | SM/10355 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At DAHIJURI GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Binpur-I_8_20)" | Assistant Engineer | Junior Engineer Binpur-I block | ORD/000104/2022-2023 | 621/JSD | 23/11/2022 | 23/12/2022 | MAHAVIR SAMPARK PVT. LTD. | 2.96 | 0 | 0 | 100
14 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. | SM/10355 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At DAHIJURI GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Binpur-I_12_20)" | Assistant Engineer | Junior Engineer Binpur-I block | ORD/000107/2022-2023 | 625/JSD | 23/11/2022 | 23/12/2022 | RAMENDRA NATH KAR | 3.16 | 3.06 | 96.8 | 100
15 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. | SM/10355 | Anganwadi | Water Supply Arrangement for Anganwadi Centers at NEPURA, BAITA and DHARAMPUR GP under Binpur-I Block in Jhargram District under Jhargram Division, PHE Dte. ( Location ID L AWC_Binpur-I_18_20) | Assistant Engineer | Junior Engineer-III | ORD/000092/2023-2024 | 1144/JHD | 21/07/2023 | 04/09/2023 | SAIKAT DANDAPAT | 75.97 | 0 | 0 | 60
16 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. | SM/10355 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At DAHIJURI GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Binpur-I_15_20)" | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000110/2022-2023 | 628/JSD | 23/11/2022 | 23/12/2022 | SANKAR KUMAR NAG | 3.68 | 0 | 0 | 100
17 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. | SM/10355 | Anganwadi | Acceptance-Cum-Work Order for "Water Supply Arrangement for Anganwadi Centers At DAHIJURI GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Binpur-I_17_20)" | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000112/2022-2023 | 630/JSD | 23/11/2022 | 23/12/2022 | SAUBHIK KUMAR NAG | 4.52 | 0 | 0 | 100
18 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. | SM/10355 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At BINPUR GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte.(Location ID : AWC_Binpur-I_4_20) | Assistant Engineer | Junior Engineer Binpur-I block,Junior Engineer-III | ORD/000118/2022-2023 | 629/JHD | 28/11/2022 | 12/01/2023 | NIMAI LAL GURIA | 16.92 | 11.9 | 70.35 | 100
19 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. | SM/10355 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At RAMGARH GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte.(Location ID : AWC_Binpur-I_20_20) | Assistant Engineer | Junior Engineer Binpur-I block,Junior Engineer-III | ORD/000087/2022-2023 | 452/JHD | 11/11/2022 | 26/12/2022 | SUNIL DULE | 63.21 | 16.84 | 26.64 | 90
20 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. | SM/10355 | Anganwadi | Water Supply Arrangement for Anganwadi Centers At BINPUR GP under Binpur-I Block in Jhargram District under Jhargram Division PHE Dte. (Location ID : AWC_Binpur-I_3_20) | Assistant Engineer | Junior Engineer Binpur-I block | ORD/000113/2022-2023 | 623/JHD | 28/11/2022 | 12/01/2023 | BIDYUT KUMAR SANTRA | 16.29 | 4.19 | 25.73 | 100
21 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(279 nos.) within Binpur-I Block under Jhargram District. | SM/10355 | Anganwadi | Arrangement for supporting structureof 1000 Lit PVC water storage tank for 1) Loagaon AWC(19344030210) at Binpur GP & 2)Providing necessary water supply arrangement within Anganwadi Center with PVC pipes (medium duty conforming to ASTMD - 1785) and G.I. pipe, supplying, installation and lowering in position with column pipe of Submersible pumping machineries of 1.0 HP with varying head & discharge of Crompton/ KSB or other renowned make conforming to latest BIS codes with control panel and all necessary electrical connections, supplying & installation of P.V.C. water storage tank of approved quality of 1000 litre capacity (to be installed at roof top of Anganwadi building) and construction of Drains / Pipe, Soak Pit etc all complete for Rathbera AWC (19344030715) at Dahijuri G.P. under Binpur-I Block in Jhargram District under Jhargram Division ,PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram Sub-Division | ORD/000356/2024-2025 | 212/JSD | 07/03/2025 | 21/03/2025 | SAURABH KAR | 1.39 | 0 | 0 | 100
Total | [13 empty] | 397.99 | 118.92 | 29.88