## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Jhargram Division | Model Water Supply System for School Located within the command area of PWSS & Source Less School(106 nos) Beyond Command Area of PWSS for District Jhargram. | SM/10358 | School | Survey & Collection of Data Through Mobile App Regarding Availability of Drinking Water, Sanitation Facilities & other Parameters in Primary, Upper Primary School, Anganwadi Centers under Jhargram Division PHE Dte. | Assistant Engineer Headquarter |  | ORD/000048/2022-2023 | 176/JHD | 12/08/2022 | 11/09/2022 | ARUNALOY SCIENTIFIC HOUSE | 4.59 | 4.59 | 100 | 100
2 | JHARGRAM |  | Jhargram Division | Model Water Supply System for School Located within the command area of PWSS & Source Less School(106 nos) Beyond Command Area of PWSS for District Jhargram. | SM/10358 | School | Creation of Water Supply System at Different Sourceless school in Binpur-II and Jamboni Block with DTH tubewell within Jhargram District under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000041/2022-2023 | 273/JHD | 12/09/2022 | 03/10/2022 | SAIKAT DANDAPAT | 22.83 | 21.62 | 94.73 | 0
3 | JHARGRAM |  | Jhargram Division | Model Water Supply System for School Located within the command area of PWSS & Source Less School(106 nos) Beyond Command Area of PWSS for District Jhargram. | SM/10358 | School | Water Supply System at Different Sourceless school in Binpur-I Block within Jhargram District under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer-III | ORD/000024/2023-2024 | 854/JHD | 08/06/2023 | 23/07/2023 | RITESH AGARWALL | 22.7 | 17.81 | 78.49 | 90
4 | JHARGRAM |  | Jhargram Division | Model Water Supply System for School Located within the command area of PWSS & Source Less School(106 nos) Beyond Command Area of PWSS for District Jhargram. | SM/10358 | School | Water Supply System at Different Source less school in Nayagram Block within Jhargram District under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer Nayagram block | ORD/000001/2023-2024 | 502/JHD | 13/04/2023 | 28/05/2023 | SUNIL KUMAR MANDAL | 14.43 | 12.66 | 87.7 | 100
5 | JHARGRAM |  | Jhargram Division | Model Water Supply System for School Located within the command area of PWSS & Source Less School(106 nos) Beyond Command Area of PWSS for District Jhargram. | SM/10358 | School | Surging, developing, washing & others allied works to rejuvenate the water sources at Manikapara High School to provide safe drinking water under Jhargram Dev. Block within Jhargram Division,PHE Dte. | Assistant Engineer |  | ORD/000043/2023-2024 | 385/JSD | 29/05/2023 | 13/06/2023 | SAURABH KAR | 0.75 | 0.75 | 100 | 100
6 | JHARGRAM |  | Jhargram Division | Model Water Supply System for School Located within the command area of PWSS & Source Less School(106 nos) Beyond Command Area of PWSS for District Jhargram. | SM/10358 | School | Water Supply System at Different Sourceless school in Gopiballavpur-II Block within Jhargram District under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer Gopiballavpur-II block | ORD/000030/2023-2024 | 856/JHD | 08/06/2023 | 08/07/2023 | MANNA COMPUTER | 10.58 | 7.26 | 68.65 | 100
7 | JHARGRAM |  | Jhargram Division | Model Water Supply System for School Located within the command area of PWSS & Source Less School(106 nos) Beyond Command Area of PWSS for District Jhargram. | SM/10358 | School | Sinking of Tube-wells and water supply arrangement at Ambihat Primary School in Gopiballavpur-II Block under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer Gopiballavpur-II block | ORD/000153/2023-2024 | 743/JSD | 17/08/2023 | 07/09/2023 | GOPESH DEY | 2.62 | 2.13 | 81.22 | 100
8 | JHARGRAM |  | Jhargram Division | Model Water Supply System for School Located within the command area of PWSS & Source Less School(106 nos) Beyond Command Area of PWSS for District Jhargram. | SM/10358 | School | Installation of 150 mm X 100 mm Dia. X 135 Mtr. DepthTube Well with Installation of Pumping Machinery for Jhargram Raj College Hostel at Jhargram Block within Jhargram District under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000344/2023-2024 | 965/JSD | 10/11/2023 | 01/12/2023 | MMS CONSTRUCTIONS PVT.LTD. | 4.53 | 4.23 | 93.33 | 100
9 | JHARGRAM |  | Jhargram Division | Model Water Supply System for School Located within the command area of PWSS & Source Less School(106 nos) Beyond Command Area of PWSS for District Jhargram. | SM/10358 | School | Water Supply System at Different Sourceless school in Gopiballavpur-I Block within Jhargram District under Jhargram Division PHE Dte.(Part-II)) 3 rd Call, (Ref eNIT_14 of 2022-23 2nd Call, SL No.-14) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000357/2023-2024 | 1997/JHD | 01/12/2023 | 15/01/2024 | BISHNU PADA NANDI | 27.7 | 26.96 | 97.35 | 100
10 | JHARGRAM |  | Jhargram Division | Model Water Supply System for School Located within the command area of PWSS & Source Less School(106 nos) Beyond Command Area of PWSS for District Jhargram. | SM/10358 | School | Installation of 150 mm X 100 mm Dia. X 135 Mtr. DepthTube Well with Installation of Pumping Machinery for Rani Binod Manjari Govt. Girl's High School at Jhargram Block within Jhargram District under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000341/2023-2024 | 964/JSD | 10/11/2023 | 01/12/2023 | J.S.S. ENTERPRISE | 4.54 | 4.31 | 95.03 | 100
11 | JHARGRAM |  | Jhargram Division | Model Water Supply System for School Located within the command area of PWSS & Source Less School(106 nos) Beyond Command Area of PWSS for District Jhargram. | SM/10358 | School | Water Supply System at Different Sourceless school in Gopiballavpur-1 Block within Jhargram District under Jhargram Division PHE Dte. (Part-1) 3rd Call (Ref. eNit No._14 of 2022-23 2nd call SL-13) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000360/2023-2024 | 1996/JHD | 01/12/2023 | 15/01/2024 | AMITAVA CHAKRABORTY | 25.72 | 23.28 | 90.5 | 55
12 | JHARGRAM |  | Jhargram Division | Model Water Supply System for School Located within the command area of PWSS & Source Less School(106 nos) Beyond Command Area of PWSS for District Jhargram. | SM/10358 | School | Water Supply System at Different Sourceless school in Jamboni Block within Jhargram District under Jhargram Division PHE Dte. 4th Call, (1st Call Ref eNIT_09 of 2022-23, SL No.-16, 2nd Call Ref eNIT_14 of 2022-23, SL No.-16, 3rd call Ref eNIT_12 of 2023-24, SL No.-7 ) | Assistant Engineer | Junior Engineer-III | ORD/000013/2024-2025 | 914/JHD | 08/07/2024 | 22/08/2024 | RAMASISH ENTERPRISE | 30.37 | 0 | 0 | 65
13 | JHARGRAM |  | Jhargram Division | Model Water Supply System for School Located within the command area of PWSS & Source Less School(106 nos) Beyond Command Area of PWSS for District Jhargram. | SM/10358 | School | EXTENTION PIPELINE AND STAND POST FOR DIFFERENT NEWLY CONSTRUCTED SUB-HEALTH CENTER UNDER DIFFERENT BLOCK UNDER JHARGRAM DIVISION, P.H.E. DTE. | Assistant Engineer | Junior Engineer-II | ORD/000432/2023-2024 | 91/JSD | 06/02/2024 | 07/03/2024 | MAA CONSTRUCTION | 2.09 | 2.09 | 99.95 | 60
14 | JHARGRAM |  | Jhargram Division | Model Water Supply System for School Located within the command area of PWSS & Source Less School(106 nos) Beyond Command Area of PWSS for District Jhargram. | SM/10358 | School | Installation of 150 mm X 100 mm Dia. X 135 Mtr. DepthTube Well with Installation of Pumping Machinery of Jhargram Raj College Ladies Hostel at Jhargram District under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000038/2024-2025 | 751/JSD | 06/08/2024 | 27/08/2024 | HONEY CONSTRUCTION | 4.62 | 3.67 | 79.47 | 100
15 | JHARGRAM |  | Jhargram Division | Model Water Supply System for School Located within the command area of PWSS & Source Less School(106 nos) Beyond Command Area of PWSS for District Jhargram. | SM/10358 | School | Water Supply System at Different Source less school in Jhargram Block within Jhargram District under Jhargram Division PHE Dte. | Assistant Engineer Headquarter | Junior Engineer, Jhargram Sub-Division | ORD/000121/2025-2026 | 1497/JHD | 09/07/2025 | 23/08/2025 | PRANTIK DRILLING AGENCY | 0 | 0 | NAN | 0
Total | [13 empty] | 178.07 | 131.37 | 73.78